## Sheet1
TaskType | Label
None | 8203 - Construction Stage Mobile Phone Network
FINISH_MILESTONE | 822 to complete lining for 823A connection (Down Track)
FINISH_MILESTONE | 822 to complete lining for 823A connection (Up Track)
None | 823A As-built Programme
FINISH_MILESTONE | 823B to complete East Culvert for 823A connection
None | 827 - Supply and Installation of Cross Passage Doors
None | 830 - Trackwork and Overhead Line System
None | 841A - Signalling System - Trackside Equipment
None | 841B - Signalling System - Train Borne Equipment
None | 843 - Tunnel Environmental Control System
None | 844 - 11kV Power Distribution
None | 846 - Trackside Auxiliaries
None | 849 - Radio Communication System
None | 850 - Passenger Mobile Communications Systems
None | 851 - Fixed Communication System
None | ABWF Works
TT_TASK | AIP Design - Prepare & Submit
TT_TASK | AIP Design - Prepare and Submit
TT_TASK | AIP Design - Response to comments and Resubmit
TT_TASK | AIP Design - Review & Approval Period (by MTR)
TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities)
TT_TASK | AIP Design - Review and Approval Period (by MTRC)
TT_TASK | AIP Design - Review and Approval Period (by MTRC)
TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities)
None | Access Dates for Designated Contractors
None | Access Dates for Works Areas
TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft
TT_TASK | Access opening to DC (DC access period)
TT_TASK | Air Quality Management Plan [P22.4.3]
START_MILESTONE | All cross passages within ERS to Tse Uk Tsuen Tunnels, down track, for door frame installation
START_MILESTONE | All cross passages within ERS to Tse Uk Tsuen Tunnels, uptrack, for door installation
START_MILESTONE | All cross passages within Tai Kong Po to ERS Tunnels,down track for door installation
START_MILESTONE | All cross passages within Tai Kong Po to ERS Tunnels,up track for door installation
TT_TASK | Application of power supply, environmental permits and construction substation
TT_TASK | Application of tree transplant
None | Approach Tunnel Roof
FINISH_MILESTONE | Approval of Contractor's Submission - Environmental Management Plan (G5.1.10)
FINISH_MILESTONE | Approval of Contractor's Submission - Method of Construction (G12.1.1)
FINISH_MILESTONE | Approval of Contractor's Submission - Preliminary Master Programme (G4.6.1)
FINISH_MILESTONE | Approval of Contractor's Submission - Quality Plan (G9.2.1)
FINISH_MILESTONE | Approval of Contractor's Submission - Submission Schedule (G12.11.1)
FINISH_MILESTONE | Approval of Contractor's Submission - Time Chainage Programme (G4.11.1)
TT_TASK | Approval of Detailed Interface Plan
FINISH_MILESTONE | Approval of Operating and Maintenance Manuals and as-built drawings for the Whole of the Works
FINISH_MILESTONE | Approval of detailed Interface Requirements Specifications with the Designated Contractors (Appendix W of the PS)
FINISH_MILESTONE | Approval of draft Operating and Maintenance Manuals and draft as-built drawings for Whole of the Works
FINISH_MILESTONE | Approval of tunnel lining design
FINISH_MILESTONE | Approval of tunnel segment mould design
TT_TASK | Approval period of AIR & AAP
None | Archaeology Survey and Rescue Operation (South Tunnels Area)
TT_TASK | Asbestos abatement works
TT_TASK | Assemble and set up back-up plant for final drive
TT_TASK | Assemble, T&C of TBM
TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1]
None | Backfilling
TT_TASK | Backfilling
TT_TASK | Backfilling (1344m3)
TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day)
TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3)
TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil
TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3)
TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19)
TT_TASK | Backfilling between tunnels (2000m3)
TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day)
TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil)
TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3)
TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil)
TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18)
TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil)
TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3)
TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil)
TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3)
TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil)
TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3)
TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3)
TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3)
TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil)
TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil)
TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil)
TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD)
TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3)
TT_TASK | Backfilling up to ground level
TT_TASK | Backfilling up top S0 Soffit
TT_TASK | Backfilling up top S1 Soffit
None | Base Slab
None | Bay 10
None | Bay 11
None | Bay 12
None | Bay 13
None | Bay 1a
None | Bay 1b
None | Bay 2a
None | Bay 2b
None | Bay 3a
None | Bay 3b
None | Bay 4a
None | Bay 4b
None | Bay 5a
None | Bay 5b
None | Bay 6