## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd
2 |  | 826 - HGP to Mai Po Tunnels, Revised Master Prog | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
3 |  | Tender and Contract Details | Wed Mar 10 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
4 |  | Tender Actions | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
5 | START_MILESTONE | Contract Award (LoA) | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
6 |  | Critical Contract Dates | Mon Mar 15 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
7 | START_MILESTONE | Stated Contract Commencement Date (Cl 64) | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 15 08:00:00 IST 2010
8 | FINISH_MILESTONE | Table 3, Ref 3A - Delivery of the first TBM to HGP | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
9 | FINISH_MILESTONE | Table 3, Ref 3B - All works in Works Area 1.6 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
10 | FINISH_MILESTONE | Table 3, Ref 3C - Delivery of the second TBM to HGP | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
11 | FINISH_MILESTONE | Table 4, Ref 4A - Achieve Deg. 1 for both Up and Down Track Tunnels | Thu Mar 31 17:00:00 IDT 2016 | Thu Mar 31 17:00:00 IDT 2016
12 | FINISH_MILESTONE | Table 1 - Completion of the Whole of the Works (wk13/2015) | Thu Jun 01 17:00:00 IDT 2017 | Thu Jun 01 17:00:00 IDT 2017
13 |  | Other Programme Data | Thu May 09 08:00:00 IDT 2013 | Sat Apr 01 07:00:00 IDT 2017
14 | START_MILESTONE | GSG Contractor to hand over S623 to Cont' 826 at HK Boundary | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013
15 | START_MILESTONE | GSG Contractor to hand over S624 to Cont' 826 at HK Boundary | Thu May 09 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
16 | START_MILESTONE | Notification to Contract 846 for cable bracket installation | Sun Nov 22 07:00:00 IST 2015 | Sun Nov 22 07:00:00 IST 2015
17 | FINISH_MILESTONE | Provision of TBM Retrieval Shaft at MPV | Wed Oct 01 07:00:00 IDT 2014 | Wed Oct 01 07:00:00 IDT 2014
18 | START_MILESTONE | OHL Power On, by Designated Contractor 830 | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
19 |  | Access Dates for Designated Contractors | Sun May 01 07:00:00 IDT 2016 | Thu Dec 01 07:00:00 IST 2016
20 | START_MILESTONE | 827, X-passage Doors - Door Frame Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
21 | START_MILESTONE | 827, X-passage Doors - Doors Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
22 | START_MILESTONE | 830, Trackwork and OHL - Up-track | Sun May 01 07:00:00 IDT 2016 | Sun May 01 07:00:00 IDT 2016
23 | START_MILESTONE | 830, Trackwork and OHL - Down-track | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
24 | START_MILESTONE | 841A, Signalling System, Trackside Eqpt - Both tunnels | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
25 | START_MILESTONE | 846, Trackside Aux - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
26 | START_MILESTONE | 849, Radio Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
27 | START_MILESTONE | 850, Passenger Mobile Communications Systems - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
28 | START_MILESTONE | 851, Fixed Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
29 | START_MILESTONE | 8203, Constrn Stage Mobile Phone Network - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
30 |  | Interface Contractor Programme - GSG | Wed Dec 01 08:00:00 IST 2010 | Sat Mar 01 07:00:00 IST 2014
31 | FINISH_MILESTONE | Complete Huanggang Park shaft construction | Mon Mar 26 08:00:00 IST 2012 | Mon Mar 26 08:00:00 IST 2012
32 | TASK_DEPENDENT | Drill & Blast Tunnel (to HK) | Wed Dec 01 08:00:00 IST 2010 | Tue Sep 27 08:00:00 IDT 2011
33 | TASK_DEPENDENT | S623 Excavate 242m (SZ) (s.rock) | Tue Jul 03 08:00:00 IDT 2012 | Sat Oct 06 08:00:00 IST 2012
34 | TASK_DEPENDENT | S623 Conduct General Maintenance | Sun Oct 07 08:00:00 IST 2012 | Wed Oct 10 08:00:00 IST 2012
35 | TASK_DEPENDENT | S623 Excavate 242m (SZ) (m.rock/total 484m) | Wed Oct 10 08:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012
36 | TASK_DEPENDENT | S623 Conduct General Maintenance | Sun Nov 18 08:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012
37 | TASK_DEPENDENT | S623 Excavate 220m (SZ) (s.rock/total 704m) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 29 08:00:00 IST 2012
38 | TASK_DEPENDENT | S623 Conduct General Maintenance | Tue Jan 08 08:00:00 IST 2013 | Sat Jan 12 08:00:00 IST 2013
39 | TASK_DEPENDENT | S623 Excavate 150m (SZ) (m.rock/total 854m) | Sat Jan 12 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
40 | TASK_DEPENDENT | S623 Conduct General Maintenance | Wed Feb 20 08:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013
41 | TASK_DEPENDENT | S623 Excavate 50m (SZ) (s.rock/total 904m) | Thu Feb 28 08:00:00 IST 2013 | Fri Mar 08 08:00:00 IST 2013
42 | TASK_DEPENDENT | S623 Conduct General Maintenance | Sun Apr 21 08:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013
43 | TASK_DEPENDENT | S623 Excavate 100m (SZ) (rock/total 1004m) | Mon Apr 22 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
44 | TASK_DEPENDENT | S623 Conduct General Maintenance | Sat Jun 08 10:38:00 IDT 2013 | Mon Jun 10 10:38:00 IDT 2013
45 | TASK_DEPENDENT | S623 Excavate 470m (SZ) (rock/total 1474m) | Wed May 15 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
46 | TASK_DEPENDENT | S623 Conduct General Maintenance | Fri Sep 13 08:00:00 IDT 2013 | Sun Sep 15 08:00:00 IDT 2013
47 | TASK_DEPENDENT | S623 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Aug 15 08:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013
48 | TASK_DEPENDENT | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013
49 | TASK_DEPENDENT | S623 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Oct 31 08:00:00 IST 2013 | Sun Nov 10 08:00:00 IST 2013
50 | TASK_DEPENDENT | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013
51 | TASK_DEPENDENT | S623 Excavate 84m (SZ) (c.rock/total 1856m) | Thu Oct 31 08:00:00 IST 2013 | Sat Nov 02 08:00:00 IST 2013
52 | FINISH_MILESTONE | Complete TBM Excavation Down Track (SZ) | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 08:00:00 IST 2013
53 | TASK_DEPENDENT | S624 Excavate 100m (SZ) (s.rock) | Mon Nov 05 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
54 | TASK_DEPENDENT | S624 Conduct General Maintenance | Mon Dec 10 08:00:00 IST 2012 | Thu Dec 13 08:00:00 IST 2012
55 | TASK_DEPENDENT | S624 Excavate 142m (SZ) (s.rock/total 242m) | Thu Dec 13 08:00:00 IST 2012 | Sun Jan 06 08:00:00 IST 2013
56 | TASK_DEPENDENT | S624 Conduct General Maintenance | Sat Jan 05 08:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013
57 | TASK_DEPENDENT | S624 Excavate 242m (SZ) (m.rock/total 484m) | Tue Jan 08 08:00:00 IST 2013 | Sun Feb 17 08:00:00 IST 2013
58 | TASK_DEPENDENT | S624 Conduct General Maintenance | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 08:00:00 IST 2013
59 | TASK_DEPENDENT | S624 Excavate 220m (SZ) (s.rock/total 704m) | Tue Feb 19 08:00:00 IST 2013 | Thu Mar 28 08:00:00 IST 2013
60 | TASK_DEPENDENT | S624 Conduct General Maintenance | Fri Jun 28 08:58:00 IDT 2013 | Mon Jul 01 08:58:00 IDT 2013
61 | TASK_DEPENDENT | S624 Excavate 150m (SZ) (m.rock/total 854m) | Tue Jul 02 08:58:00 IDT 2013 | Mon Jul 22 08:58:00 IDT 2013
62 | TASK_DEPENDENT | S624 Conduct General Maintenance | Wed Jul 24 08:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013
63 | TASK_DEPENDENT | S624 Excavate 50m (SZ) (s.rock/total 904m) | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
64 | TASK_DEPENDENT | S624 Conduct General Maintenance | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 08:00:00 IDT 2013
65 | TASK_DEPENDENT | S624 Excavate 100m (SZ) (s/m.rock/total 1004m) | Tue Aug 06 08:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013
66 | TASK_DEPENDENT | S624 Conduct General Maintenance | Mon Aug 26 08:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013
67 | TASK_DEPENDENT | S624 Excavate 470m (SZ) (s/m.rock/total 1474m) | Fri Sep 13 08:00:00 IDT 2013 | Sun Dec 01 08:00:00 IST 2013
68 | TASK_DEPENDENT | S624 Conduct General Maintenance | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
69 | TASK_DEPENDENT | S624 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Jan 30 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
70 | TASK_DEPENDENT | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
71 | TASK_DEPENDENT | S624 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Jan 30 08:00:00 IST 2014 | Sun Feb 09 08:00:00 IST 2014
72 | TASK_DEPENDENT | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
73 | TASK_DEPENDENT | S624 Excavate 92m (SZ) (c.rock/total 1864m) | Thu Jan 30 08:00:00 IST 2014 | Tue Feb 11 08:00:00 IST 2014
74 | FINISH_MILESTONE | Complete TBM Excavation Up Track (SZ) | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
75 |  | Interface Contractor Programme - 825 | Tue Sep 21 08:00:00 IST 2010 | Thu Dec 01 07:00:00 IST 2016
76 | FINISH_MILESTONE | TBM shaft for Contract 826 within Works Area 1.5 | Tue Jun 09 11:00:00 IDT 2015 | Tue Jun 09 11:00:00 IDT 2015
77 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - first time | Tue Sep 21 08:00:00 IST 2010 | Tue Sep 21 08:00:00 IST 2010
78 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - second time | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
79 | TASK_DEPENDENT | Cut & cover tunnel Bay 1 tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 20 08:00:00 IST 2014
80 | TASK_DEPENDENT | Cut & cover tunnel Bay 2 tunnel construction | Sat Nov 30 08:00:00 IST 2013 | Mon Feb 17 08:00:00 IST 2014
81 | FINISH_MILESTONE | 826 to complete all works at interface and allow 825 access | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
82 | TASK_DEPENDENT | 825 complete stitch joint to 826 tunnel | Sun May 01 07:00:00 IDT 2016 | Sat Jun 25 17:00:00 IDT 2016
83 | FINISH_MILESTONE | Return of Works Area 1.5 to 825 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
84 |  | Interface Contractor Programme - 830 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
85 | TASK_DEPENDENT | Allow concrete pumping access for Contract 830 within Works Area 1.5 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
86 |  | Works Areas | Mon Sep 20 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
87 |  | Access Dates | Mon Sep 20 08:00:00 IST 2010 | Thu Nov 05 07:00:00 IST 2015
88 | START_MILESTONE | Works Area 1.3 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
89 | START_MILESTONE | Works Area 1.4A (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
90 | START_MILESTONE | Works Area 1.4B first time (36/2010, 13 Sep 10) | Mon Sep 20 08:00:00 IST 2010 | Mon Sep 20 08:00:00 IST 2010
91 | START_MILESTONE | Works Area 1.4B second time (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
92 | START_MILESTONE | Works Area 1.5 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
93 | START_MILESTONE | Works Area 1.6 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
94 | START_MILESTONE | Works Area 1.16 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
95 | START_MILESTONE | Works Area 1.17 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
96 | START_MILESTONE | Works Area 1.19 (47/2010, 29 Nov 10) | Mon Nov 29 08:00:00 IST 2010 | Mon Nov 29 08:00:00 IST 2010
97 | START_MILESTONE | Works Area 1.21 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
98 |  | Return Dates | Fri Dec 17 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
99 | FINISH_MILESTONE | Works Area 1.3 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
100 | FINISH_MILESTONE | Works Area 1.4A (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
101 | FINISH_MILESTONE | Works Area 1.4B first time (01/2011, 9 Jan 11) | Fri Dec 17 08:00:00 IST 2010 | Fri Dec 17 08:00:00 IST 2010
102 | FINISH_MILESTONE | Works Area 1.4B second time (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
103 | FINISH_MILESTONE | Works Area 1.5 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
104 | FINISH_MILESTONE | Works Area 1.6 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
105 | FINISH_MILESTONE | Works Area 1.16 (36/2013, 8 Sep 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
106 | FINISH_MILESTONE | Works Area 1.17 (50/2013, 15 Dec 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
107 | FINISH_MILESTONE | Works Area 1.19 (10 May 16) | Tue Feb 28 17:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017
108 | FINISH_MILESTONE | Works Area 1.21 (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
109 |  | Specified Milestone Dates | Sun Apr 25 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
110 |  | Cost Centre A | Sun Jun 27 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
111 | FINISH_MILESTONE | A1 (25/2010, 27 Jun 10) - Contractor's Submissions | Sun Jun 27 08:00:00 IDT 2010 | Sun Jun 27 08:00:00 IDT 2010
112 | FINISH_MILESTONE | A2 (51/2010, 26 Dec 10) - Approval of TBM Tunnelling method Statement | Wed Jan 05 08:00:00 IST 2011 | Wed Jan 05 08:00:00 IST 2011
113 | FINISH_MILESTONE | A3 (08/2011, 27 Feb 11) - Implementation of Specified Plans and Programming | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
114 | FINISH_MILESTONE | A4 (38/2011, 25 Sep 11) - Delivery of 2 nos. TBM to HGP Launching Shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
115 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of the MS of Construction of Cross Passages | Thu Feb 23 08:00:00 IST 2012 | Thu Feb 23 08:00:00 IST 2012
116 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of Detailed Interface Require Specific with Designated Contractor | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
117 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Implementation of Specified Plans | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
118 | FINISH_MILESTONE | A6 (08/2012, 26 Feb 12) - Implementation of Specified Plans and Programme | Fri Feb 24 08:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012
119 | FINISH_MILESTONE | A7 (25/2012, 24 Jun 12) - Approval of Detailed Interface Require Specific with Designated Contractor | Tue Jul 31 08:00:00 IDT 2012 | Tue Jul 31 08:00:00 IDT 2012
120 | FINISH_MILESTONE | A8 (34/2012, 26 Aug 12) - Implementation of Specified Plans | Wed Aug 22 08:00:00 IDT 2012 | Wed Aug 22 08:00:00 IDT 2012
121 | FINISH_MILESTONE | *A9 (48/2014, 30 Nov 14) - Complete 28% of the 1st tunnel drive | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 01 07:00:00 IST 2014
122 | FINISH_MILESTONE | A9a (08/2013, 24 Feb 13) - Implementation of Specific Plans and Program | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
123 | FINISH_MILESTONE | *A9b (08/2014, 1 May 14) - Complete 15% of the 1st tunnel drive | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
124 | FINISH_MILESTONE | A10 (34/2013, 25 Aug 13) - Implementation of Specific Plans | Tue Jul 15 17:00:00 IDT 2014 | Tue Jul 15 17:00:00 IDT 2014
125 | FINISH_MILESTONE | *A11 (51/2015, 27 Dec 15) - Achieve Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
126 | FINISH_MILESTONE | A12 (32/2014, 10 Aug 14) - Approval of Draft O & M Manuals and Draft As-built drawings | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
127 | FINISH_MILESTONE | A13 (06/2015, 8 Feb 15) - Approval of Operating & Maintenance Mauls | Fri Feb 24 17:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017
128 |  | Cost Centre B | Sun Apr 25 08:00:00 IDT 2010 | Fri Apr 01 07:00:00 IDT 2016
129 | FINISH_MILESTONE | B1.1 (16/2010, 25 Apr 10) - Provide Evidence that TBM | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
130 | FINISH_MILESTONE | B1a (25/2010, 27 Jun 10) - On-demand bond or bank guarantee | Sat Jun 26 08:00:00 IDT 2010 | Sat Jun 26 08:00:00 IDT 2010
131 | FINISH_MILESTONE | B1.2 (28/2010, 18 Jul 10) - Provide Evidence that the STP | Thu Jul 29 08:00:00 IDT 2010 | Thu Jul 29 08:00:00 IDT 2010
132 | FINISH_MILESTONE | B2 (21/2011, 29 May 11) - Delivery of the 1st TBM | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
133 | FINISH_MILESTONE | B2a (38/2011, 25 Sep 11) - Delivery of the 2nd TBM | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
134 | FINISH_MILESTONE | B3 (49/2013, 8 Dec 13) - Complete Final Disassembly of TBM | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
135 |  | Cost Centre C (UT/S624) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
136 | FINISH_MILESTONE | C1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
137 | FINISH_MILESTONE | *C2 (17/2014, 27 Apr 14) - Complete 10% Tunnel Drive & 70% Segments | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
138 | FINISH_MILESTONE | *C3 (52/2014, 28 Dec 14) - Complete 40% Tunnel Drive & 95% Segments | Mon Feb 23 07:00:00 IST 2015 | Mon Feb 23 07:00:00 IST 2015
139 | FINISH_MILESTONE | *C4 (26/2015, 28 Jun 15) - Complete 100% Tunnel Drive | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
140 | FINISH_MILESTONE | *C5 (35/2015, 30 Aug 15) -Complete 50% Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
141 | FINISH_MILESTONE | *C6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
142 | FINISH_MILESTONE | C7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
143 |  | Cost Centre D (DT/S623) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
144 | FINISH_MILESTONE | D1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
145 | FINISH_MILESTONE | D2 (10/2013, 10MAR13) - Complete 5% Tunnel Drive & 40% Segments | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
146 | FINISH_MILESTONE | *D3 (48/2014, 30 Nov 14) -Complete 28% Tunnel Drive & 85% Segments | Tue Jun 30 07:00:00 IDT 2015 | Tue Jun 30 07:00:00 IDT 2015
147 | FINISH_MILESTONE | *D4 (35/2015, 30 Aug 15) -Complete 100% Tunnel Drive | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
148 | FINISH_MILESTONE | *D5 (43/2015, 25 Oct 15) - Complete 50% of Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
149 | FINISH_MILESTONE | *D6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
150 | FINISH_MILESTONE | D7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
151 |  | Cost Centre E (CP) | Thu Dec 16 08:00:00 IST 2010 | Sat Dec 31 17:00:00 IST 2016
152 | FINISH_MILESTONE | E1 (01/2011, 9 Jan 11) - Complete Ground Treatment | Thu Dec 16 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
153 | FINISH_MILESTONE | E2 (08/2011, 27 Feb 11) - Submit instrumentation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
154 | FINISH_MILESTONE | E3 (34/2011, 28 Aug 11) - Submit instrumentation | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
155 | FINISH_MILESTONE | E4 (08/2012, 26 Feb 12) - Submit instrumentation | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 08:00:00 IST 2012
156 | FINISH_MILESTONE | E5 (34/2012, 26 Aug 12) - Submit instrumentation | Sat Aug 25 08:00:00 IDT 2012 | Sat Aug 25 08:00:00 IDT 2012
157 | FINISH_MILESTONE | E6 (08/2013, 24 Feb 13) - Submit instrumentation | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
158 | FINISH_MILESTONE | E7 (48/2013, 30 Nov 13) - Major ground treatment plant for CPs | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 01 07:00:00 IST 2015
159 | FINISH_MILESTONE | E8 (13/2015, 29 Mar 15) - Complete 4 Cross Passage Ground Treatment | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
160 | FINISH_MILESTONE | *E9 (51/2015, 20 Dec 15) - Deg 1 Completion in Cross Passage | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
161 | FINISH_MILESTONE | E10 (25/2016) - All Works Complete | Sat Dec 31 17:00:00 IST 2016 | Sat Dec 31 17:00:00 IST 2016
162 |  | Construction and Site Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
163 |  | Surface Operations in Works Areas | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
164 |  | Huanggang Park | Tue Nov 02 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
165 | TASK_DEPENDENT | Establish MTRC Project Office in Shenzhen | Tue Nov 02 08:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010
166 | TASK_DEPENDENT | Establish 826 HGP Site Office | Tue Nov 30 08:00:00 IST 2010 | Mon Jan 17 08:00:00 IST 2011
167 | TASK_DEPENDENT | University Games Period | Mon Aug 01 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
168 | TASK_DEPENDENT | Operation and maintenance of ground support facilities during tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Tue Oct 31 08:00:00 IST 2017
169 |  | Mai Po Retrieval Shaft | Fri Aug 06 08:00:00 IDT 2010 | Tue Apr 21 08:00:00 IDT 2015
170 |  | Ground Treatment Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Feb 01 08:00:00 IST 2011
171 | FINISH_MILESTONE | Submit Inspection and Testing Plan for ground treatment works | Fri Aug 06 08:00:00 IDT 2010 | Fri Aug 06 08:00:00 IDT 2010
172 | TASK_DEPENDENT | Engineer's review on Inspection and Testing Plan | Fri Aug 06 08:00:00 IDT 2010 | Fri Sep 03 08:00:00 IDT 2010
173 | TASK_DEPENDENT | Establish Works Area 1.4B with 825 Contractor | Mon Sep 20 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
174 | TASK_DEPENDENT | Set up grouting plant | Tue Oct 05 08:00:00 IST 2010 | Fri Oct 15 08:00:00 IST 2010
175 | TASK_DEPENDENT | Drilling - Down Track tunnel | Thu Oct 07 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
176 | TASK_DEPENDENT | Drilling - Up Track tunnel | Mon Oct 18 08:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010
177 | TASK_DEPENDENT | TAM Grouting works - Down Track tunnel | Thu Nov 04 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
178 | TASK_DEPENDENT | TAM Grouting works - Up Track tunnel | Thu Nov 11 08:00:00 IST 2010 | Sat Nov 27 08:00:00 IST 2010
179 | TASK_DEPENDENT | TAM Grouting works - Down Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
180 | TASK_DEPENDENT | TAM Grouting works - Up Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
181 | TASK_DEPENDENT | Permeability testing - Down Track tunnel | Tue Dec 07 08:00:00 IST 2010 | Mon Dec 13 08:00:00 IST 2010
182 | TASK_DEPENDENT | Permeability testing - Up Track tunnel | Wed Dec 08 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
183 | TASK_DEPENDENT | Demobilise grout plant | Mon Dec 13 08:00:00 IST 2010 | Sat Dec 18 08:00:00 IST 2010
184 | TASK_DEPENDENT | Clear Works Area 1.4B for 825 Contractor's D.Wall | Mon Dec 13 08:00:00 IST 2010 | Wed Dec 22 08:00:00 IST 2010
185 | TASK_DEPENDENT | Install instrumentation and monitoring equipment | Thu Oct 28 08:00:00 IST 2010 | Tue Feb 01 08:00:00 IST 2011
186 |  | Jet Grouting Works for TBM Break-out | Tue Dec 31 08:00:00 IST 2013 | Tue Nov 18 08:00:00 IST 2014
187 | TASK_DEPENDENT | Submit Method Statement for Jet Grouting Works | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 27 08:00:00 IST 2014
188 | TASK_DEPENDENT | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
189 | TASK_DEPENDENT | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 22 08:00:00 IST 2014
190 | TASK_DEPENDENT | Trial of Jet grouting | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 27 08:00:00 IST 2014
191 | TASK_DEPENDENT | Jet Grouting Works | Fri Jul 18 08:00:00 IDT 2014 | Tue Nov 18 08:00:00 IST 2014
192 |  | Ground Freezing Plant | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
193 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Ground freezing | Tue Mar 24 08:00:00 IST 2015 | Tue Mar 24 08:00:00 IST 2015
194 | TASK_DEPENDENT | Engineer's review on Inspection and Testing Plan | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
195 |  | TBM Drives from Boundary to Mai Po Shaft | Fri May 10 08:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
196 |  | Down Track - Ch.115+929 to Ch.117+400 | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 16 17:00:00 IST 2015
197 | TASK_DEPENDENT | Anticipated handover at Boundary from GSG Contractor | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
198 | TASK_DEPENDENT | Continue S623 drive, ch. 115+929 to ch. 115+950 in soil | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013
199 | TASK_DEPENDENT | Continue S623 drive, ch. 115+950 to ch. 115+983 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Sat Jan 04 08:00:00 IST 2014
200 | TASK_DEPENDENT | Continue S623 drive, ch. 115+983 to ch. 116+050 in soil | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 08 08:00:00 IST 2014
201 | TASK_DEPENDENT | Continue S623 drive, ch. 116+050 to ch. 116+213 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
202 | TASK_DEPENDENT | Continue S623 drive, ch. 116+213 to ch. 116+230 in soil | Tue Apr 01 08:00:00 IDT 2014 | Thu Apr 03 08:00:00 IDT 2014
203 | TASK_DEPENDENT | Continue S623 drive, ch. 116+230 to ch. 116+260 in marble | Tue Apr 01 08:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014
204 | TASK_DEPENDENT | Continue S623 drive, ch. 116+260 to ch. 116+284 in marble | Tue Jul 01 08:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014
205 | TASK_DEPENDENT | TBM Cutter Head Repair & S624 Overtaking Stoppage | Fri Aug 01 08:00:00 IDT 2014 | Fri Oct 24 08:00:00 IDT 2014
206 | TASK_DEPENDENT | Continue S623 drive, ch. 116+284 to ch. 116+319 in marble | Fri Nov 21 07:00:00 IST 2014 | Mon Dec 01 17:00:00 IST 2014
207 | TASK_DEPENDENT | Continue S623 drive, ch. 116+319 to ch. 116+349 in marble | Wed Feb 04 07:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
208 | TASK_DEPENDENT | Continue S623 drive, ch. 116+349 to ch. 116+379 in marble | Sun Feb 01 07:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
209 | TASK_DEPENDENT | Continue S623 drive, ch. 116+379 to ch. 116+408 in marble | Sun Mar 01 07:00:00 IST 2015 | Thu Mar 05 01:00:00 IST 2015
210 | TASK_DEPENDENT | Continue S623 drive, ch. 116+408 to ch. 116+430 in marble | Sun Mar 01 07:00:00 IST 2015 | Sat Mar 07 17:00:00 IST 2015
211 | TASK_DEPENDENT | Continue S623 drive, ch. 116+430 to ch. 116+600 in soil | Sun Mar 01 07:00:00 IST 2015 | Mon Mar 30 17:00:00 IDT 2015
212 | TASK_DEPENDENT | Continue S623 drive, ch. 116+600 to ch. 116+694 in soil | Fri Jul 17 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
213 | TASK_DEPENDENT | Continue S623 drive, ch. 116+694 to ch. 116+927 in Alluvial zone | Tue Jun 30 07:00:00 IDT 2015 | Thu Sep 17 17:00:00 IDT 2015
214 | TASK_DEPENDENT | Continue S623 drive, ch. 116+927 to ch. 116+945 in soil | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
215 | TASK_DEPENDENT | Continue S623 drive, ch. 116+945 to ch. 117+400 in soil | Tue Sep 29 07:00:00 IDT 2015 | Wed Dec 16 17:00:00 IST 2015
216 | TASK_DEPENDENT | Pre-coring at diaphragm wall after TBM S623 arrival | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
217 | TASK_DEPENDENT | TBM Breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
218 |  | S623 TBM Removal | Thu Oct 22 07:00:00 IDT 2015 | Thu Dec 01 07:00:00 IST 2016
219 | TASK_DEPENDENT | Move TBM S623 front portion to cradle | Thu Oct 22 07:00:00 IDT 2015 | Tue Oct 27 17:00:00 IST 2015
220 | TASK_DEPENDENT | Weld additional bracing brackets corbels | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
221 | TASK_DEPENDENT | Install cradle on lateral shifting system | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
222 | TASK_DEPENDENT | Move and shift TBM to dismantle location | Thu Apr 07 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
223 | TASK_DEPENDENT | Dismantle Cutter Head & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
224 | TASK_DEPENDENT | Dismantle TBM rear & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
225 | TASK_DEPENDENT | Dismantle segment installation machine & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
226 | TASK_DEPENDENT | Dismantle TBM middle sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
227 | TASK_DEPENDENT | Dismantle TBM front sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
228 | TASK_DEPENDENT | Dismantle S623 Link Bridge & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
229 | TASK_DEPENDENT | Dismantle S623 Wagon #1 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
230 | TASK_DEPENDENT | Dismantle S623 Wagon #2 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
231 | TASK_DEPENDENT | Dismantle S623 Wagon #3 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
232 | TASK_DEPENDENT | Dismantle S623 Wagon #4 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
233 | TASK_DEPENDENT | Dismantle S623 Wagon #5 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
234 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N1 | Thu Jun 23 07:00:00 IDT 2016 | Thu Jun 23 07:00:00 IDT 2016
235 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N2 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
236 | TASK_DEPENDENT | Site clearance | Fri Apr 01 07:00:00 IDT 2016 | Tue Sep 27 17:00:00 IDT 2016
237 |  | Up Track - Ch.115+940 to Ch.117+413 | Fri May 10 08:00:00 IDT 2013 | Fri Oct 09 17:00:00 IDT 2015
238 | TASK_DEPENDENT | Anticipated handover at Boundary from GSG Contractor | Fri May 10 08:00:00 IDT 2013 | Sat May 11 08:00:00 IDT 2013
239 | TASK_DEPENDENT | Continue S624 drive, ch. 115+939 to ch. 115+950 in soil | Fri May 09 08:00:00 IDT 2014 | Sat May 10 08:00:00 IDT 2014
240 | TASK_DEPENDENT | Continue S624 drive, ch. 115+950 to ch. 115+987 in mixed ground | Fri May 09 08:00:00 IDT 2014 | Tue May 13 08:00:00 IDT 2014
241 | TASK_DEPENDENT | Continue S624 drive, ch. 115+987 to ch. 116+050 in soil | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 08:00:00 IDT 2014
242 | TASK_DEPENDENT | Continue S624 drive, ch. 116+050 to ch. 116+226 in mixed ground | Sun Jun 01 08:00:00 IDT 2014 | Wed Jul 02 08:00:00 IDT 2014
243 | TASK_DEPENDENT | Continue S624 drive, ch. 116+226 to ch. 116+240 in soil/marble | Fri Aug 01 08:00:00 IDT 2014 | Sun Aug 03 08:00:00 IDT 2014
244 | TASK_DEPENDENT | Continue S624 drive, ch. 116+240 to ch. 116+270 in marble | Fri Aug 01 08:00:00 IDT 2014 | Wed Aug 13 08:00:00 IDT 2014
245 | TASK_DEPENDENT | Continue S624 drive, ch. 116+270 to ch. 116+300 in marble | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014
246 | TASK_DEPENDENT | Continue S624 drive, ch. 116+300 to ch. 116+329 in marble | Wed Oct 01 08:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014
247 | TASK_DEPENDENT | Continue S624 drive, ch. 116+329 to ch. 116+358 in marble | Sat Nov 01 07:00:00 IST 2014 | Mon Nov 17 17:00:00 IST 2014
248 | TASK_DEPENDENT | Continue S624 drive, ch. 116+358 to ch. 116+388 in marble | Sun Nov 23 07:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
249 | TASK_DEPENDENT | Continue S624 drive, ch. 116+388 to ch. 116+415 in marble | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 02 17:00:00 IST 2015
250 | TASK_DEPENDENT | Continue S624 drive, ch. 116+415 to ch. 116+430 in soil/marble | Sun Jan 11 07:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
251 | TASK_DEPENDENT | Continue S624 drive, ch. 116+430 to ch. 116+600 in soil | Tue Jan 13 07:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
252 | TASK_DEPENDENT | Continue S624 drive, ch. 116+600 to ch. 116+850 in soil/Alluv. zone | Wed Jan 21 07:00:00 IST 2015 | Thu Mar 05 17:00:00 IST 2015
253 | TASK_DEPENDENT | Continue S624 drive, ch. 116+850 to ch. 116+930 in Alluv. zone | Tue Mar 31 07:00:00 IDT 2015 | Mon Apr 13 17:00:00 IDT 2015
254 | TASK_DEPENDENT | Continue S624 drive, ch. 116+930 to ch. 117+413 in soil at Mai Po | Thu Jul 16 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
255 | TASK_DEPENDENT | Pre-coring at diaphragm wall after TBM S624 arrival | Sat Aug 15 07:00:00 IDT 2015 | Mon Aug 17 17:00:00 IDT 2015
256 | TASK_DEPENDENT | TBM S624 breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
257 |  | TBM Removal Preparation | Mon Dec 01 07:00:00 IST 2014 | Wed Nov 11 17:00:00 IST 2015
258 | TASK_DEPENDENT | Prepare TTMS report for removal of TBM S624 & S623 | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 15 17:00:00 IST 2014
259 | TASK_DEPENDENT | Working Group Meeting & SLG Meeting | Fri Jan 16 07:00:00 IST 2015 | Wed Apr 15 17:00:00 IDT 2015
260 | TASK_DEPENDENT | Drawings' approval and endosement from RDO | Mon Feb 23 07:00:00 IST 2015 | Mon Mar 09 17:00:00 IST 2015
261 | TASK_DEPENDENT | Submit advance notice to the HK Police | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
262 | TASK_DEPENDENT | On stie preparation works | Mon Jul 13 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
263 | TASK_DEPENDENT | Proof drilling for water tightness test of jet grout block | Wed Jul 01 07:00:00 IDT 2015 | Tue Jul 07 17:00:00 IDT 2015
264 | TASK_DEPENDENT | Shaft bottom slab levelling | Fri Jul 24 07:00:00 IDT 2015 | Sat Jul 25 17:00:00 IDT 2015
265 | TASK_DEPENDENT | Moving device and cradle installation | Thu Jul 23 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
266 |  | S624 TBM Removal | Tue Sep 29 07:00:00 IDT 2015 | Sun Nov 08 17:00:00 IST 2015
267 | TASK_DEPENDENT | Move TBM S624 front portion to cradle | Tue Oct 13 07:00:00 IDT 2015 | Sun Oct 18 17:00:00 IDT 2015
268 | TASK_DEPENDENT | Weld additional bracing brackets corbels | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
269 | TASK_DEPENDENT | Install cradle on lateral shifting system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
270 | TASK_DEPENDENT | Move and shift TBM to dismantle location | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
271 | TASK_DEPENDENT | Dismantle Cutter Head & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
272 | TASK_DEPENDENT | Dismantle TBM front sheild & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
273 | TASK_DEPENDENT | Dismantle segment installation machine & Remove | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
274 | TASK_DEPENDENT | Dismantle TBM middle sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
275 | TASK_DEPENDENT | Dismantle TBM rear sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
276 | TASK_DEPENDENT | Dismantle S624 Link Bridge & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
277 | TASK_DEPENDENT | Dismantle S624 Wagon #1 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
278 | TASK_DEPENDENT | Dismantle S624 Wagon #2 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
279 | TASK_DEPENDENT | Dismantle S624 Wagon #3 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
280 | TASK_DEPENDENT | Dismantle S624 Wagon #4 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
281 | TASK_DEPENDENT | Dismantle S624 Wagon #5 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
282 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N1 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
283 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N2 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
284 |  | Cross Passages (HK) | Wed Oct 01 07:00:00 IDT 2014 | Thu Aug 04 17:00:00 IDT 2016
285 |  | Freezing Station A | Sat Oct 11 07:00:00 IDT 2014 | Mon Nov 09 17:00:00 IST 2015
286 | TASK_DEPENDENT | Erect Freezing Station Platform | Sat Oct 11 07:00:00 IDT 2014 | Tue Oct 21 17:00:00 IDT 2014
287 | TASK_DEPENDENT | Freezing Station Installation & Testing | Thu Jan 01 07:00:00 IST 2015 | Sat Jan 31 17:00:00 IST 2015
288 | TASK_DEPENDENT | Remove Freezing Station A | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
289 |  | Cross Passage #1. Ch.116+030 | Wed Oct 01 07:00:00 IDT 2014 | Tue May 10 17:00:00 IDT 2016
290 | TASK_DEPENDENT | Erect Temporary Drilling Platform | Wed Oct 01 07:00:00 IDT 2014 | Fri Oct 10 17:00:00 IDT 2014
291 | TASK_DEPENDENT | Drill & Install Freezing Pipe | Mon Dec 01 07:00:00 IST 2014 | Wed Jan 14 17:00:00 IST 2015
292 | TASK_DEPENDENT | Install temporary support including ring support (Up-track) | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 15 17:00:00 IST 2015
293 | TASK_DEPENDENT | Install temporary support including ring support (Down-track) | Mon Feb 23 07:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
294 | TASK_DEPENDENT | Intall safe door | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 25 17:00:00 IDT 2015
295 | TASK_DEPENDENT | Install freezing & monitoring system | Mon Feb 23 07:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
296 | TASK_DEPENDENT | Conduct Ground Freezing | Sun Mar 01 07:00:00 IST 2015 | Tue Apr 14 17:00:00 IDT 2015
297 | TASK_DEPENDENT | Maintain ground freezing during construction of CP | Tue Apr 21 07:00:00 IDT 2015 | Sun Jun 14 17:00:00 IDT 2015
298 | TASK_DEPENDENT | Tunnel segment cutting & removal | Tue Apr 21 07:00:00 IDT 2015 | Wed Apr 22 17:00:00 IDT 2015
299 | TASK_DEPENDENT | Excavate and temporary support | Tue Apr 21 07:00:00 IDT 2015 | Sat May 23 17:00:00 IDT 2015
300 | TASK_DEPENDENT | Tunnel segment removal | Tue Aug 04 07:00:00 IDT 2015 | Mon Aug 10 17:00:00 IDT 2015
301 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Fri Jul 03 07:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
302 | TASK_DEPENDENT | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 08 17:00:00 IDT 2015
303 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
304 | TASK_DEPENDENT | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
305 | TASK_DEPENDENT | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
306 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
307 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
308 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
309 | TASK_DEPENDENT | Remove formwork | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
310 | TASK_DEPENDENT | Concrete achieved the design strength | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
311 | TASK_DEPENDENT | Remove temporary works | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
312 | TASK_DEPENDENT | Remove Freezing Plant | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
313 | TASK_DEPENDENT | Thawing & Proof Grouting | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
314 | TASK_DEPENDENT | Make Good Freezing Pipe Hole | Sun May 01 07:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
315 |  | Cross Passage #2. Ch.116+195 | Mon Feb 23 07:00:00 IST 2015 | Sun Apr 10 17:00:00 IDT 2016
316 | TASK_DEPENDENT | Erect Temporary Drilling Platform | Mon Feb 23 07:00:00 IST 2015 | Wed Feb 25 17:00:00 IST 2015
317 | TASK_DEPENDENT | Drill & Install Freezing Pipe | Mon Feb 23 07:00:00 IST 2015 | Fri Apr 10 17:00:00 IDT 2015
318 | TASK_DEPENDENT | Install temporary support (including ring support) | Tue Apr 21 07:00:00 IDT 2015 | Tue May 05 17:00:00 IDT 2015
319 | TASK_DEPENDENT | Install safe door | Mon Jun 01 07:00:00 IDT 2015 | Thu Jun 04 17:00:00 IDT 2015
320 | TASK_DEPENDENT | Install freezing & monitoring system | Tue Apr 21 07:00:00 IDT 2015 | Thu Apr 23 17:00:00 IDT 2015
321 | TASK_DEPENDENT | Conduct Ground Freezing | Tue Apr 21 07:00:00 IDT 2015 | Tue Jun 16 17:00:00 IDT 2015
322 | TASK_DEPENDENT | Maintain ground freezing during construction of CP | Fri Jul 24 07:00:00 IDT 2015 | Mon Sep 21 17:00:00 IDT 2015
323 | TASK_DEPENDENT | Tunnel segment cutting & removal | Fri Jul 24 07:00:00 IDT 2015 | Thu Jul 30 17:00:00 IDT 2015
324 | TASK_DEPENDENT | Excavate and temporary support | Sun Jul 26 07:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
325 | TASK_DEPENDENT | Tunnel segment removal | Mon Aug 03 07:00:00 IDT 2015 | Tue Aug 04 17:00:00 IDT 2015
326 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
327 | TASK_DEPENDENT | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
328 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
329 | TASK_DEPENDENT | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
330 | TASK_DEPENDENT | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
331 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
332 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
333 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
334 | TASK_DEPENDENT | Remove formwork | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
335 | TASK_DEPENDENT | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
336 | TASK_DEPENDENT | Remove temporary works | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
337 | TASK_DEPENDENT | Remove Freezing Pipes | Sat Nov 14 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
338 | TASK_DEPENDENT | Thawing & Proof Grouting | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
339 | TASK_DEPENDENT | Make Good Freezing Pipe Holes | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
340 |  | Freezing Station B | Mon Jun 01 07:00:00 IDT 2015 | Thu Aug 04 17:00:00 IDT 2016
341 | TASK_DEPENDENT | Erect Freezing Station Platform | Mon Jun 01 07:00:00 IDT 2015 | Sat Jun 20 17:00:00 IDT 2015
342 | TASK_DEPENDENT | Freezing Station Installation & Testing | Sun Jun 21 07:00:00 IDT 2015 | Fri Jul 10 17:00:00 IDT 2015
343 | TASK_DEPENDENT | Remove Station B | Fri Jul 22 07:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016
344 |  | Cross Passage #3. Ch. 116+445 | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
345 | TASK_DEPENDENT | Erect Temporary Drilling Platform | Tue Apr 21 07:00:00 IDT 2015 | Sun Apr 26 17:00:00 IDT 2015
346 | TASK_DEPENDENT | Drill & Install Freezing Pipe | Tue Apr 21 07:00:00 IDT 2015 | Fri Jun 05 17:00:00 IDT 2015
347 | TASK_DEPENDENT | Install temporary support (including ring support) | Sun Jul 19 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
348 | TASK_DEPENDENT | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
349 | TASK_DEPENDENT | Install freezing & monitoring system | Wed Jul 01 07:00:00 IDT 2015 | Fri Jul 03 17:00:00 IDT 2015
350 | TASK_DEPENDENT | Conduct Ground Freezing | Sat Jul 04 07:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
351 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Sep 29 07:00:00 IDT 2015 | Fri Dec 18 17:00:00 IST 2015
352 | TASK_DEPENDENT | Tunnel segment cutting & removal at U/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
353 | TASK_DEPENDENT | Excavate and temporary support | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 31 17:00:00 IST 2015
354 | TASK_DEPENDENT | Tunnel segment removal at D/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
355 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
356 | TASK_DEPENDENT | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
357 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
358 | TASK_DEPENDENT | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
359 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 12 17:00:00 IST 2015
360 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
361 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
362 | TASK_DEPENDENT | Make Good Freezing Pipe Hole | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
363 | TASK_DEPENDENT | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
364 | TASK_DEPENDENT | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
365 | TASK_DEPENDENT | Remove temp. works, ring support and temp. platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
366 | TASK_DEPENDENT | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
367 |  | Cross Passage #4. Ch. 116+671 | Mon Jul 06 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
368 | TASK_DEPENDENT | Erect Temporary Drilling Platform | Sun Jul 19 07:00:00 IDT 2015 | Thu Jul 23 17:00:00 IDT 2015
369 | TASK_DEPENDENT | Drill & Install Freezing Pipe | Mon Jul 06 07:00:00 IDT 2015 | Thu Aug 20 17:00:00 IDT 2015
370 | TASK_DEPENDENT | Install temporary support (including ring support) | Tue Sep 29 07:00:00 IDT 2015 | Tue Oct 13 17:00:00 IDT 2015
371 | TASK_DEPENDENT | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
372 | TASK_DEPENDENT | Install freezing & monitoring system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
373 | TASK_DEPENDENT | Conduct Ground Freezing | Tue Sep 29 07:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
374 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Thu Nov 05 07:00:00 IST 2015 | Fri Feb 19 17:00:00 IST 2016
375 | TASK_DEPENDENT | Tunnel segment cutting & removal at U/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
376 | TASK_DEPENDENT | Excavate and temporary support | Mon Nov 09 07:00:00 IST 2015 | Wed Nov 25 17:00:00 IST 2015
377 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
378 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
379 | TASK_DEPENDENT | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
380 | TASK_DEPENDENT | Lining concrete curing (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
381 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
382 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Tue Nov 10 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
383 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
384 | TASK_DEPENDENT | Remove formwork | Fri Apr 08 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
385 | TASK_DEPENDENT | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
386 | TASK_DEPENDENT | Remove temp. works and ring support | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
387 | TASK_DEPENDENT | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
388 | TASK_DEPENDENT | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
389 | TASK_DEPENDENT | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
390 |  | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Sat Nov 07 17:00:00 IST 2015
391 | TASK_DEPENDENT | Erect temp. working platform | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
392 | TASK_DEPENDENT | Drilling remaining holes at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
393 | TASK_DEPENDENT | Install ring support at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
394 | TASK_DEPENDENT | Tunnel segment removal at D/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
395 |  | Cross Passage #5. Ch. 116+966 | Wed Jul 01 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
396 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+066); last gantry passed CP5 | Wed Jul 01 07:00:00 IDT 2015 | Wed Jul 01 07:00:00 IDT 2015
397 | TASK_DEPENDENT | Erect Temporary Drilling Platform at U/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
398 | START_MILESTONE | TBM S623 C/W exited Alluvial zone at S1425/Ch. 116+927 (* Note1) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
399 | TASK_DEPENDENT | TBM S623 C/W boring from Ch. 116+927 to Ch. 116+986 (CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
400 | TASK_DEPENDENT | Drill & Install Freezing Pipe at U/T | Sat Oct 10 07:00:00 IDT 2015 | Tue Nov 24 17:00:00 IST 2015
401 | TASK_DEPENDENT | Raise track rail, slurry pipes diversion, install temp. support at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
402 | TASK_DEPENDENT | Install Ring Support | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
403 | TASK_DEPENDENT | Install freezing & monitoring system | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
404 | TASK_DEPENDENT | Freezing system Test & Commissioning | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
405 | TASK_DEPENDENT | Conduct Ground Freezing (Active phase) | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
406 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Dec 01 07:00:00 IST 2015 | Sun Mar 20 17:00:00 IST 2016
407 | TASK_DEPENDENT | Install safe door (both sides) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
408 | TASK_DEPENDENT | Tunnel segment cutting & removal at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
409 | TASK_DEPENDENT | Excavate and temporary support (excavation from D/T) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
410 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
411 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
412 | TASK_DEPENDENT | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
413 | TASK_DEPENDENT | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
414 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
415 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
416 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
417 | TASK_DEPENDENT | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
418 | TASK_DEPENDENT | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
419 | TASK_DEPENDENT | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
420 | TASK_DEPENDENT | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
421 | TASK_DEPENDENT | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
422 | TASK_DEPENDENT | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
423 |  | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Fri Nov 27 17:00:00 IST 2015
424 | TASK_DEPENDENT | TBM S623 C/W boring from Ch.. 116+986 to Ch117+086 (last gantry passed CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 16 17:00:00 IDT 2015
425 | TASK_DEPENDENT | Erect Temporary Drilling Platorm at D/T | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
426 | TASK_DEPENDENT | Drilling remaining holes at D/T after S623 gantries passed | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 27 17:00:00 IST 2015
427 | TASK_DEPENDENT | Install ring support at D/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
428 |  | Cross Passage #6. Ch. 117+216 | Sat Aug 01 07:00:00 IDT 2015 | Wed Jun 15 17:00:00 IDT 2016
429 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Sat Aug 01 07:00:00 IDT 2015 | Sat Aug 01 07:00:00 IDT 2015
430 | TASK_DEPENDENT | Erect Drilling Platform at U/T | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
431 | TASK_DEPENDENT | Drill ground freezing holes at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
432 | TASK_DEPENDENT | Install Ring Support at U/T | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
433 | TASK_DEPENDENT | Install freezing & monitoring system at U/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
434 | TASK_DEPENDENT | Freezing system Test & Commissioning at U/T, Station B | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
435 | TASK_DEPENDENT | Conduct Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Thu May 19 17:00:00 IDT 2016
436 | LEVEL_OF_EFFORT | Maintain Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Wed Jun 15 17:00:00 IDT 2016
437 | TASK_DEPENDENT | Install safe door (both sides) | Sun Apr 10 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
438 | TASK_DEPENDENT | Tunnel segment removal | Sat Apr 16 07:00:00 IDT 2016 | Wed Apr 20 17:00:00 IDT 2016
439 | TASK_DEPENDENT | Excavate and temporary support (excavation from U/T side only) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
440 | TASK_DEPENDENT | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
441 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
442 | TASK_DEPENDENT | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
443 | TASK_DEPENDENT | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
444 | TASK_DEPENDENT | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
445 | TASK_DEPENDENT | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
446 | TASK_DEPENDENT | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
447 | TASK_DEPENDENT | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
448 | TASK_DEPENDENT | Remove formwork & Remove safe doors | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
449 | TASK_DEPENDENT | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
450 | TASK_DEPENDENT | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
451 | TASK_DEPENDENT | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
452 | TASK_DEPENDENT | Make Good Freezing Pipe Hole | Mon Apr 11 07:00:00 IDT 2016 | Thu Apr 14 17:00:00 IDT 2016
453 |  | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Mon Apr 11 17:00:00 IDT 2016
454 | START_MILESTONE | S623 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
455 | TASK_DEPENDENT | Erect Working Platform at D/T | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
456 | TASK_DEPENDENT | Drill ground freezing holes at D/T | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
457 | TASK_DEPENDENT | Install freezing & monitoring system at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
458 | TASK_DEPENDENT | Ring support installation at D/T | Wed Apr 06 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
459 |  | Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
460 |  | Down Track Tunnel Finishes | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
461 |  | Tunnel Invert Slab (DT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 30 17:00:00 IDT 2016
462 | TASK_DEPENDENT | Invert Slab between HK Boundary and CP1 (104-15=89m-64=25m) | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
463 | TASK_DEPENDENT | Invert Slab at CP1 (30m) | Sun May 29 07:00:00 IDT 2016 | Mon May 30 17:00:00 IDT 2016
464 | TASK_DEPENDENT | Invert Slab between CP1 and CP2 (164-30=134m) | Sat May 21 07:00:00 IDT 2016 | Sat May 28 17:00:00 IDT 2016
465 | TASK_DEPENDENT | Invert Slab at CP2 (30m) | Sat May 21 07:00:00 IDT 2016 | Sun May 22 17:00:00 IDT 2016
466 | TASK_DEPENDENT | Invert Slab between CP2 and CP3 (250-30=220m) | Sun May 08 07:00:00 IDT 2016 | Fri May 20 17:00:00 IDT 2016
467 | TASK_DEPENDENT | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
468 | TASK_DEPENDENT | Invert Slab between CP3 and CP4 (226-45=181m) | Fri Apr 29 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
469 | TASK_DEPENDENT | Invert Slab at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
470 | TASK_DEPENDENT | Invert Slab between CP4 and CP5 (296-59=237m) | Thu Apr 14 07:00:00 IDT 2016 | Thu Apr 28 17:00:00 IDT 2016
471 | TASK_DEPENDENT | Invert Slab at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
472 | TASK_DEPENDENT | Invert Slab between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
473 | TASK_DEPENDENT | Invert Slab at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
474 | TASK_DEPENDENT | Invert Slab between CP6 and 2B Gates(next to CP6) (14m) | Thu Apr 07 07:00:00 IDT 2016 | Fri Apr 08 17:00:00 IDT 2016
475 | TASK_DEPENDENT | Invert Slab between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Thu Apr 07 07:00:00 IDT 2016 | Sat Apr 16 17:00:00 IDT 2016
476 | TASK_DEPENDENT | Invert Slab between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
477 |  | Lower Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
478 | TASK_DEPENDENT | Lower Wkys between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
479 | TASK_DEPENDENT | Lower Wkys at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
480 | TASK_DEPENDENT | Lower Wkys between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
481 | TASK_DEPENDENT | Lower Wks at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
482 | TASK_DEPENDENT | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
483 | TASK_DEPENDENT | Lower Wkys at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
484 | TASK_DEPENDENT | Lower Wkys between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
485 | TASK_DEPENDENT | Lower Wkys at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
486 | TASK_DEPENDENT | Lower Wkys between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
487 | TASK_DEPENDENT | Lower Wkys at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
488 | TASK_DEPENDENT | Lower Wkys between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
489 | TASK_DEPENDENT | Lower Wkys at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
490 | TASK_DEPENDENT | Lower Wkys between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
491 | TASK_DEPENDENT | Lower Wkys between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
492 | TASK_DEPENDENT | Lower Wkys between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
493 |  | Upper Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
494 | TASK_DEPENDENT | Upper Wky between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
495 | TASK_DEPENDENT | Upper Wky at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
496 | TASK_DEPENDENT | Upper Wky between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
497 | TASK_DEPENDENT | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
498 | TASK_DEPENDENT | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
499 | TASK_DEPENDENT | Upper Wky at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
500 | TASK_DEPENDENT | Upper Wky between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
501 | TASK_DEPENDENT | Upper Wky at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
502 | TASK_DEPENDENT | Upper Wky between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
503 | TASK_DEPENDENT | Upper Wky at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
504 | TASK_DEPENDENT | Upper Wky between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
505 | TASK_DEPENDENT | Upper Wky at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
506 | TASK_DEPENDENT | Upper Wky between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
507 | TASK_DEPENDENT | Upper Wky between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
508 | TASK_DEPENDENT | Upper Wky between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
509 |  | DT Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Sat Dec 24 17:00:00 IST 2016
510 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
511 | TASK_DEPENDENT | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
512 | TASK_DEPENDENT | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
513 | TASK_DEPENDENT | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
514 | TASK_DEPENDENT | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
515 |  | Double Gates (DT) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
516 | TASK_DEPENDENT | Install double gates at 20m south of CP6 | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
517 | TASK_DEPENDENT | Lock up manlock when cutter head breakthrough cont' wall | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
518 | TASK_DEPENDENT | Shift double gates to Mai Po Shaft after TBM removal | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
519 | TASK_DEPENDENT | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
520 |  | Up Track Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 22 17:00:00 IST 2016
521 |  | Tunnel Invert Slab (UT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 02 17:00:00 IDT 2016
522 | TASK_DEPENDENT | Invert Slab between HK Boundary and CP1 (104-15=89m) | Tue Apr 26 07:00:00 IDT 2016 | Sun May 01 17:00:00 IDT 2016
523 | TASK_DEPENDENT | Invert Slab at CP1 (30m) | Tue Apr 26 07:00:00 IDT 2016 | Wed Apr 27 17:00:00 IDT 2016
524 | TASK_DEPENDENT | Invert Slab between CP1 and CP2 (164-30=134m) incl. Station A area | Mon Apr 18 07:00:00 IDT 2016 | Mon Apr 25 17:00:00 IDT 2016
525 | TASK_DEPENDENT | Invert Slab at CP2 (30m) | Mon Apr 18 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
526 | TASK_DEPENDENT | Invert Slab between CP2 and CP3 (250-30=220m) | Tue Apr 05 07:00:00 IDT 2016 | Sun Apr 17 17:00:00 IDT 2016
527 | TASK_DEPENDENT | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
528 | TASK_DEPENDENT | Invert Slab between CP3 and CP4 (226-47-34=145m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
529 | TASK_DEPENDENT | Invert Slab at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
530 | TASK_DEPENDENT | Invert Slab at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
531 | TASK_DEPENDENT | Invert Slab between CP4 and CP5 (296-51=245m) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
532 | TASK_DEPENDENT | Invert Slab at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
533 | TASK_DEPENDENT | Invert Slab between CP5 and CP6 (250-32=218m) | Sat Dec 19 07:00:00 IST 2015 | Thu Dec 31 17:00:00 IST 2015
534 | TASK_DEPENDENT | Invert Slab at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
535 | TASK_DEPENDENT | Invert Slab between CP6 and 2B Gates(next to CP6) (20m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
536 | TASK_DEPENDENT | Invert Slab between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
537 | TASK_DEPENDENT | Invert Slab between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
538 |  | Lower Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
539 | TASK_DEPENDENT | Lower Wkys between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
540 | TASK_DEPENDENT | Lower Wkys at CP1 (30m) | Mon May 16 07:00:00 IDT 2016 | Tue May 17 17:00:00 IDT 2016
541 | TASK_DEPENDENT | Lower Wkys between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
542 | TASK_DEPENDENT | Lower Wkys at CP2 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
543 | TASK_DEPENDENT | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
544 | TASK_DEPENDENT | Lower Wkys at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
545 | TASK_DEPENDENT | Lower Wkys between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
546 | TASK_DEPENDENT | Lower Wkys at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
547 | TASK_DEPENDENT | Lower Wkys at CP4 (64m) | Sat Apr 16 07:00:00 IDT 2016 | Mon Apr 18 17:00:00 IDT 2016
548 | TASK_DEPENDENT | Lower Wkys between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
549 | TASK_DEPENDENT | Lower Wkys at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
550 | TASK_DEPENDENT | Lower Wkys between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
551 | TASK_DEPENDENT | Lower Wkys at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
552 | TASK_DEPENDENT | Lower Wkys between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
553 | TASK_DEPENDENT | Lower Wkys between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
554 | TASK_DEPENDENT | Lower Wkys between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
555 |  | Upper Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
556 | TASK_DEPENDENT | Upper Wky between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
557 | TASK_DEPENDENT | Upper Wky at CP1 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
558 | TASK_DEPENDENT | Upper Wky between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
559 | TASK_DEPENDENT | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
560 | TASK_DEPENDENT | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
561 | TASK_DEPENDENT | Upper Wky at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
562 | TASK_DEPENDENT | Upper Wky between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
563 | TASK_DEPENDENT | Upper Wky at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
564 | TASK_DEPENDENT | Upper Wky at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
565 | TASK_DEPENDENT | Upper Wky between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
566 | TASK_DEPENDENT | Upper Wky at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
567 | TASK_DEPENDENT | Upper Wky between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
568 | TASK_DEPENDENT | Upper Wky at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
569 | TASK_DEPENDENT | Upper Wky between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
570 | TASK_DEPENDENT | Upper Wky between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
571 | TASK_DEPENDENT | Upper Wky between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
572 |  | Up Track Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Thu Dec 22 17:00:00 IST 2016
573 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
574 | TASK_DEPENDENT | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
575 | TASK_DEPENDENT | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Thu Dec 22 17:00:00 IST 2016
576 | TASK_DEPENDENT | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
577 | TASK_DEPENDENT | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
578 |  | UT Double Gates | Thu Nov 05 07:00:00 IST 2015 | Wed Apr 06 17:00:00 IDT 2016
579 | TASK_DEPENDENT | Install double gates at 20m south of CP6 | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
580 | TASK_DEPENDENT | Lock up manlock when cutter head breakthrough cont' wall | Wed Nov 11 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
581 | TASK_DEPENDENT | Shift double gates to Mai Po Shaft after TBM removal | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
582 | TASK_DEPENDENT | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
583 |  | Tunnel Finishes to Completion | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
584 |  | Down Track | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
585 | TASK_DEPENDENT | Operation and maintenance of temporary services | Fri Apr 08 07:00:00 IDT 2016 | Sun Mar 05 17:00:00 IST 2017
586 | TASK_DEPENDENT | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
587 |  | Up Track | Wed Jun 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
588 | TASK_DEPENDENT | Operation and maintenance of temporary services | Wed Jun 01 07:00:00 IDT 2016 | Thu Oct 06 17:00:00 IDT 2016
589 | TASK_DEPENDENT | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
590 |  | Commissioning, Inspections and Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
591 | RESOURCE_DEPENDENT | Site Cleaning, Inspection for Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
592 | FINISH_MILESTONE | Submit draft as-built drawings (Z8.2) and draft O&M Manuals | Sat Dec 24 17:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
593 | FINISH_MILESTONE | Submit approved Design Data (Z8.4) | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
594 | FINISH_MILESTONE | Submit final as-built drawings and O&M Manuals | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
595 | TASK_DEPENDENT | Inspect & Certify completion of whole works | Sat Mar 25 07:00:00 IDT 2017 | Fri Mar 31 17:00:00 IDT 2017
596 |  | Contract Preliminaries | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
597 |  | Designs and Submissions | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
598 |  | Principle Method Statements, Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
599 |  | Management Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Sun Oct 30 08:00:00 IST 2011
600 | TASK_DEPENDENT | Submit System Assurance Plan (App P, P3.1) | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
601 | TASK_DEPENDENT | Engineer's review on System Assurance Plan | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
602 | TASK_DEPENDENT | Submit Health and Safety Plan (G3.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
603 | TASK_DEPENDENT | Engineer's review on Health and Safety Plan | Wed May 05 08:00:00 IDT 2010 | Wed Jun 02 08:00:00 IDT 2010
604 | TASK_DEPENDENT | Submit Quality Assurance Plan (G9.2.1) | Thu Apr 15 08:00:00 IDT 2010 | Thu May 13 08:00:00 IDT 2010
605 | TASK_DEPENDENT | Engineer's review on Quality Assurance Plan | Wed May 12 08:00:00 IDT 2010 | Wed Jun 09 08:00:00 IDT 2010
606 | TASK_DEPENDENT | Submit Prelimiary Master Programme (G4.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
607 | TASK_DEPENDENT | Engineer's review on Prelimiary Master Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
608 | TASK_DEPENDENT | Submit first Three-Month Rolling Programme (G4.8 | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 29 08:00:00 IDT 2010
609 | TASK_DEPENDENT | Engineer's review on first Three-Month Rolling P | Fri Apr 02 08:00:00 IDT 2010 | Fri Apr 30 08:00:00 IDT 2010
610 | TASK_DEPENDENT | Submit Time-chainage Programme (G4.11.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
611 | TASK_DEPENDENT | Engineer's review on Time-chainage Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
612 | TASK_DEPENDENT | Submit Design Schedule (App Z) | Mon May 03 08:00:00 IDT 2010 | Mon May 17 08:00:00 IDT 2010
613 | TASK_DEPENDENT | Engineer's review on Design Schedule | Fri May 28 08:00:00 IDT 2010 | Fri Jun 25 08:00:00 IDT 2010
614 | TASK_DEPENDENT | Submit Subcontractor Management Plan (App S) | Sat May 15 08:00:00 IDT 2010 | Mon Jun 14 08:00:00 IDT 2010
615 | TASK_DEPENDENT | Engineer's review on Subcontractor Management Pl | Tue Jun 15 08:00:00 IDT 2010 | Tue Jul 13 08:00:00 IDT 2010
616 | TASK_DEPENDENT | Submit Groundwater Monitoring and Emergency Resp | Thu Apr 22 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
617 | TASK_DEPENDENT | Engineer's review on Groundwater Monitoring and | Fri Jun 04 08:00:00 IDT 2010 | Fri Jul 02 08:00:00 IDT 2010
618 | TASK_DEPENDENT | Submit Water Pollution Control Measures and Moni | Thu Apr 15 08:00:00 IDT 2010 | Sun May 30 08:00:00 IDT 2010
619 | TASK_DEPENDENT | Engineer's review on Water Pollution Control Mea | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
620 | TASK_DEPENDENT | Submit Waste Management Plan (P22.8.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
621 | TASK_DEPENDENT | Engineer's review on Waste Management Plan | Tue May 18 08:00:00 IDT 2010 | Tue Jun 15 08:00:00 IDT 2010
622 | TASK_DEPENDENT | Submit the Plan for the Design for Safety and Co | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
623 | TASK_DEPENDENT | Engineer's review on Plan for the Design for Saf | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
624 | TASK_DEPENDENT | Submit Air Quality Management Plan (P22.4.4) | Fri Apr 09 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
625 | TASK_DEPENDENT | Engineer's review on Air Quality Management Plan | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
626 | TASK_DEPENDENT | Submit TBM manufacturiing and delivery programme | Sat May 22 08:00:00 IDT 2010 | Sat Jun 19 08:00:00 IDT 2010
627 | TASK_DEPENDENT | Engineer's review on TBM manufacturiing and deli | Wed Jun 02 08:00:00 IDT 2010 | Wed Jun 30 08:00:00 IDT 2010
628 | TASK_DEPENDENT | Submit Environmental Management Plan (G5.1.10) | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
629 | TASK_DEPENDENT | Engineer's review on Environmental Management Pl | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
630 | TASK_DEPENDENT | Submit interfacing documentation for System-wide | Mon Aug 01 08:00:00 IDT 2011 | Sun Oct 30 08:00:00 IST 2011
631 | TASK_DEPENDENT | Engineer's review on interfacing documentation f | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
632 |  | Method Statements | Fri Apr 09 08:00:00 IDT 2010 | Wed Jun 17 17:00:00 IDT 2015
633 | TASK_DEPENDENT | Submit Geotechnical Instruments installation | Fri Jun 18 08:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010
634 | TASK_DEPENDENT | Engineer's review on Geotechnical Instruments installation | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
635 | TASK_DEPENDENT | Submit Survey control network | Fri Apr 09 08:00:00 IDT 2010 | Mon May 24 08:00:00 IDT 2010
636 | TASK_DEPENDENT | Engineer's review on Survey control network | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
637 | TASK_DEPENDENT | Submit MS for surveying and survey control for tunnelling works | Mon Jun 14 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
638 | TASK_DEPENDENT | Engineer's review on MS for surveying and survey control for tunnelling works | Sat Aug 07 08:00:00 IDT 2010 | Sat Sep 04 08:00:00 IDT 2010
639 | TASK_DEPENDENT | Submit a Ground Treatment Works spoil disposal plan | Tue Jun 08 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
640 | TASK_DEPENDENT | Engineer's review on Ground Treatment Works spoil disposal plan | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
641 | TASK_DEPENDENT | Submit MS for ground treatment | Sun May 09 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
642 | TASK_DEPENDENT | Engineer's review on MS for ground treatment | Fri Jun 25 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
643 | TASK_DEPENDENT | Submit TBM MS for transportation and erection of the TBMs (X.17.1.1) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
644 | TASK_DEPENDENT | Engineer's review on TBM MS for transportation and erection of the TBMs | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
645 | TASK_DEPENDENT | Submit TBM MS for operation of the TBM (X17.1.3) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
646 | TASK_DEPENDENT | Engineer's review on TBM MS for operation of the TBM | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
647 | TASK_DEPENDENT | Submit MS for instrumentation and monitoring works in Ramsar & WPC areas | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 29 08:00:00 IDT 2011
648 | TASK_DEPENDENT | Engineer's review on MS for instrumentation and monitoring works in Ramsar & WPC | Tue Mar 08 08:00:00 IST 2011 | Tue Apr 05 08:00:00 IDT 2011
649 | TASK_DEPENDENT | Submit TBM MS for determining ground conditions ahead of the face (X17.1.5) (CS569) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
650 | TASK_DEPENDENT | Engineer's review on TBM MS for determining ground conditions ahead of the face | Fri Apr 17 07:00:00 IDT 2015 | Thu May 14 17:00:00 IDT 2015
651 | TASK_DEPENDENT | Submit MS for cross passage construction | Mon Jul 04 08:00:00 IDT 2011 | Mon Aug 01 08:00:00 IDT 2011
652 | TASK_DEPENDENT | Engineer's review on MS for cross passage construction | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 26 08:00:00 IDT 2011
653 | TASK_DEPENDENT | Submit TBM MS for commencing the initial drives (X17.1.2) (CS80) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
654 | TASK_DEPENDENT | Engineer's review on TBM MS for commencing the initial drives | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
655 | TASK_DEPENDENT | Submit TBM MS for setting out and controlling the tunnel alignment (Survey MS CS21) | Tue May 11 07:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
656 | TASK_DEPENDENT | Engineer's review on TBM MS for setting out & contolling the tunnel alignment | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
657 | TASK_DEPENDENT | Submit TBM MS for monitoring ground loss and settlement monitoring (X17.1.6) (CS36) | Tue Nov 30 07:00:00 IST 2010 | Tue Nov 30 07:00:00 IST 2010
658 | TASK_DEPENDENT | Engineer's review on TBM MS for monitoring ground loss & settlement monitoring | Wed Aug 11 07:00:00 IDT 2010 | Wed Aug 11 07:00:00 IDT 2010
659 | TASK_DEPENDENT | Submit TBM MS for hyperbaric interventions (X17.1.7) (CS520) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
660 | TASK_DEPENDENT | Engineer's review on TBM MS for hyperbaric interventions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
661 | TASK_DEPENDENT | Submit MS for the identification and removal of obstructions (P11.11) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
662 | TASK_DEPENDENT | Engineer's review on MS for the identification & removal of obstructions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
663 | TASK_DEPENDENT | Submit TBM MS for tunnelling under sensitive structures (X17.1.10) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
664 | TASK_DEPENDENT | Engineer's review on TBM MS for tunnelling under sensitive structures | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
665 | TASK_DEPENDENT | Submit TBM MS for TBM dismantling (X17.1.9) (CS652) | Fri Feb 20 07:00:00 IST 2015 | Wed May 20 17:00:00 IDT 2015
666 | TASK_DEPENDENT | Engineer's review on TBM MS for TBM dismantling | Thu May 21 07:00:00 IDT 2015 | Wed Jun 17 17:00:00 IDT 2015
667 | TASK_DEPENDENT | Submit TBM MS for junctions with shafts (X17.1.8) (CS246) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
668 | TASK_DEPENDENT | Engineer's review on TBM MS for junctions with shafts | Thu Jun 23 07:00:00 IDT 2011 | Wed Jul 20 17:00:00 IDT 2011
669 | TASK_DEPENDENT | Submit MS for ground freezing works (CS686) | Mon Dec 12 08:00:00 IST 2011 | Fri Feb 10 08:00:00 IST 2012
670 | TASK_DEPENDENT | Engineer's review on MS for ground freezing work | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 16 08:00:00 IDT 2012
671 | TASK_DEPENDENT | Submit MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 01 08:00:00 IST 2014
672 | TASK_DEPENDENT | Engineer's review on MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
673 | TASK_DEPENDENT | Submit Methods of Construction | Thu May 27 08:00:00 IDT 2010 | Thu Jun 17 08:00:00 IDT 2010
674 | TASK_DEPENDENT | Engineer's review on Methods of Construction | Fri Jun 18 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
675 | TASK_DEPENDENT | Submit TBM Spoil Disposal Plan (HK) | Wed Jun 23 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
676 | TASK_DEPENDENT | Engineer's review on TBM Spoil Disposal Plan | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
677 | TASK_DEPENDENT | Submit TBM Spoil Disposal Plan (SZ) | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 21 08:00:00 IST 2013
678 | TASK_DEPENDENT | Engineer's review on TBM Spoil Disposal Plan | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 23 08:00:00 IST 2014
679 |  | Submissions to Government Departments | Sat May 29 08:00:00 IDT 2010 | Tue Jun 03 09:00:00 IDT 2014
680 | TASK_DEPENDENT | Apply for the initial batch of Frontier Closed Area Permits | Sat May 29 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
681 | TASK_DEPENDENT | Submit Emergency Rescue proposals and procedures | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
682 | TASK_DEPENDENT | Engineer's review on Emergency Rescue proposals and procedures | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 28 08:00:00 IST 2013
683 | TASK_DEPENDENT | Application and obtain approval of Construction Noise Permits | Fri Apr 04 09:00:00 IDT 2014 | Tue Jun 03 09:00:00 IDT 2014
684 |  | Temporary Works Design Submissions | Thu Apr 22 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
685 | TASK_DEPENDENT | Submit site logistics plans (initial layout) | Thu Apr 22 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
686 | TASK_DEPENDENT | Engineer's review on site logistics plans (initial layout) | Fri Jul 23 08:00:00 IDT 2010 | Fri Aug 20 08:00:00 IDT 2010
687 | TASK_DEPENDENT | Submit designs for the Engineer's Office | Mon Jul 12 08:00:00 IDT 2010 | Fri Sep 10 08:00:00 IDT 2010
688 | TASK_DEPENDENT | Engineer's review on designs for the Engineer's | Mon Aug 23 08:00:00 IDT 2010 | Mon Sep 20 08:00:00 IST 2010
689 | TASK_DEPENDENT | Submit temporary ventilation system design | Mon Aug 01 08:00:00 IDT 2011 | Fri Sep 30 08:00:00 IDT 2011
690 | TASK_DEPENDENT | Engineer's review on temporary ventilation syste | Sat Aug 20 08:00:00 IDT 2011 | Sat Sep 17 08:00:00 IDT 2011
691 |  | Design of Permanent Works | Tue Jun 01 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
692 |  | Tunnel Permanent Lining | Tue Jun 01 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
693 | TASK_DEPENDENT | Submission preparation & ICE checking | Tue Jun 01 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
694 | TASK_DEPENDENT | Engineer's review | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
695 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Tue Aug 31 08:00:00 IDT 2010
696 | TASK_DEPENDENT | Engineer's review | Wed Aug 04 08:00:00 IDT 2010 | Wed Sep 01 08:00:00 IDT 2010
697 | TASK_DEPENDENT | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
698 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
699 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
700 |  | Permanent Tunnel Lining of Cross Passages | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
701 |  | AIP Submission | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
702 | TASK_DEPENDENT | Submission preparation | Mon Jun 28 08:00:00 IDT 2010 | Sat Aug 07 08:00:00 IDT 2010
703 | TASK_DEPENDENT | Engineer's review | Sat Aug 14 08:00:00 IDT 2010 | Sat Sep 11 08:00:00 IDT 2010
704 | TASK_DEPENDENT | Re-submission preparation | Fri Aug 03 08:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012
705 | TASK_DEPENDENT | Engineer's review | Mon Sep 03 08:00:00 IDT 2012 | Mon Oct 01 08:00:00 IST 2012
706 |  | Connection between Bored Tunnel and Retrival Shaft | Mon Aug 16 08:00:00 IDT 2010 | Tue Jul 01 08:00:00 IDT 2014
707 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 25 08:00:00 IST 2010
708 | TASK_DEPENDENT | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
709 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Sat Oct 23 08:00:00 IST 2010 | Sun Nov 28 08:00:00 IST 2010
710 | TASK_DEPENDENT | Engineer's review | Sat Oct 06 08:00:00 IST 2012 | Sat Nov 03 08:00:00 IST 2012
711 | TASK_DEPENDENT | Submission for RDO/BD consultation | Sun Feb 10 08:00:00 IST 2013 | Sun Mar 10 08:00:00 IST 2013
712 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Tue Dec 17 08:00:00 IST 2013 | Tue Jan 14 08:00:00 IST 2014
713 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
714 |  | Junction between Main Tunnel and Cross Passages | Mon Oct 04 08:00:00 IST 2010 | Sun Sep 07 08:00:00 IDT 2014
715 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon Oct 04 08:00:00 IST 2010 | Tue Nov 23 08:00:00 IST 2010
716 | TASK_DEPENDENT | Engineer's review | Thu Feb 07 08:00:00 IST 2013 | Thu Mar 07 08:00:00 IST 2013
717 | TASK_DEPENDENT | Submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
718 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Tue Jul 01 08:00:00 IDT 2014 | Sun Aug 10 08:00:00 IDT 2014
719 | TASK_DEPENDENT | Engineer's review | Sun Aug 10 08:00:00 IDT 2014 | Sun Sep 07 08:00:00 IDT 2014
720 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
721 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
722 |  | Design of Temporary Works | Sat May 01 08:00:00 IDT 2010 | Fri Aug 29 08:00:00 IDT 2014
723 |  | Ground Treatment Works for TBM Break-in | Sat May 01 08:00:00 IDT 2010 | Tue Nov 02 08:00:00 IST 2010
724 | TASK_DEPENDENT | Submission preparation & ICE checking | Sat May 01 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
725 | TASK_DEPENDENT | Engineer's review | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 12 08:00:00 IDT 2010
726 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Wed Jun 30 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
727 | TASK_DEPENDENT | Engineer's review | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
728 | TASK_DEPENDENT | Submission for RDO/BD consultation | Tue Aug 31 08:00:00 IDT 2010 | Tue Sep 28 08:00:00 IST 2010
729 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Tue Oct 05 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
730 | START_MILESTONE | Construction drawings issuance | Tue Nov 02 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
731 |  | Geotechnical Assessment Report | Mon Jun 14 08:00:00 IDT 2010 | Mon Dec 26 08:00:00 IST 2011
732 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010
733 | TASK_DEPENDENT | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
734 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Thu Oct 21 08:00:00 IST 2010 | Fri Nov 05 08:00:00 IST 2010
735 | TASK_DEPENDENT | Engineer's review | Fri Nov 05 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
736 | TASK_DEPENDENT | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
737 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
738 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
739 |  | Groundwater Assessment Report | Mon Jul 26 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
740 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010
741 | TASK_DEPENDENT | Engineer's review | Tue Sep 07 08:00:00 IDT 2010 | Tue Oct 05 08:00:00 IST 2010
742 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Wed Nov 03 08:00:00 IST 2010 | Sun Nov 21 08:00:00 IST 2010
743 | TASK_DEPENDENT | Engineer's review | Tue Nov 23 08:00:00 IST 2010 | Tue Dec 21 08:00:00 IST 2010
744 | TASK_DEPENDENT | Submission for RDO/BD consultation | Wed Oct 06 08:00:00 IST 2010 | Wed Nov 03 08:00:00 IST 2010
745 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Sat Oct 23 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
746 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
747 |  | Ground Freezing and Temporary Support of Cross Passages | Sat Jan 01 08:00:00 IST 2011 | Fri Aug 29 08:00:00 IDT 2014
748 | TASK_DEPENDENT | Submission preparation & ICE checking | Sat Jan 01 08:00:00 IST 2011 | Sat Mar 12 08:00:00 IST 2011
749 | TASK_DEPENDENT | Engineer's review | Fri Nov 25 08:00:00 IST 2011 | Fri Dec 23 08:00:00 IST 2011
750 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Fri Feb 15 08:00:00 IST 2013 | Mon Apr 01 08:00:00 IDT 2013
751 | TASK_DEPENDENT | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
752 | TASK_DEPENDENT | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
753 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014
754 | START_MILESTONE | Construction drawings issuance | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014
755 |  | Bulk Head for TBM Removal | Mon May 31 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
756 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon May 31 08:00:00 IDT 2010 | Mon Aug 09 08:00:00 IDT 2010
757 | TASK_DEPENDENT | Engineer's review | Fri Jul 30 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
758 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Thu Aug 12 08:00:00 IDT 2010 | Sun Sep 26 08:00:00 IST 2010
759 | TASK_DEPENDENT | Engineer's review | Thu Sep 16 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
760 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
761 |  | Prediction of Ground Movement | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
762 |  | Report on the Prediction of Ground Movement and and Assessment on effect of EBS | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
763 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon Jul 12 08:00:00 IDT 2010 | Tue Aug 17 08:00:00 IDT 2010
764 | TASK_DEPENDENT | Engineer's review | Sun Aug 22 08:00:00 IDT 2010 | Sun Sep 19 08:00:00 IST 2010
765 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Wed Sep 29 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
766 | TASK_DEPENDENT | Engineer's review | Wed Oct 13 08:00:00 IST 2010 | Wed Nov 10 08:00:00 IST 2010
767 | TASK_DEPENDENT | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
768 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
769 | START_MILESTONE | Construction drawings issuance | Tue Dec 27 08:00:00 IST 2011 | Tue Dec 27 08:00:00 IST 2011
770 |  | Instrumentation and Montoring Plans | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
771 |  | Instrumentation Plan | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
772 | TASK_DEPENDENT | Submission preparation & ICE checking | Mon May 03 08:00:00 IDT 2010 | Fri May 28 08:00:00 IDT 2010
773 | TASK_DEPENDENT | Engineer's review | Tue Jun 08 08:00:00 IDT 2010 | Tue Jul 06 08:00:00 IDT 2010
774 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Wed Jul 28 08:00:00 IDT 2010 | Sun Aug 15 08:00:00 IDT 2010
775 | TASK_DEPENDENT | Engineer's review | Tue Aug 10 08:00:00 IDT 2010 | Tue Sep 07 08:00:00 IDT 2010
776 | TASK_DEPENDENT | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
777 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
778 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
779 |  | Additional Ground Investigation Plans and Laboratory | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
780 |  | Further GI Plan and Lab Test Schedule | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
781 | TASK_DEPENDENT | Submission preparation & ICE checking | Tue May 31 08:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011
782 | TASK_DEPENDENT | Engineer's review | Thu Jul 14 08:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011
783 | TASK_DEPENDENT | Re-submission preparation & ICE checking | Mon Oct 31 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
784 | TASK_DEPENDENT | Engineer's review | Sat Nov 19 08:00:00 IST 2011 | Sat Dec 17 08:00:00 IST 2011
785 | TASK_DEPENDENT | Submission for RDO/BD consultation | Sat Dec 17 08:00:00 IST 2011 | Sat Jan 14 08:00:00 IST 2012
786 | TASK_DEPENDENT | Re-submission for RDO/BD consultation | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
787 | START_MILESTONE | Construction drawings issuance | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 08:00:00 IST 2013
788 |  | Procurement | Mon Mar 15 08:00:00 IST 2010 | Mon Sep 07 17:00:00 IDT 2015
789 |  | TBM Manufacture and Delivery | Mon Mar 15 08:00:00 IST 2010 | Thu Nov 01 08:00:00 IST 2012
790 | TASK_DEPENDENT | Confirmation of purchase order on TBM manufacture | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
791 | FINISH_MILESTONE | Submit PO to the Engineer | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
792 | TASK_DEPENDENT | Shop drawing preparation and submission | Thu Jul 15 08:00:00 IDT 2010 | Wed Aug 04 08:00:00 IDT 2010
793 | TASK_DEPENDENT | Shop drawing review by the Engineer | Tue Aug 24 08:00:00 IDT 2010 | Tue Sep 21 08:00:00 IST 2010
794 | TASK_DEPENDENT | Resubmission of shop drawings | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 25 08:00:00 IST 2010
795 | TASK_DEPENDENT | Engineer's approval of shop drawings | Thu Nov 18 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
796 | TASK_DEPENDENT | Shop drawings issued for manufacture | Thu Dec 16 08:00:00 IST 2010 | Fri Dec 31 08:00:00 IST 2010
797 | TASK_DEPENDENT | Manufacturing & purchase parts for TBM #1 | Mon Aug 23 08:00:00 IDT 2010 | Mon Nov 01 08:00:00 IST 2010
798 | TASK_DEPENDENT | TBM #1 factory preassembly and packing | Thu Oct 07 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
799 | TASK_DEPENDENT | TBM #1 delivery to workshop | Fri Nov 19 08:00:00 IST 2010 | Sun Dec 19 08:00:00 IST 2010
800 | TASK_DEPENDENT | TBM #1 workshop assembly | Fri Jan 07 08:00:00 IST 2011 | Fri Mar 18 08:00:00 IST 2011
801 | TASK_DEPENDENT | TBM #1 test runs, acceptance, dis-assembly and p | Mon May 16 08:00:00 IDT 2011 | Wed Jun 15 08:00:00 IDT 2011
802 | TASK_DEPENDENT | TBM #1 delivery to Shenzhen | Wed May 25 08:00:00 IDT 2011 | Sat Jun 04 08:00:00 IDT 2011
803 | FINISH_MILESTONE | TBM #1 delivery to HGP shaft | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
804 | TASK_DEPENDENT | TBM #1 on-site assembly, T&C @ HGP Shaft | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
805 | TASK_DEPENDENT | TBM #1 free walk-thru to commencement position | Fri Apr 27 08:00:00 IDT 2012 | Thu May 17 08:00:00 IDT 2012
806 | FINISH_MILESTONE | TBM #1 ready to commence drive at HGP by GSG Contractor | Wed Jul 04 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
807 | TASK_DEPENDENT | Manufacturing & purchase parts for TBM #2 | Thu Dec 16 08:00:00 IST 2010 | Thu Feb 24 08:00:00 IST 2011
808 | TASK_DEPENDENT | TBM #2 factory preassembly and packing | Mon Feb 14 08:00:00 IST 2011 | Mon Apr 25 08:00:00 IDT 2011
809 | TASK_DEPENDENT | TBM #2 delivery to workshop | Sat Mar 05 08:00:00 IST 2011 | Mon Apr 04 08:00:00 IDT 2011
810 | TASK_DEPENDENT | TBM #2 workshop assembly | Mon May 30 08:00:00 IDT 2011 | Mon Aug 08 08:00:00 IDT 2011
811 | TASK_DEPENDENT | TBM #2 test runs, acceptance, dis-assembly and p | Mon Aug 22 08:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011
812 | TASK_DEPENDENT | TBM #2 delivery to temporary storage at Nansha | Mon Sep 19 08:00:00 IDT 2011 | Thu Sep 22 08:00:00 IDT 2011
813 | TASK_DEPENDENT | TBM #2 delivery to Shenzhen | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
814 | FINISH_MILESTONE | TBM #2 delivery to HGP shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
815 | TASK_DEPENDENT | TBM #2 on-site assembly, T&C @ HGP Shaft | Thu Apr 05 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
816 | TASK_DEPENDENT | TBM #2 free walk-thru to commencement position | Mon Oct 01 08:00:00 IST 2012 | Sun Oct 21 08:00:00 IST 2012
817 | FINISH_MILESTONE | TBM #2 ready to commence drive at HGP by GSG Con | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012
818 |  | TBM Ground Support Equipment | Thu Jul 08 08:00:00 IDT 2010 | Mon Nov 05 08:00:00 IST 2012
819 | TASK_DEPENDENT | Confirm order for slurry treatment plant (STP) | Thu Jul 08 08:00:00 IDT 2010 | Thu Jul 15 08:00:00 IDT 2010
820 | TASK_DEPENDENT | STP shop drawing preparation and submission | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010
821 | TASK_DEPENDENT | STP shop drawing review by the Engineer | Wed Dec 01 08:00:00 IST 2010 | Wed Dec 29 08:00:00 IST 2010
822 | TASK_DEPENDENT | STP procurement of components and materials | Thu Dec 09 08:00:00 IST 2010 | Sun Jan 23 08:00:00 IST 2011
823 | TASK_DEPENDENT | STP resubmission of shop drawings | Mon Jan 10 08:00:00 IST 2011 | Mon Jan 24 08:00:00 IST 2011
824 | TASK_DEPENDENT | STP Engineer's approval of shop drawings | Tue Apr 05 08:00:00 IDT 2011 | Tue May 03 08:00:00 IDT 2011
825 | TASK_DEPENDENT | STP shop drawings issued for manufacture | Mon Mar 14 08:00:00 IST 2011 | Mon Mar 21 08:00:00 IST 2011
826 | TASK_DEPENDENT | STP sub-unit assembly | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 08:00:00 IDT 2011
827 | TASK_DEPENDENT | STP final assembly at factory | Wed Mar 23 08:00:00 IST 2011 | Sat Apr 02 08:00:00 IDT 2011
828 | TASK_DEPENDENT | STP factory testing | Wed Mar 30 08:00:00 IST 2011 | Sat Apr 09 08:00:00 IDT 2011
829 | TASK_DEPENDENT | STP packaging and transportation to docks | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 15 08:00:00 IDT 2011
830 | TASK_DEPENDENT | STP shipping to Shenzhen, customs clearance and forwarding | Mon Apr 04 08:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011
831 | FINISH_MILESTONE | STP delivery to HGP works area | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 12 08:00:00 IDT 2011
832 | TASK_DEPENDENT | STP on-site assembly | Wed Sep 28 08:00:00 IDT 2011 | Sat Oct 22 08:00:00 IST 2011
833 | TASK_DEPENDENT | STP on-site self testing and commissioning | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 08:00:00 IST 2012
834 | TASK_DEPENDENT | STP on-site testing and commissioning with TBM#1 | Mon Jun 18 08:00:00 IDT 2012 | Fri Jun 29 08:00:00 IDT 2012
835 | TASK_DEPENDENT | STP on-site testing and commissioning with TBM#2 | Wed Oct 03 08:00:00 IST 2012 | Sun Oct 14 08:00:00 IST 2012
836 | FINISH_MILESTONE | STP ready to commence operations for TBM #1 | Mon Jun 18 08:00:00 IDT 2012 | Mon Jun 18 08:00:00 IDT 2012
837 | FINISH_MILESTONE | STP ready to commence operations for TBM #2 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
838 |  | Tunnel Lining Segments | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 07 17:00:00 IDT 2015
839 | START_MILESTONE | Confirmation of purchase order on segment manufacturer | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
840 | TASK_DEPENDENT | Shop drawings issued for manufacture | Mon Aug 29 08:00:00 IDT 2011 | Sat Sep 10 08:00:00 IDT 2011
841 | TASK_DEPENDENT | Pre-casting trials | Thu Nov 03 08:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011
842 | TASK_DEPENDENT | Engineer's approval of trial segments | Thu Dec 15 08:00:00 IST 2011 | Thu Jan 12 08:00:00 IST 2012
843 | TASK_DEPENDENT | Manufacture 926 Tunnel Rings (SZ) | Wed Feb 01 08:00:00 IST 2012 | Fri Jul 20 08:00:00 IDT 2012
844 | TASK_DEPENDENT | Manufacture 163 Tunnel Rings (SZ) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 25 08:00:00 IST 2012
845 | TASK_DEPENDENT | Manufacture 105 Tunnel Rings (SZ) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012
846 | TASK_DEPENDENT | Manufacture 98 Tunnel Rings (SZ) | Wed Oct 31 08:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012
847 | TASK_DEPENDENT | Manufacture 250 Tunnel Rings (SZ) | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 26 08:00:00 IST 2012
848 | TASK_DEPENDENT | Manufacture 250 Tunnel Rings (SZ) | Sun Jan 13 08:00:00 IST 2013 | Thu Feb 07 08:00:00 IST 2013
849 | TASK_DEPENDENT | Manufacture 60 Tunnel Rings (SZ) | Sun Feb 24 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013
850 | TASK_DEPENDENT | Manufacture 81 Tunnel Rings (HK) | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 08:00:00 IDT 2013
851 | TASK_DEPENDENT | Manufacture 76 Tunnel Rings (HK) | Sun Jun 30 08:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013
852 | TASK_DEPENDENT | Manufacture 75 Tunnel Rings (HK) | Mon Jul 01 08:00:00 IDT 2013 | Fri Jul 26 08:00:00 IDT 2013
853 | TASK_DEPENDENT | Manufacture 88 Tunnel Rings (HK) | Thu Aug 01 08:00:00 IDT 2013 | Sun Aug 25 08:00:00 IDT 2013
854 | TASK_DEPENDENT | Manufacture 120 Tunnel Rings (HK) | Sun Sep 01 08:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013
855 | TASK_DEPENDENT | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Fri Jan 24 08:00:00 IST 2014
856 | TASK_DEPENDENT | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
857 | TASK_DEPENDENT | Manufacture 120 Tunnel Rings (HK) | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
858 | TASK_DEPENDENT | Manufacture 120 Tunnel Rings (HK) | Tue Jul 01 08:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014
859 | TASK_DEPENDENT | Manufacture 100 Tunnel Rings (HK) | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014
860 | TASK_DEPENDENT | Manufacture 50 Tunnel Rings (HK) | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
861 | TASK_DEPENDENT | Manufacture 50 Tunnel Rings (HK) | Mon Feb 16 07:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
862 | TASK_DEPENDENT | Manufacture 100 Tunnel Rings (HK) | Tue Mar 03 07:00:00 IST 2015 | Fri Mar 27 17:00:00 IDT 2015
863 | TASK_DEPENDENT | Manufacture 60 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Sat May 02 17:00:00 IDT 2015
864 | TASK_DEPENDENT | Manufacture 100 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Fri May 15 17:00:00 IDT 2015
865 | TASK_DEPENDENT | Manufacture 100 Tunnel Rings (HK) | Sun Aug 09 07:00:00 IDT 2015 | Wed Sep 02 17:00:00 IDT 2015
866 | TASK_DEPENDENT | Manufacture 10 Tunnel Rings (HK) | Thu Sep 03 07:00:00 IDT 2015 | Mon Sep 07 17:00:00 IDT 2015
867 | TASK_DEPENDENT | Ship & Deliver Tunnel Rings to HGP (SZ rings) | Wed Aug 01 08:00:00 IDT 2012 | Wed Dec 26 08:00:00 IST 2012
868 | TASK_DEPENDENT | Ship & Deliver Tunnel Rings to HGP (HK rings) | Sat Nov 30 08:00:00 IST 2013 | Sun Oct 12 08:00:00 IDT 2014
869 |  | Segment Mould Design, Fabrication and Delivery | Mon May 16 08:00:00 IDT 2011 | Wed Feb 15 08:00:00 IST 2012
870 | START_MILESTONE | Confirm order for moulds | Mon May 16 08:00:00 IDT 2011 | Mon May 16 08:00:00 IDT 2011
871 | TASK_DEPENDENT | Design and planning | Mon May 16 08:00:00 IDT 2011 | Thu Jun 09 08:00:00 IDT 2011
872 | TASK_DEPENDENT | Design mould drawings for manufacture | Fri Jul 08 08:00:00 IDT 2011 | Sun Aug 07 08:00:00 IDT 2011
873 | TASK_DEPENDENT | Materials procurement | Fri Jul 08 08:00:00 IDT 2011 | Thu Jul 28 08:00:00 IDT 2011
874 | TASK_DEPENDENT | Factory assembly | Mon Jul 18 08:00:00 IDT 2011 | Fri Sep 16 08:00:00 IDT 2011
875 | TASK_DEPENDENT | Shipping and delivery to Shenzhen - 1st batch (3 sets) | Sat Nov 05 08:00:00 IST 2011 | Thu Nov 10 08:00:00 IST 2011
876 | TASK_DEPENDENT | Shipping and delivery to Shenzhen - 2nd batch (3 sets) | Fri Feb 10 08:00:00 IST 2012 | Wed Feb 15 08:00:00 IST 2012
877 | TASK_DEPENDENT | Mould erection and commissioning ready for production in precast yard | Thu Nov 10 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
878 |  | Other Procurement Items | Tue Nov 02 08:00:00 IST 2010 | Sun Apr 06 08:00:00 IDT 2014
879 | TASK_DEPENDENT | Transformer and substation procurement | Tue May 31 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
880 | TASK_DEPENDENT | Procure temporary electrics subcontractor | Wed Jun 01 08:00:00 IDT 2011 | Fri Jul 01 08:00:00 IDT 2011
881 | TASK_DEPENDENT | Place order for ready mixed concrete | Fri Mar 01 08:00:00 IST 2013 | Sat Apr 06 08:00:00 IDT 2013
882 | TASK_DEPENDENT | Procure other major construction plant and equip | Tue Mar 01 08:00:00 IST 2011 | Mon May 30 08:00:00 IDT 2011
883 | TASK_DEPENDENT | Place order for rebar supply | Mon Oct 31 08:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011
884 | TASK_DEPENDENT | Rental agreement for off site office accommodation | Tue Nov 02 08:00:00 IST 2010 | Thu Dec 02 08:00:00 IST 2010
885 | TASK_DEPENDENT | Procure tunnel personnel electronic tagging system | Sat Nov 30 08:00:00 IST 2013 | Sat Jan 11 08:00:00 IST 2014
886 | TASK_DEPENDENT | Procure tunnel ventilation system | Thu Mar 01 08:00:00 IST 2012 | Tue Apr 10 08:00:00 IDT 2012
887 | TASK_DEPENDENT | Procure ground freezing specialist subcontractor | Sat Mar 01 08:00:00 IST 2014 | Sun Apr 06 08:00:00 IDT 2014
888 |  | Site Mobilisation | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
889 | TASK_DEPENDENT | Initial project staff assignments | Mon Mar 15 08:00:00 IST 2010 | Sun Jun 13 08:00:00 IDT 2010
890 | TASK_DEPENDENT | Establish Works Areas at HGP | Wed Dec 01 08:00:00 IST 2010 | Tue Jan 18 08:00:00 IST 2011
891 | TASK_DEPENDENT | Establish Works Areas at MPV | Fri Feb 01 08:00:00 IST 2013 | Sat Mar 09 08:00:00 IST 2013
892 | TASK_DEPENDENT | Establish and operate Project Office in Hong Kong | Thu Apr 22 08:00:00 IDT 2010 | Fri Feb 18 08:00:00 IST 2011
893 | TASK_DEPENDENT | Establish and operate Project Office in Shenzhen | Mon Jan 10 08:00:00 IST 2011 | Sat Oct 01 08:00:00 IDT 2016
894 | TASK_DEPENDENT | Establish and operate Project Office in Mai Po | Tue Mar 15 08:00:00 IST 2011 | Fri Jul 25 08:00:00 IDT 2014
895 | START_MILESTONE | Commencement to operate compound at Mai Po, Area 1.19, for DLP | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
1 | None | 826 As-built Programme | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
2 | None | 826 - HGP to Mai Po Tunnels, Revised Master Prog | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
3 | None | Tender and Contract Details | Wed Mar 10 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
4 | None | Tender Actions | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
5 | START_MILESTONE | Contract Award (LoA) | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
6 | None | Critical Contract Dates | Mon Mar 15 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
7 | START_MILESTONE | Stated Contract Commencement Date (Cl 64) | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 15 08:00:00 IST 2010
8 | FINISH_MILESTONE | Table 3, Ref 3A - Delivery of the first TBM to HGP | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
9 | FINISH_MILESTONE | Table 3, Ref 3B - All works in Works Area 1.6 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
10 | FINISH_MILESTONE | Table 3, Ref 3C - Delivery of the second TBM to HGP | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
11 | FINISH_MILESTONE | Table 4, Ref 4A - Achieve Deg. 1 for both Up and Down Track Tunnels | Thu Mar 31 17:00:00 IDT 2016 | Thu Mar 31 17:00:00 IDT 2016
12 | FINISH_MILESTONE | Table 1 - Completion of the Whole of the Works (wk13/2015) | Thu Jun 01 17:00:00 IDT 2017 | Thu Jun 01 17:00:00 IDT 2017
13 | None | Other Programme Data | Thu May 09 08:00:00 IDT 2013 | Sat Apr 01 07:00:00 IDT 2017
14 | START_MILESTONE | GSG Contractor to hand over S623 to Cont' 826 at HK Boundary | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013
15 | START_MILESTONE | GSG Contractor to hand over S624 to Cont' 826 at HK Boundary | Thu May 09 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
16 | START_MILESTONE | Notification to Contract 846 for cable bracket installation | Sun Nov 22 07:00:00 IST 2015 | Sun Nov 22 07:00:00 IST 2015
17 | FINISH_MILESTONE | Provision of TBM Retrieval Shaft at MPV | Wed Oct 01 07:00:00 IDT 2014 | Wed Oct 01 07:00:00 IDT 2014
18 | START_MILESTONE | OHL Power On, by Designated Contractor 830 | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
19 | None | Access Dates for Designated Contractors | Sun May 01 07:00:00 IDT 2016 | Thu Dec 01 07:00:00 IST 2016
20 | START_MILESTONE | 827, X-passage Doors - Door Frame Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
21 | START_MILESTONE | 827, X-passage Doors - Doors Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
22 | START_MILESTONE | 830, Trackwork and OHL - Up-track | Sun May 01 07:00:00 IDT 2016 | Sun May 01 07:00:00 IDT 2016
23 | START_MILESTONE | 830, Trackwork and OHL - Down-track | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
24 | START_MILESTONE | 841A, Signalling System, Trackside Eqpt - Both tunnels | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
25 | START_MILESTONE | 846, Trackside Aux - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
26 | START_MILESTONE | 849, Radio Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
27 | START_MILESTONE | 850, Passenger Mobile Communications Systems - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
28 | START_MILESTONE | 851, Fixed Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
29 | START_MILESTONE | 8203, Constrn Stage Mobile Phone Network - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
30 | None | Interface Contractor Programme - GSG | Wed Dec 01 08:00:00 IST 2010 | Sat Mar 01 07:00:00 IST 2014
31 | FINISH_MILESTONE | Complete Huanggang Park shaft construction | Mon Mar 26 08:00:00 IST 2012 | Mon Mar 26 08:00:00 IST 2012
32 | TT_TASK | Drill & Blast Tunnel (to HK) | Wed Dec 01 08:00:00 IST 2010 | Tue Sep 27 08:00:00 IDT 2011
33 | TT_TASK | S623 Excavate 242m (SZ) (s.rock) | Tue Jul 03 08:00:00 IDT 2012 | Sat Oct 06 08:00:00 IST 2012
34 | TT_TASK | S623 Conduct General Maintenance | Sun Oct 07 08:00:00 IST 2012 | Wed Oct 10 08:00:00 IST 2012
35 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 484m) | Wed Oct 10 08:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012
36 | TT_TASK | S623 Conduct General Maintenance | Sun Nov 18 08:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012
37 | TT_TASK | S623 Excavate 220m (SZ) (s.rock/total 704m) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 29 08:00:00 IST 2012
38 | TT_TASK | S623 Conduct General Maintenance | Tue Jan 08 08:00:00 IST 2013 | Sat Jan 12 08:00:00 IST 2013
39 | TT_TASK | S623 Excavate 150m (SZ) (m.rock/total 854m) | Sat Jan 12 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
40 | TT_TASK | S623 Conduct General Maintenance | Wed Feb 20 08:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013
41 | TT_TASK | S623 Excavate 50m (SZ) (s.rock/total 904m) | Thu Feb 28 08:00:00 IST 2013 | Fri Mar 08 08:00:00 IST 2013
42 | TT_TASK | S623 Conduct General Maintenance | Sun Apr 21 08:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013
43 | TT_TASK | S623 Excavate 100m (SZ) (rock/total 1004m) | Mon Apr 22 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
44 | TT_TASK | S623 Conduct General Maintenance | Sat Jun 08 10:38:00 IDT 2013 | Mon Jun 10 10:38:00 IDT 2013
45 | TT_TASK | S623 Excavate 470m (SZ) (rock/total 1474m) | Wed May 15 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
46 | TT_TASK | S623 Conduct General Maintenance | Fri Sep 13 08:00:00 IDT 2013 | Sun Sep 15 08:00:00 IDT 2013
47 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Aug 15 08:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013
48 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013
49 | TT_TASK | S623 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Oct 31 08:00:00 IST 2013 | Sun Nov 10 08:00:00 IST 2013
50 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013
51 | TT_TASK | S623 Excavate 84m (SZ) (c.rock/total 1856m) | Thu Oct 31 08:00:00 IST 2013 | Sat Nov 02 08:00:00 IST 2013
52 | FINISH_MILESTONE | Complete TBM Excavation Down Track (SZ) | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 08:00:00 IST 2013
53 | TT_TASK | S624 Excavate 100m (SZ) (s.rock) | Mon Nov 05 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
54 | TT_TASK | S624 Conduct General Maintenance | Mon Dec 10 08:00:00 IST 2012 | Thu Dec 13 08:00:00 IST 2012
55 | TT_TASK | S624 Excavate 142m (SZ) (s.rock/total 242m) | Thu Dec 13 08:00:00 IST 2012 | Sun Jan 06 08:00:00 IST 2013
56 | TT_TASK | S624 Conduct General Maintenance | Sat Jan 05 08:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013
57 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 484m) | Tue Jan 08 08:00:00 IST 2013 | Sun Feb 17 08:00:00 IST 2013
58 | TT_TASK | S624 Conduct General Maintenance | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 08:00:00 IST 2013
59 | TT_TASK | S624 Excavate 220m (SZ) (s.rock/total 704m) | Tue Feb 19 08:00:00 IST 2013 | Thu Mar 28 08:00:00 IST 2013
60 | TT_TASK | S624 Conduct General Maintenance | Fri Jun 28 08:58:00 IDT 2013 | Mon Jul 01 08:58:00 IDT 2013
61 | TT_TASK | S624 Excavate 150m (SZ) (m.rock/total 854m) | Tue Jul 02 08:58:00 IDT 2013 | Mon Jul 22 08:58:00 IDT 2013
62 | TT_TASK | S624 Conduct General Maintenance | Wed Jul 24 08:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013
63 | TT_TASK | S624 Excavate 50m (SZ) (s.rock/total 904m) | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
64 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 08:00:00 IDT 2013
65 | TT_TASK | S624 Excavate 100m (SZ) (s/m.rock/total 1004m) | Tue Aug 06 08:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013
66 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 26 08:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013
67 | TT_TASK | S624 Excavate 470m (SZ) (s/m.rock/total 1474m) | Fri Sep 13 08:00:00 IDT 2013 | Sun Dec 01 08:00:00 IST 2013
68 | TT_TASK | S624 Conduct General Maintenance | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
69 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Jan 30 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
70 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
71 | TT_TASK | S624 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Jan 30 08:00:00 IST 2014 | Sun Feb 09 08:00:00 IST 2014
72 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
73 | TT_TASK | S624 Excavate 92m (SZ) (c.rock/total 1864m) | Thu Jan 30 08:00:00 IST 2014 | Tue Feb 11 08:00:00 IST 2014
74 | FINISH_MILESTONE | Complete TBM Excavation Up Track (SZ) | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
75 | None | Interface Contractor Programme - 825 | Tue Sep 21 08:00:00 IST 2010 | Thu Dec 01 07:00:00 IST 2016
76 | FINISH_MILESTONE | TBM shaft for Contract 826 within Works Area 1.5 | Tue Jun 09 11:00:00 IDT 2015 | Tue Jun 09 11:00:00 IDT 2015
77 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - first time | Tue Sep 21 08:00:00 IST 2010 | Tue Sep 21 08:00:00 IST 2010
78 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - second time | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
79 | TT_TASK | Cut & cover tunnel Bay 1 tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 20 08:00:00 IST 2014
80 | TT_TASK | Cut & cover tunnel Bay 2 tunnel construction | Sat Nov 30 08:00:00 IST 2013 | Mon Feb 17 08:00:00 IST 2014
81 | FINISH_MILESTONE | 826 to complete all works at interface and allow 825 access | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
82 | TT_TASK | 825 complete stitch joint to 826 tunnel | Sun May 01 07:00:00 IDT 2016 | Sat Jun 25 17:00:00 IDT 2016
83 | FINISH_MILESTONE | Return of Works Area 1.5 to 825 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
84 | None | Interface Contractor Programme - 830 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
85 | TT_TASK | Allow concrete pumping access for Contract 830 within Works Area 1.5 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
86 | None | Works Areas | Mon Sep 20 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
87 | None | Access Dates | Mon Sep 20 08:00:00 IST 2010 | Thu Nov 05 07:00:00 IST 2015
88 | START_MILESTONE | Works Area 1.3 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
89 | START_MILESTONE | Works Area 1.4A (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
90 | START_MILESTONE | Works Area 1.4B first time (36/2010, 13 Sep 10) | Mon Sep 20 08:00:00 IST 2010 | Mon Sep 20 08:00:00 IST 2010
91 | START_MILESTONE | Works Area 1.4B second time (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
92 | START_MILESTONE | Works Area 1.5 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
93 | START_MILESTONE | Works Area 1.6 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
94 | START_MILESTONE | Works Area 1.16 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
95 | START_MILESTONE | Works Area 1.17 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
96 | START_MILESTONE | Works Area 1.19 (47/2010, 29 Nov 10) | Mon Nov 29 08:00:00 IST 2010 | Mon Nov 29 08:00:00 IST 2010
97 | START_MILESTONE | Works Area 1.21 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
98 | None | Return Dates | Fri Dec 17 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
99 | FINISH_MILESTONE | Works Area 1.3 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
100 | FINISH_MILESTONE | Works Area 1.4A (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
101 | FINISH_MILESTONE | Works Area 1.4B first time (01/2011, 9 Jan 11) | Fri Dec 17 08:00:00 IST 2010 | Fri Dec 17 08:00:00 IST 2010
102 | FINISH_MILESTONE | Works Area 1.4B second time (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
103 | FINISH_MILESTONE | Works Area 1.5 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
104 | FINISH_MILESTONE | Works Area 1.6 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
105 | FINISH_MILESTONE | Works Area 1.16 (36/2013, 8 Sep 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
106 | FINISH_MILESTONE | Works Area 1.17 (50/2013, 15 Dec 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
107 | FINISH_MILESTONE | Works Area 1.19 (10 May 16) | Tue Feb 28 17:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017
108 | FINISH_MILESTONE | Works Area 1.21 (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
109 | None | Specified Milestone Dates | Sun Apr 25 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
110 | None | Cost Centre A | Sun Jun 27 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
111 | FINISH_MILESTONE | A1 (25/2010, 27 Jun 10) - Contractor's Submissions | Sun Jun 27 08:00:00 IDT 2010 | Sun Jun 27 08:00:00 IDT 2010
112 | FINISH_MILESTONE | A2 (51/2010, 26 Dec 10) - Approval of TBM Tunnelling method Statement | Wed Jan 05 08:00:00 IST 2011 | Wed Jan 05 08:00:00 IST 2011
113 | FINISH_MILESTONE | A3 (08/2011, 27 Feb 11) - Implementation of Specified Plans and Programming | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
114 | FINISH_MILESTONE | A4 (38/2011, 25 Sep 11) - Delivery of 2 nos. TBM to HGP Launching Shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
115 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of the MS of Construction of Cross Passages | Thu Feb 23 08:00:00 IST 2012 | Thu Feb 23 08:00:00 IST 2012
116 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of Detailed Interface Require Specific with Designated Contractor | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
117 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Implementation of Specified Plans | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
118 | FINISH_MILESTONE | A6 (08/2012, 26 Feb 12) - Implementation of Specified Plans and Programme | Fri Feb 24 08:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012
119 | FINISH_MILESTONE | A7 (25/2012, 24 Jun 12) - Approval of Detailed Interface Require Specific with Designated Contractor | Tue Jul 31 08:00:00 IDT 2012 | Tue Jul 31 08:00:00 IDT 2012
120 | FINISH_MILESTONE | A8 (34/2012, 26 Aug 12) - Implementation of Specified Plans | Wed Aug 22 08:00:00 IDT 2012 | Wed Aug 22 08:00:00 IDT 2012
121 | FINISH_MILESTONE | *A9 (48/2014, 30 Nov 14) - Complete 28% of the 1st tunnel drive | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 01 07:00:00 IST 2014
122 | FINISH_MILESTONE | A9a (08/2013, 24 Feb 13) - Implementation of Specific Plans and Program | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
123 | FINISH_MILESTONE | *A9b (08/2014, 1 May 14) - Complete 15% of the 1st tunnel drive | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
124 | FINISH_MILESTONE | A10 (34/2013, 25 Aug 13) - Implementation of Specific Plans | Tue Jul 15 17:00:00 IDT 2014 | Tue Jul 15 17:00:00 IDT 2014
125 | FINISH_MILESTONE | *A11 (51/2015, 27 Dec 15) - Achieve Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
126 | FINISH_MILESTONE | A12 (32/2014, 10 Aug 14) - Approval of Draft O & M Manuals and Draft As-built drawings | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
127 | FINISH_MILESTONE | A13 (06/2015, 8 Feb 15) - Approval of Operating & Maintenance Mauls | Fri Feb 24 17:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017
128 | None | Cost Centre B | Sun Apr 25 08:00:00 IDT 2010 | Fri Apr 01 07:00:00 IDT 2016
129 | FINISH_MILESTONE | B1.1 (16/2010, 25 Apr 10) - Provide Evidence that TBM | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
130 | FINISH_MILESTONE | B1a (25/2010, 27 Jun 10) - On-demand bond or bank guarantee | Sat Jun 26 08:00:00 IDT 2010 | Sat Jun 26 08:00:00 IDT 2010
131 | FINISH_MILESTONE | B1.2 (28/2010, 18 Jul 10) - Provide Evidence that the STP | Thu Jul 29 08:00:00 IDT 2010 | Thu Jul 29 08:00:00 IDT 2010
132 | FINISH_MILESTONE | B2 (21/2011, 29 May 11) - Delivery of the 1st TBM | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
133 | FINISH_MILESTONE | B2a (38/2011, 25 Sep 11) - Delivery of the 2nd TBM | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
134 | FINISH_MILESTONE | B3 (49/2013, 8 Dec 13) - Complete Final Disassembly of TBM | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
135 | None | Cost Centre C (UT/S624) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
136 | FINISH_MILESTONE | C1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
137 | FINISH_MILESTONE | *C2 (17/2014, 27 Apr 14) - Complete 10% Tunnel Drive & 70% Segments | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
138 | FINISH_MILESTONE | *C3 (52/2014, 28 Dec 14) - Complete 40% Tunnel Drive & 95% Segments | Mon Feb 23 07:00:00 IST 2015 | Mon Feb 23 07:00:00 IST 2015
139 | FINISH_MILESTONE | *C4 (26/2015, 28 Jun 15) - Complete 100% Tunnel Drive | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
140 | FINISH_MILESTONE | *C5 (35/2015, 30 Aug 15) -Complete 50% Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
141 | FINISH_MILESTONE | *C6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
142 | FINISH_MILESTONE | C7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
143 | None | Cost Centre D (DT/S623) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
144 | FINISH_MILESTONE | D1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
145 | FINISH_MILESTONE | D2 (10/2013, 10MAR13) - Complete 5% Tunnel Drive & 40% Segments | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
146 | FINISH_MILESTONE | *D3 (48/2014, 30 Nov 14) -Complete 28% Tunnel Drive & 85% Segments | Tue Jun 30 07:00:00 IDT 2015 | Tue Jun 30 07:00:00 IDT 2015
147 | FINISH_MILESTONE | *D4 (35/2015, 30 Aug 15) -Complete 100% Tunnel Drive | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
148 | FINISH_MILESTONE | *D5 (43/2015, 25 Oct 15) - Complete 50% of Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
149 | FINISH_MILESTONE | *D6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
150 | FINISH_MILESTONE | D7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
151 | None | Cost Centre E (CP) | Thu Dec 16 08:00:00 IST 2010 | Sat Dec 31 17:00:00 IST 2016
152 | FINISH_MILESTONE | E1 (01/2011, 9 Jan 11) - Complete Ground Treatment | Thu Dec 16 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
153 | FINISH_MILESTONE | E2 (08/2011, 27 Feb 11) - Submit instrumentation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
154 | FINISH_MILESTONE | E3 (34/2011, 28 Aug 11) - Submit instrumentation | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
155 | FINISH_MILESTONE | E4 (08/2012, 26 Feb 12) - Submit instrumentation | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 08:00:00 IST 2012
156 | FINISH_MILESTONE | E5 (34/2012, 26 Aug 12) - Submit instrumentation | Sat Aug 25 08:00:00 IDT 2012 | Sat Aug 25 08:00:00 IDT 2012
157 | FINISH_MILESTONE | E6 (08/2013, 24 Feb 13) - Submit instrumentation | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
158 | FINISH_MILESTONE | E7 (48/2013, 30 Nov 13) - Major ground treatment plant for CPs | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 01 07:00:00 IST 2015
159 | FINISH_MILESTONE | E8 (13/2015, 29 Mar 15) - Complete 4 Cross Passage Ground Treatment | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
160 | FINISH_MILESTONE | *E9 (51/2015, 20 Dec 15) - Deg 1 Completion in Cross Passage | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
161 | FINISH_MILESTONE | E10 (25/2016) - All Works Complete | Sat Dec 31 17:00:00 IST 2016 | Sat Dec 31 17:00:00 IST 2016
162 | None | Construction and Site Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
163 | None | Surface Operations in Works Areas | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
164 | None | Huanggang Park | Tue Nov 02 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
165 | TT_TASK | Establish MTRC Project Office in Shenzhen | Tue Nov 02 08:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010
166 | TT_TASK | Establish 826 HGP Site Office | Tue Nov 30 08:00:00 IST 2010 | Mon Jan 17 08:00:00 IST 2011
167 | TT_TASK | University Games Period | Mon Aug 01 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
168 | TT_TASK | Operation and maintenance of ground support facilities during tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Tue Oct 31 08:00:00 IST 2017
169 | None | Mai Po Retrieval Shaft | Fri Aug 06 08:00:00 IDT 2010 | Tue Apr 21 08:00:00 IDT 2015
170 | None | Ground Treatment Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Feb 01 08:00:00 IST 2011
171 | FINISH_MILESTONE | Submit Inspection and Testing Plan for ground treatment works | Fri Aug 06 08:00:00 IDT 2010 | Fri Aug 06 08:00:00 IDT 2010
172 | TT_TASK | Engineer's review on Inspection and Testing Plan | Fri Aug 06 08:00:00 IDT 2010 | Fri Sep 03 08:00:00 IDT 2010
173 | TT_TASK | Establish Works Area 1.4B with 825 Contractor | Mon Sep 20 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
174 | TT_TASK | Set up grouting plant | Tue Oct 05 08:00:00 IST 2010 | Fri Oct 15 08:00:00 IST 2010
175 | TT_TASK | Drilling - Down Track tunnel | Thu Oct 07 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
176 | TT_TASK | Drilling - Up Track tunnel | Mon Oct 18 08:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010
177 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 04 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
178 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 11 08:00:00 IST 2010 | Sat Nov 27 08:00:00 IST 2010
179 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
180 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
181 | TT_TASK | Permeability testing - Down Track tunnel | Tue Dec 07 08:00:00 IST 2010 | Mon Dec 13 08:00:00 IST 2010
182 | TT_TASK | Permeability testing - Up Track tunnel | Wed Dec 08 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
183 | TT_TASK | Demobilise grout plant | Mon Dec 13 08:00:00 IST 2010 | Sat Dec 18 08:00:00 IST 2010
184 | TT_TASK | Clear Works Area 1.4B for 825 Contractor's D.Wall | Mon Dec 13 08:00:00 IST 2010 | Wed Dec 22 08:00:00 IST 2010
185 | TT_TASK | Install instrumentation and monitoring equipment | Thu Oct 28 08:00:00 IST 2010 | Tue Feb 01 08:00:00 IST 2011
186 | None | Jet Grouting Works for TBM Break-out | Tue Dec 31 08:00:00 IST 2013 | Tue Nov 18 08:00:00 IST 2014
187 | TT_TASK | Submit Method Statement for Jet Grouting Works | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 27 08:00:00 IST 2014
188 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
189 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 22 08:00:00 IST 2014
190 | TT_TASK | Trial of Jet grouting | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 27 08:00:00 IST 2014
191 | TT_TASK | Jet Grouting Works | Fri Jul 18 08:00:00 IDT 2014 | Tue Nov 18 08:00:00 IST 2014
192 | None | Ground Freezing Plant | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
193 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Ground freezing | Tue Mar 24 08:00:00 IST 2015 | Tue Mar 24 08:00:00 IST 2015
194 | TT_TASK | Engineer's review on Inspection and Testing Plan | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
195 | None | TBM Drives from Boundary to Mai Po Shaft | Fri May 10 08:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
196 | None | Down Track - Ch.115+929 to Ch.117+400 | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 16 17:00:00 IST 2015
197 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
198 | TT_TASK | Continue S623 drive, ch. 115+929 to ch. 115+950 in soil | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013
199 | TT_TASK | Continue S623 drive, ch. 115+950 to ch. 115+983 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Sat Jan 04 08:00:00 IST 2014
200 | TT_TASK | Continue S623 drive, ch. 115+983 to ch. 116+050 in soil | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 08 08:00:00 IST 2014
201 | TT_TASK | Continue S623 drive, ch. 116+050 to ch. 116+213 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
202 | TT_TASK | Continue S623 drive, ch. 116+213 to ch. 116+230 in soil | Tue Apr 01 08:00:00 IDT 2014 | Thu Apr 03 08:00:00 IDT 2014
203 | TT_TASK | Continue S623 drive, ch. 116+230 to ch. 116+260 in marble | Tue Apr 01 08:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014
204 | TT_TASK | Continue S623 drive, ch. 116+260 to ch. 116+284 in marble | Tue Jul 01 08:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014
205 | TT_TASK | TBM Cutter Head Repair & S624 Overtaking Stoppage | Fri Aug 01 08:00:00 IDT 2014 | Fri Oct 24 08:00:00 IDT 2014
206 | TT_TASK | Continue S623 drive, ch. 116+284 to ch. 116+319 in marble | Fri Nov 21 07:00:00 IST 2014 | Mon Dec 01 17:00:00 IST 2014
207 | TT_TASK | Continue S623 drive, ch. 116+319 to ch. 116+349 in marble | Wed Feb 04 07:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
208 | TT_TASK | Continue S623 drive, ch. 116+349 to ch. 116+379 in marble | Sun Feb 01 07:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
209 | TT_TASK | Continue S623 drive, ch. 116+379 to ch. 116+408 in marble | Sun Mar 01 07:00:00 IST 2015 | Thu Mar 05 01:00:00 IST 2015
210 | TT_TASK | Continue S623 drive, ch. 116+408 to ch. 116+430 in marble | Sun Mar 01 07:00:00 IST 2015 | Sat Mar 07 17:00:00 IST 2015
211 | TT_TASK | Continue S623 drive, ch. 116+430 to ch. 116+600 in soil | Sun Mar 01 07:00:00 IST 2015 | Mon Mar 30 17:00:00 IDT 2015
212 | TT_TASK | Continue S623 drive, ch. 116+600 to ch. 116+694 in soil | Fri Jul 17 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
213 | TT_TASK | Continue S623 drive, ch. 116+694 to ch. 116+927 in Alluvial zone | Tue Jun 30 07:00:00 IDT 2015 | Thu Sep 17 17:00:00 IDT 2015
214 | TT_TASK | Continue S623 drive, ch. 116+927 to ch. 116+945 in soil | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
215 | TT_TASK | Continue S623 drive, ch. 116+945 to ch. 117+400 in soil | Tue Sep 29 07:00:00 IDT 2015 | Wed Dec 16 17:00:00 IST 2015
216 | TT_TASK | Pre-coring at diaphragm wall after TBM S623 arrival | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
217 | TT_TASK | TBM Breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
218 | None | S623 TBM Removal | Thu Oct 22 07:00:00 IDT 2015 | Thu Dec 01 07:00:00 IST 2016
219 | TT_TASK | Move TBM S623 front portion to cradle | Thu Oct 22 07:00:00 IDT 2015 | Tue Oct 27 17:00:00 IST 2015
220 | TT_TASK | Weld additional bracing brackets corbels | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
221 | TT_TASK | Install cradle on lateral shifting system | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
222 | TT_TASK | Move and shift TBM to dismantle location | Thu Apr 07 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
223 | TT_TASK | Dismantle Cutter Head & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
224 | TT_TASK | Dismantle TBM rear & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
225 | TT_TASK | Dismantle segment installation machine & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
226 | TT_TASK | Dismantle TBM middle sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
227 | TT_TASK | Dismantle TBM front sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
228 | TT_TASK | Dismantle S623 Link Bridge & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
229 | TT_TASK | Dismantle S623 Wagon #1 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
230 | TT_TASK | Dismantle S623 Wagon #2 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
231 | TT_TASK | Dismantle S623 Wagon #3 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
232 | TT_TASK | Dismantle S623 Wagon #4 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
233 | TT_TASK | Dismantle S623 Wagon #5 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
234 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N1 | Thu Jun 23 07:00:00 IDT 2016 | Thu Jun 23 07:00:00 IDT 2016
235 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N2 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
236 | TT_TASK | Site clearance | Fri Apr 01 07:00:00 IDT 2016 | Tue Sep 27 17:00:00 IDT 2016
237 | None | Up Track - Ch.115+940 to Ch.117+413 | Fri May 10 08:00:00 IDT 2013 | Fri Oct 09 17:00:00 IDT 2015
238 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Fri May 10 08:00:00 IDT 2013 | Sat May 11 08:00:00 IDT 2013
239 | TT_TASK | Continue S624 drive, ch. 115+939 to ch. 115+950 in soil | Fri May 09 08:00:00 IDT 2014 | Sat May 10 08:00:00 IDT 2014
240 | TT_TASK | Continue S624 drive, ch. 115+950 to ch. 115+987 in mixed ground | Fri May 09 08:00:00 IDT 2014 | Tue May 13 08:00:00 IDT 2014
241 | TT_TASK | Continue S624 drive, ch. 115+987 to ch. 116+050 in soil | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 08:00:00 IDT 2014
242 | TT_TASK | Continue S624 drive, ch. 116+050 to ch. 116+226 in mixed ground | Sun Jun 01 08:00:00 IDT 2014 | Wed Jul 02 08:00:00 IDT 2014
243 | TT_TASK | Continue S624 drive, ch. 116+226 to ch. 116+240 in soil/marble | Fri Aug 01 08:00:00 IDT 2014 | Sun Aug 03 08:00:00 IDT 2014
244 | TT_TASK | Continue S624 drive, ch. 116+240 to ch. 116+270 in marble | Fri Aug 01 08:00:00 IDT 2014 | Wed Aug 13 08:00:00 IDT 2014
245 | TT_TASK | Continue S624 drive, ch. 116+270 to ch. 116+300 in marble | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014
246 | TT_TASK | Continue S624 drive, ch. 116+300 to ch. 116+329 in marble | Wed Oct 01 08:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014
247 | TT_TASK | Continue S624 drive, ch. 116+329 to ch. 116+358 in marble | Sat Nov 01 07:00:00 IST 2014 | Mon Nov 17 17:00:00 IST 2014
248 | TT_TASK | Continue S624 drive, ch. 116+358 to ch. 116+388 in marble | Sun Nov 23 07:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
249 | TT_TASK | Continue S624 drive, ch. 116+388 to ch. 116+415 in marble | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 02 17:00:00 IST 2015
250 | TT_TASK | Continue S624 drive, ch. 116+415 to ch. 116+430 in soil/marble | Sun Jan 11 07:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
251 | TT_TASK | Continue S624 drive, ch. 116+430 to ch. 116+600 in soil | Tue Jan 13 07:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
252 | TT_TASK | Continue S624 drive, ch. 116+600 to ch. 116+850 in soil/Alluv. zone | Wed Jan 21 07:00:00 IST 2015 | Thu Mar 05 17:00:00 IST 2015
253 | TT_TASK | Continue S624 drive, ch. 116+850 to ch. 116+930 in Alluv. zone | Tue Mar 31 07:00:00 IDT 2015 | Mon Apr 13 17:00:00 IDT 2015
254 | TT_TASK | Continue S624 drive, ch. 116+930 to ch. 117+413 in soil at Mai Po | Thu Jul 16 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
255 | TT_TASK | Pre-coring at diaphragm wall after TBM S624 arrival | Sat Aug 15 07:00:00 IDT 2015 | Mon Aug 17 17:00:00 IDT 2015
256 | TT_TASK | TBM S624 breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
257 | None | TBM Removal Preparation | Mon Dec 01 07:00:00 IST 2014 | Wed Nov 11 17:00:00 IST 2015
258 | TT_TASK | Prepare TTMS report for removal of TBM S624 & S623 | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 15 17:00:00 IST 2014
259 | TT_TASK | Working Group Meeting & SLG Meeting | Fri Jan 16 07:00:00 IST 2015 | Wed Apr 15 17:00:00 IDT 2015
260 | TT_TASK | Drawings' approval and endosement from RDO | Mon Feb 23 07:00:00 IST 2015 | Mon Mar 09 17:00:00 IST 2015
261 | TT_TASK | Submit advance notice to the HK Police | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
262 | TT_TASK | On stie preparation works | Mon Jul 13 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
263 | TT_TASK | Proof drilling for water tightness test of jet grout block | Wed Jul 01 07:00:00 IDT 2015 | Tue Jul 07 17:00:00 IDT 2015
264 | TT_TASK | Shaft bottom slab levelling | Fri Jul 24 07:00:00 IDT 2015 | Sat Jul 25 17:00:00 IDT 2015
265 | TT_TASK | Moving device and cradle installation | Thu Jul 23 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
266 | None | S624 TBM Removal | Tue Sep 29 07:00:00 IDT 2015 | Sun Nov 08 17:00:00 IST 2015
267 | TT_TASK | Move TBM S624 front portion to cradle | Tue Oct 13 07:00:00 IDT 2015 | Sun Oct 18 17:00:00 IDT 2015
268 | TT_TASK | Weld additional bracing brackets corbels | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
269 | TT_TASK | Install cradle on lateral shifting system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
270 | TT_TASK | Move and shift TBM to dismantle location | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
271 | TT_TASK | Dismantle Cutter Head & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
272 | TT_TASK | Dismantle TBM front sheild & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
273 | TT_TASK | Dismantle segment installation machine & Remove | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
274 | TT_TASK | Dismantle TBM middle sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
275 | TT_TASK | Dismantle TBM rear sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
276 | TT_TASK | Dismantle S624 Link Bridge & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
277 | TT_TASK | Dismantle S624 Wagon #1 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
278 | TT_TASK | Dismantle S624 Wagon #2 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
279 | TT_TASK | Dismantle S624 Wagon #3 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
280 | TT_TASK | Dismantle S624 Wagon #4 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
281 | TT_TASK | Dismantle S624 Wagon #5 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
282 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N1 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
283 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N2 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
284 | None | Cross Passages (HK) | Wed Oct 01 07:00:00 IDT 2014 | Thu Aug 04 17:00:00 IDT 2016
285 | None | Freezing Station A | Sat Oct 11 07:00:00 IDT 2014 | Mon Nov 09 17:00:00 IST 2015
286 | TT_TASK | Erect Freezing Station Platform | Sat Oct 11 07:00:00 IDT 2014 | Tue Oct 21 17:00:00 IDT 2014
287 | TT_TASK | Freezing Station Installation & Testing | Thu Jan 01 07:00:00 IST 2015 | Sat Jan 31 17:00:00 IST 2015
288 | TT_TASK | Remove Freezing Station A | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
289 | None | Cross Passage #1. Ch.116+030 | Wed Oct 01 07:00:00 IDT 2014 | Tue May 10 17:00:00 IDT 2016
290 | TT_TASK | Erect Temporary Drilling Platform | Wed Oct 01 07:00:00 IDT 2014 | Fri Oct 10 17:00:00 IDT 2014
291 | TT_TASK | Drill & Install Freezing Pipe | Mon Dec 01 07:00:00 IST 2014 | Wed Jan 14 17:00:00 IST 2015
292 | TT_TASK | Install temporary support including ring support (Up-track) | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 15 17:00:00 IST 2015
293 | TT_TASK | Install temporary support including ring support (Down-track) | Mon Feb 23 07:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
294 | TT_TASK | Intall safe door | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 25 17:00:00 IDT 2015
295 | TT_TASK | Install freezing & monitoring system | Mon Feb 23 07:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
296 | TT_TASK | Conduct Ground Freezing | Sun Mar 01 07:00:00 IST 2015 | Tue Apr 14 17:00:00 IDT 2015
297 | TT_TASK | Maintain ground freezing during construction of CP | Tue Apr 21 07:00:00 IDT 2015 | Sun Jun 14 17:00:00 IDT 2015
298 | TT_TASK | Tunnel segment cutting & removal | Tue Apr 21 07:00:00 IDT 2015 | Wed Apr 22 17:00:00 IDT 2015
299 | TT_TASK | Excavate and temporary support | Tue Apr 21 07:00:00 IDT 2015 | Sat May 23 17:00:00 IDT 2015
300 | TT_TASK | Tunnel segment removal | Tue Aug 04 07:00:00 IDT 2015 | Mon Aug 10 17:00:00 IDT 2015
301 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Jul 03 07:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
302 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 08 17:00:00 IDT 2015
303 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
304 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
305 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
306 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
307 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
308 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
309 | TT_TASK | Remove formwork | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
310 | TT_TASK | Concrete achieved the design strength | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
311 | TT_TASK | Remove temporary works | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
312 | TT_TASK | Remove Freezing Plant | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
313 | TT_TASK | Thawing & Proof Grouting | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
314 | TT_TASK | Make Good Freezing Pipe Hole | Sun May 01 07:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
315 | None | Cross Passage #2. Ch.116+195 | Mon Feb 23 07:00:00 IST 2015 | Sun Apr 10 17:00:00 IDT 2016
316 | TT_TASK | Erect Temporary Drilling Platform | Mon Feb 23 07:00:00 IST 2015 | Wed Feb 25 17:00:00 IST 2015
317 | TT_TASK | Drill & Install Freezing Pipe | Mon Feb 23 07:00:00 IST 2015 | Fri Apr 10 17:00:00 IDT 2015
318 | TT_TASK | Install temporary support (including ring support) | Tue Apr 21 07:00:00 IDT 2015 | Tue May 05 17:00:00 IDT 2015
319 | TT_TASK | Install safe door | Mon Jun 01 07:00:00 IDT 2015 | Thu Jun 04 17:00:00 IDT 2015
320 | TT_TASK | Install freezing & monitoring system | Tue Apr 21 07:00:00 IDT 2015 | Thu Apr 23 17:00:00 IDT 2015
321 | TT_TASK | Conduct Ground Freezing | Tue Apr 21 07:00:00 IDT 2015 | Tue Jun 16 17:00:00 IDT 2015
322 | TT_TASK | Maintain ground freezing during construction of CP | Fri Jul 24 07:00:00 IDT 2015 | Mon Sep 21 17:00:00 IDT 2015
323 | TT_TASK | Tunnel segment cutting & removal | Fri Jul 24 07:00:00 IDT 2015 | Thu Jul 30 17:00:00 IDT 2015
324 | TT_TASK | Excavate and temporary support | Sun Jul 26 07:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
325 | TT_TASK | Tunnel segment removal | Mon Aug 03 07:00:00 IDT 2015 | Tue Aug 04 17:00:00 IDT 2015
326 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
327 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
328 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
329 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
330 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
331 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
332 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
333 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
334 | TT_TASK | Remove formwork | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
335 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
336 | TT_TASK | Remove temporary works | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
337 | TT_TASK | Remove Freezing Pipes | Sat Nov 14 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
338 | TT_TASK | Thawing & Proof Grouting | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
339 | TT_TASK | Make Good Freezing Pipe Holes | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
340 | None | Freezing Station B | Mon Jun 01 07:00:00 IDT 2015 | Thu Aug 04 17:00:00 IDT 2016
341 | TT_TASK | Erect Freezing Station Platform | Mon Jun 01 07:00:00 IDT 2015 | Sat Jun 20 17:00:00 IDT 2015
342 | TT_TASK | Freezing Station Installation & Testing | Sun Jun 21 07:00:00 IDT 2015 | Fri Jul 10 17:00:00 IDT 2015
343 | TT_TASK | Remove Station B | Fri Jul 22 07:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016
344 | None | Cross Passage #3. Ch. 116+445 | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
345 | TT_TASK | Erect Temporary Drilling Platform | Tue Apr 21 07:00:00 IDT 2015 | Sun Apr 26 17:00:00 IDT 2015
346 | TT_TASK | Drill & Install Freezing Pipe | Tue Apr 21 07:00:00 IDT 2015 | Fri Jun 05 17:00:00 IDT 2015
347 | TT_TASK | Install temporary support (including ring support) | Sun Jul 19 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
348 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
349 | TT_TASK | Install freezing & monitoring system | Wed Jul 01 07:00:00 IDT 2015 | Fri Jul 03 17:00:00 IDT 2015
350 | TT_TASK | Conduct Ground Freezing | Sat Jul 04 07:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
351 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Sep 29 07:00:00 IDT 2015 | Fri Dec 18 17:00:00 IST 2015
352 | TT_TASK | Tunnel segment cutting & removal at U/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
353 | TT_TASK | Excavate and temporary support | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 31 17:00:00 IST 2015
354 | TT_TASK | Tunnel segment removal at D/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
355 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
356 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
357 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
358 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
359 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 12 17:00:00 IST 2015
360 | TT_TASK | Lining concreting (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
361 | TT_TASK | Lining concrete curing (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
362 | TT_TASK | Make Good Freezing Pipe Hole | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
363 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
364 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
365 | TT_TASK | Remove temp. works, ring support and temp. platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
366 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
367 | None | Cross Passage #4. Ch. 116+671 | Mon Jul 06 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
368 | TT_TASK | Erect Temporary Drilling Platform | Sun Jul 19 07:00:00 IDT 2015 | Thu Jul 23 17:00:00 IDT 2015
369 | TT_TASK | Drill & Install Freezing Pipe | Mon Jul 06 07:00:00 IDT 2015 | Thu Aug 20 17:00:00 IDT 2015
370 | TT_TASK | Install temporary support (including ring support) | Tue Sep 29 07:00:00 IDT 2015 | Tue Oct 13 17:00:00 IDT 2015
371 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
372 | TT_TASK | Install freezing & monitoring system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
373 | TT_TASK | Conduct Ground Freezing | Tue Sep 29 07:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
374 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Thu Nov 05 07:00:00 IST 2015 | Fri Feb 19 17:00:00 IST 2016
375 | TT_TASK | Tunnel segment cutting & removal at U/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
376 | TT_TASK | Excavate and temporary support | Mon Nov 09 07:00:00 IST 2015 | Wed Nov 25 17:00:00 IST 2015
377 | TT_TASK | Earthing, Waterproof works and waterproof test | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
378 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
379 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
380 | TT_TASK | Lining concrete curing (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
381 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
382 | TT_TASK | Lining concreting (side walls and roof) | Tue Nov 10 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
383 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
384 | TT_TASK | Remove formwork | Fri Apr 08 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
385 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
386 | TT_TASK | Remove temp. works and ring support | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
387 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
388 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
389 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
390 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Sat Nov 07 17:00:00 IST 2015
391 | TT_TASK | Erect temp. working platform | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
392 | TT_TASK | Drilling remaining holes at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
393 | TT_TASK | Install ring support at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
394 | TT_TASK | Tunnel segment removal at D/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
395 | None | Cross Passage #5. Ch. 116+966 | Wed Jul 01 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
396 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+066); last gantry passed CP5 | Wed Jul 01 07:00:00 IDT 2015 | Wed Jul 01 07:00:00 IDT 2015
397 | TT_TASK | Erect Temporary Drilling Platform at U/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
398 | START_MILESTONE | TBM S623 C/W exited Alluvial zone at S1425/Ch. 116+927 (* Note1) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
399 | TT_TASK | TBM S623 C/W boring from Ch. 116+927 to Ch. 116+986 (CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
400 | TT_TASK | Drill & Install Freezing Pipe at U/T | Sat Oct 10 07:00:00 IDT 2015 | Tue Nov 24 17:00:00 IST 2015
401 | TT_TASK | Raise track rail, slurry pipes diversion, install temp. support at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
402 | TT_TASK | Install Ring Support | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
403 | TT_TASK | Install freezing & monitoring system | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
404 | TT_TASK | Freezing system Test & Commissioning | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
405 | TT_TASK | Conduct Ground Freezing (Active phase) | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
406 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Dec 01 07:00:00 IST 2015 | Sun Mar 20 17:00:00 IST 2016
407 | TT_TASK | Install safe door (both sides) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
408 | TT_TASK | Tunnel segment cutting & removal at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
409 | TT_TASK | Excavate and temporary support (excavation from D/T) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
410 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
411 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
412 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
413 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
414 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
415 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
416 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
417 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
418 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
419 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
420 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
421 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
422 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
423 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Fri Nov 27 17:00:00 IST 2015
424 | TT_TASK | TBM S623 C/W boring from Ch.. 116+986 to Ch117+086 (last gantry passed CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 16 17:00:00 IDT 2015
425 | TT_TASK | Erect Temporary Drilling Platorm at D/T | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
426 | TT_TASK | Drilling remaining holes at D/T after S623 gantries passed | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 27 17:00:00 IST 2015
427 | TT_TASK | Install ring support at D/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
428 | None | Cross Passage #6. Ch. 117+216 | Sat Aug 01 07:00:00 IDT 2015 | Wed Jun 15 17:00:00 IDT 2016
429 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Sat Aug 01 07:00:00 IDT 2015 | Sat Aug 01 07:00:00 IDT 2015
430 | TT_TASK | Erect Drilling Platform at U/T | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
431 | TT_TASK | Drill ground freezing holes at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
432 | TT_TASK | Install Ring Support at U/T | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
433 | TT_TASK | Install freezing & monitoring system at U/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
434 | TT_TASK | Freezing system Test & Commissioning at U/T, Station B | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
435 | TT_TASK | Conduct Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Thu May 19 17:00:00 IDT 2016
436 | LEVEL_OF_EFFORT | Maintain Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Wed Jun 15 17:00:00 IDT 2016
437 | TT_TASK | Install safe door (both sides) | Sun Apr 10 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
438 | TT_TASK | Tunnel segment removal | Sat Apr 16 07:00:00 IDT 2016 | Wed Apr 20 17:00:00 IDT 2016
439 | TT_TASK | Excavate and temporary support (excavation from U/T side only) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
440 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
441 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
442 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
443 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
444 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
445 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
446 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
447 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
448 | TT_TASK | Remove formwork & Remove safe doors | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
449 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
450 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
451 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
452 | TT_TASK | Make Good Freezing Pipe Hole | Mon Apr 11 07:00:00 IDT 2016 | Thu Apr 14 17:00:00 IDT 2016
453 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Mon Apr 11 17:00:00 IDT 2016
454 | START_MILESTONE | S623 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
455 | TT_TASK | Erect Working Platform at D/T | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
456 | TT_TASK | Drill ground freezing holes at D/T | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
457 | TT_TASK | Install freezing & monitoring system at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
458 | TT_TASK | Ring support installation at D/T | Wed Apr 06 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
459 | None | Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
460 | None | Down Track Tunnel Finishes | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
461 | None | Tunnel Invert Slab (DT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 30 17:00:00 IDT 2016
462 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m-64=25m) | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
463 | TT_TASK | Invert Slab at CP1 (30m) | Sun May 29 07:00:00 IDT 2016 | Mon May 30 17:00:00 IDT 2016
464 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) | Sat May 21 07:00:00 IDT 2016 | Sat May 28 17:00:00 IDT 2016
465 | TT_TASK | Invert Slab at CP2 (30m) | Sat May 21 07:00:00 IDT 2016 | Sun May 22 17:00:00 IDT 2016
466 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Sun May 08 07:00:00 IDT 2016 | Fri May 20 17:00:00 IDT 2016
467 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
468 | TT_TASK | Invert Slab between CP3 and CP4 (226-45=181m) | Fri Apr 29 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
469 | TT_TASK | Invert Slab at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
470 | TT_TASK | Invert Slab between CP4 and CP5 (296-59=237m) | Thu Apr 14 07:00:00 IDT 2016 | Thu Apr 28 17:00:00 IDT 2016
471 | TT_TASK | Invert Slab at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
472 | TT_TASK | Invert Slab between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
473 | TT_TASK | Invert Slab at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
474 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (14m) | Thu Apr 07 07:00:00 IDT 2016 | Fri Apr 08 17:00:00 IDT 2016
475 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Thu Apr 07 07:00:00 IDT 2016 | Sat Apr 16 17:00:00 IDT 2016
476 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
477 | None | Lower Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
478 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
479 | TT_TASK | Lower Wkys at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
480 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
481 | TT_TASK | Lower Wks at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
482 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
483 | TT_TASK | Lower Wkys at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
484 | TT_TASK | Lower Wkys between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
485 | TT_TASK | Lower Wkys at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
486 | TT_TASK | Lower Wkys between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
487 | TT_TASK | Lower Wkys at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
488 | TT_TASK | Lower Wkys between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
489 | TT_TASK | Lower Wkys at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
490 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
491 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
492 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
493 | None | Upper Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
494 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
495 | TT_TASK | Upper Wky at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
496 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
497 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
498 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
499 | TT_TASK | Upper Wky at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
500 | TT_TASK | Upper Wky between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
501 | TT_TASK | Upper Wky at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
502 | TT_TASK | Upper Wky between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
503 | TT_TASK | Upper Wky at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
504 | TT_TASK | Upper Wky between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
505 | TT_TASK | Upper Wky at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
506 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
507 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
508 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
509 | None | DT Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Sat Dec 24 17:00:00 IST 2016
510 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
511 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
512 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
513 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
514 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
515 | None | Double Gates (DT) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
516 | TT_TASK | Install double gates at 20m south of CP6 | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
517 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
518 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
519 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
520 | None | Up Track Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 22 17:00:00 IST 2016
521 | None | Tunnel Invert Slab (UT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 02 17:00:00 IDT 2016
522 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m) | Tue Apr 26 07:00:00 IDT 2016 | Sun May 01 17:00:00 IDT 2016
523 | TT_TASK | Invert Slab at CP1 (30m) | Tue Apr 26 07:00:00 IDT 2016 | Wed Apr 27 17:00:00 IDT 2016
524 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) incl. Station A area | Mon Apr 18 07:00:00 IDT 2016 | Mon Apr 25 17:00:00 IDT 2016
525 | TT_TASK | Invert Slab at CP2 (30m) | Mon Apr 18 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
526 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Tue Apr 05 07:00:00 IDT 2016 | Sun Apr 17 17:00:00 IDT 2016
527 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
528 | TT_TASK | Invert Slab between CP3 and CP4 (226-47-34=145m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
529 | TT_TASK | Invert Slab at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
530 | TT_TASK | Invert Slab at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
531 | TT_TASK | Invert Slab between CP4 and CP5 (296-51=245m) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
532 | TT_TASK | Invert Slab at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
533 | TT_TASK | Invert Slab between CP5 and CP6 (250-32=218m) | Sat Dec 19 07:00:00 IST 2015 | Thu Dec 31 17:00:00 IST 2015
534 | TT_TASK | Invert Slab at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
535 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (20m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
536 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
537 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
538 | None | Lower Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
539 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
540 | TT_TASK | Lower Wkys at CP1 (30m) | Mon May 16 07:00:00 IDT 2016 | Tue May 17 17:00:00 IDT 2016
541 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
542 | TT_TASK | Lower Wkys at CP2 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
543 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
544 | TT_TASK | Lower Wkys at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
545 | TT_TASK | Lower Wkys between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
546 | TT_TASK | Lower Wkys at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
547 | TT_TASK | Lower Wkys at CP4 (64m) | Sat Apr 16 07:00:00 IDT 2016 | Mon Apr 18 17:00:00 IDT 2016
548 | TT_TASK | Lower Wkys between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
549 | TT_TASK | Lower Wkys at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
550 | TT_TASK | Lower Wkys between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
551 | TT_TASK | Lower Wkys at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
552 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
553 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
554 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
555 | None | Upper Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
556 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
557 | TT_TASK | Upper Wky at CP1 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
558 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
559 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
560 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
561 | TT_TASK | Upper Wky at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
562 | TT_TASK | Upper Wky between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
563 | TT_TASK | Upper Wky at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
564 | TT_TASK | Upper Wky at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
565 | TT_TASK | Upper Wky between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
566 | TT_TASK | Upper Wky at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
567 | TT_TASK | Upper Wky between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
568 | TT_TASK | Upper Wky at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
569 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
570 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
571 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
572 | None | Up Track Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Thu Dec 22 17:00:00 IST 2016
573 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
574 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
575 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Thu Dec 22 17:00:00 IST 2016
576 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
577 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
578 | None | UT Double Gates | Thu Nov 05 07:00:00 IST 2015 | Wed Apr 06 17:00:00 IDT 2016
579 | TT_TASK | Install double gates at 20m south of CP6 | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
580 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Wed Nov 11 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
581 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
582 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
583 | None | Tunnel Finishes to Completion | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
584 | None | Down Track | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
585 | TT_TASK | Operation and maintenance of temporary services | Fri Apr 08 07:00:00 IDT 2016 | Sun Mar 05 17:00:00 IST 2017
586 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
587 | None | Up Track | Wed Jun 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
588 | TT_TASK | Operation and maintenance of temporary services | Wed Jun 01 07:00:00 IDT 2016 | Thu Oct 06 17:00:00 IDT 2016
589 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
590 | None | Commissioning, Inspections and Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
591 | RESOURCE_DEPENDENT | Site Cleaning, Inspection for Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
592 | FINISH_MILESTONE | Submit draft as-built drawings (Z8.2) and draft O&M Manuals | Sat Dec 24 17:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
593 | FINISH_MILESTONE | Submit approved Design Data (Z8.4) | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
594 | FINISH_MILESTONE | Submit final as-built drawings and O&M Manuals | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
595 | TT_TASK | Inspect & Certify completion of whole works | Sat Mar 25 07:00:00 IDT 2017 | Fri Mar 31 17:00:00 IDT 2017
596 | None | Contract Preliminaries | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
597 | None | Designs and Submissions | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
598 | None | Principle Method Statements, Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
599 | None | Management Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Sun Oct 30 08:00:00 IST 2011
600 | TT_TASK | Submit System Assurance Plan (App P, P3.1) | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
601 | TT_TASK | Engineer's review on System Assurance Plan | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
602 | TT_TASK | Submit Health and Safety Plan (G3.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
603 | TT_TASK | Engineer's review on Health and Safety Plan | Wed May 05 08:00:00 IDT 2010 | Wed Jun 02 08:00:00 IDT 2010
604 | TT_TASK | Submit Quality Assurance Plan (G9.2.1) | Thu Apr 15 08:00:00 IDT 2010 | Thu May 13 08:00:00 IDT 2010
605 | TT_TASK | Engineer's review on Quality Assurance Plan | Wed May 12 08:00:00 IDT 2010 | Wed Jun 09 08:00:00 IDT 2010
606 | TT_TASK | Submit Prelimiary Master Programme (G4.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
607 | TT_TASK | Engineer's review on Prelimiary Master Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
608 | TT_TASK | Submit first Three-Month Rolling Programme (G4.8 | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 29 08:00:00 IDT 2010
609 | TT_TASK | Engineer's review on first Three-Month Rolling P | Fri Apr 02 08:00:00 IDT 2010 | Fri Apr 30 08:00:00 IDT 2010
610 | TT_TASK | Submit Time-chainage Programme (G4.11.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
611 | TT_TASK | Engineer's review on Time-chainage Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
612 | TT_TASK | Submit Design Schedule (App Z) | Mon May 03 08:00:00 IDT 2010 | Mon May 17 08:00:00 IDT 2010
613 | TT_TASK | Engineer's review on Design Schedule | Fri May 28 08:00:00 IDT 2010 | Fri Jun 25 08:00:00 IDT 2010
614 | TT_TASK | Submit Subcontractor Management Plan (App S) | Sat May 15 08:00:00 IDT 2010 | Mon Jun 14 08:00:00 IDT 2010
615 | TT_TASK | Engineer's review on Subcontractor Management Pl | Tue Jun 15 08:00:00 IDT 2010 | Tue Jul 13 08:00:00 IDT 2010
616 | TT_TASK | Submit Groundwater Monitoring and Emergency Resp | Thu Apr 22 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
617 | TT_TASK | Engineer's review on Groundwater Monitoring and | Fri Jun 04 08:00:00 IDT 2010 | Fri Jul 02 08:00:00 IDT 2010
618 | TT_TASK | Submit Water Pollution Control Measures and Moni | Thu Apr 15 08:00:00 IDT 2010 | Sun May 30 08:00:00 IDT 2010
619 | TT_TASK | Engineer's review on Water Pollution Control Mea | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
620 | TT_TASK | Submit Waste Management Plan (P22.8.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
621 | TT_TASK | Engineer's review on Waste Management Plan | Tue May 18 08:00:00 IDT 2010 | Tue Jun 15 08:00:00 IDT 2010
622 | TT_TASK | Submit the Plan for the Design for Safety and Co | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
623 | TT_TASK | Engineer's review on Plan for the Design for Saf | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
624 | TT_TASK | Submit Air Quality Management Plan (P22.4.4) | Fri Apr 09 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
625 | TT_TASK | Engineer's review on Air Quality Management Plan | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
626 | TT_TASK | Submit TBM manufacturiing and delivery programme | Sat May 22 08:00:00 IDT 2010 | Sat Jun 19 08:00:00 IDT 2010
627 | TT_TASK | Engineer's review on TBM manufacturiing and deli | Wed Jun 02 08:00:00 IDT 2010 | Wed Jun 30 08:00:00 IDT 2010
628 | TT_TASK | Submit Environmental Management Plan (G5.1.10) | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
629 | TT_TASK | Engineer's review on Environmental Management Pl | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
630 | TT_TASK | Submit interfacing documentation for System-wide | Mon Aug 01 08:00:00 IDT 2011 | Sun Oct 30 08:00:00 IST 2011
631 | TT_TASK | Engineer's review on interfacing documentation f | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
632 | None | Method Statements | Fri Apr 09 08:00:00 IDT 2010 | Wed Jun 17 17:00:00 IDT 2015
633 | TT_TASK | Submit Geotechnical Instruments installation | Fri Jun 18 08:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010
634 | TT_TASK | Engineer's review on Geotechnical Instruments installation | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
635 | TT_TASK | Submit Survey control network | Fri Apr 09 08:00:00 IDT 2010 | Mon May 24 08:00:00 IDT 2010
636 | TT_TASK | Engineer's review on Survey control network | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
637 | TT_TASK | Submit MS for surveying and survey control for tunnelling works | Mon Jun 14 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
638 | TT_TASK | Engineer's review on MS for surveying and survey control for tunnelling works | Sat Aug 07 08:00:00 IDT 2010 | Sat Sep 04 08:00:00 IDT 2010
639 | TT_TASK | Submit a Ground Treatment Works spoil disposal plan | Tue Jun 08 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
640 | TT_TASK | Engineer's review on Ground Treatment Works spoil disposal plan | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
641 | TT_TASK | Submit MS for ground treatment | Sun May 09 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
642 | TT_TASK | Engineer's review on MS for ground treatment | Fri Jun 25 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
643 | TT_TASK | Submit TBM MS for transportation and erection of the TBMs (X.17.1.1) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
644 | TT_TASK | Engineer's review on TBM MS for transportation and erection of the TBMs | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
645 | TT_TASK | Submit TBM MS for operation of the TBM (X17.1.3) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
646 | TT_TASK | Engineer's review on TBM MS for operation of the TBM | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
647 | TT_TASK | Submit MS for instrumentation and monitoring works in Ramsar & WPC areas | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 29 08:00:00 IDT 2011
648 | TT_TASK | Engineer's review on MS for instrumentation and monitoring works in Ramsar & WPC | Tue Mar 08 08:00:00 IST 2011 | Tue Apr 05 08:00:00 IDT 2011
649 | TT_TASK | Submit TBM MS for determining ground conditions ahead of the face (X17.1.5) (CS569) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
650 | TT_TASK | Engineer's review on TBM MS for determining ground conditions ahead of the face | Fri Apr 17 07:00:00 IDT 2015 | Thu May 14 17:00:00 IDT 2015
651 | TT_TASK | Submit MS for cross passage construction | Mon Jul 04 08:00:00 IDT 2011 | Mon Aug 01 08:00:00 IDT 2011
652 | TT_TASK | Engineer's review on MS for cross passage construction | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 26 08:00:00 IDT 2011
653 | TT_TASK | Submit TBM MS for commencing the initial drives (X17.1.2) (CS80) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
654 | TT_TASK | Engineer's review on TBM MS for commencing the initial drives | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
655 | TT_TASK | Submit TBM MS for setting out and controlling the tunnel alignment (Survey MS CS21) | Tue May 11 07:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
656 | TT_TASK | Engineer's review on TBM MS for setting out & contolling the tunnel alignment | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
657 | TT_TASK | Submit TBM MS for monitoring ground loss and settlement monitoring (X17.1.6) (CS36) | Tue Nov 30 07:00:00 IST 2010 | Tue Nov 30 07:00:00 IST 2010
658 | TT_TASK | Engineer's review on TBM MS for monitoring ground loss & settlement monitoring | Wed Aug 11 07:00:00 IDT 2010 | Wed Aug 11 07:00:00 IDT 2010
659 | TT_TASK | Submit TBM MS for hyperbaric interventions (X17.1.7) (CS520) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
660 | TT_TASK | Engineer's review on TBM MS for hyperbaric interventions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
661 | TT_TASK | Submit MS for the identification and removal of obstructions (P11.11) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
662 | TT_TASK | Engineer's review on MS for the identification & removal of obstructions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
663 | TT_TASK | Submit TBM MS for tunnelling under sensitive structures (X17.1.10) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
664 | TT_TASK | Engineer's review on TBM MS for tunnelling under sensitive structures | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
665 | TT_TASK | Submit TBM MS for TBM dismantling (X17.1.9) (CS652) | Fri Feb 20 07:00:00 IST 2015 | Wed May 20 17:00:00 IDT 2015
666 | TT_TASK | Engineer's review on TBM MS for TBM dismantling | Thu May 21 07:00:00 IDT 2015 | Wed Jun 17 17:00:00 IDT 2015
667 | TT_TASK | Submit TBM MS for junctions with shafts (X17.1.8) (CS246) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
668 | TT_TASK | Engineer's review on TBM MS for junctions with shafts | Thu Jun 23 07:00:00 IDT 2011 | Wed Jul 20 17:00:00 IDT 2011
669 | TT_TASK | Submit MS for ground freezing works (CS686) | Mon Dec 12 08:00:00 IST 2011 | Fri Feb 10 08:00:00 IST 2012
670 | TT_TASK | Engineer's review on MS for ground freezing work | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 16 08:00:00 IDT 2012
671 | TT_TASK | Submit MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 01 08:00:00 IST 2014
672 | TT_TASK | Engineer's review on MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
673 | TT_TASK | Submit Methods of Construction | Thu May 27 08:00:00 IDT 2010 | Thu Jun 17 08:00:00 IDT 2010
674 | TT_TASK | Engineer's review on Methods of Construction | Fri Jun 18 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
675 | TT_TASK | Submit TBM Spoil Disposal Plan (HK) | Wed Jun 23 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
676 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
677 | TT_TASK | Submit TBM Spoil Disposal Plan (SZ) | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 21 08:00:00 IST 2013
678 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 23 08:00:00 IST 2014
679 | None | Submissions to Government Departments | Sat May 29 08:00:00 IDT 2010 | Tue Jun 03 09:00:00 IDT 2014
680 | TT_TASK | Apply for the initial batch of Frontier Closed Area Permits | Sat May 29 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
681 | TT_TASK | Submit Emergency Rescue proposals and procedures | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
682 | TT_TASK | Engineer's review on Emergency Rescue proposals and procedures | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 28 08:00:00 IST 2013
683 | TT_TASK | Application and obtain approval of Construction Noise Permits | Fri Apr 04 09:00:00 IDT 2014 | Tue Jun 03 09:00:00 IDT 2014
684 | None | Temporary Works Design Submissions | Thu Apr 22 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
685 | TT_TASK | Submit site logistics plans (initial layout) | Thu Apr 22 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
686 | TT_TASK | Engineer's review on site logistics plans (initial layout) | Fri Jul 23 08:00:00 IDT 2010 | Fri Aug 20 08:00:00 IDT 2010
687 | TT_TASK | Submit designs for the Engineer's Office | Mon Jul 12 08:00:00 IDT 2010 | Fri Sep 10 08:00:00 IDT 2010
688 | TT_TASK | Engineer's review on designs for the Engineer's | Mon Aug 23 08:00:00 IDT 2010 | Mon Sep 20 08:00:00 IST 2010
689 | TT_TASK | Submit temporary ventilation system design | Mon Aug 01 08:00:00 IDT 2011 | Fri Sep 30 08:00:00 IDT 2011
690 | TT_TASK | Engineer's review on temporary ventilation syste | Sat Aug 20 08:00:00 IDT 2011 | Sat Sep 17 08:00:00 IDT 2011
691 | None | Design of Permanent Works | Tue Jun 01 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
692 | None | Tunnel Permanent Lining | Tue Jun 01 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
693 | TT_TASK | Submission preparation & ICE checking | Tue Jun 01 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
694 | TT_TASK | Engineer's review | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
695 | TT_TASK | Re-submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Tue Aug 31 08:00:00 IDT 2010
696 | TT_TASK | Engineer's review | Wed Aug 04 08:00:00 IDT 2010 | Wed Sep 01 08:00:00 IDT 2010
697 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
698 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
699 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
700 | None | Permanent Tunnel Lining of Cross Passages | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
701 | None | AIP Submission | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
702 | TT_TASK | Submission preparation | Mon Jun 28 08:00:00 IDT 2010 | Sat Aug 07 08:00:00 IDT 2010
703 | TT_TASK | Engineer's review | Sat Aug 14 08:00:00 IDT 2010 | Sat Sep 11 08:00:00 IDT 2010
704 | TT_TASK | Re-submission preparation | Fri Aug 03 08:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012
705 | TT_TASK | Engineer's review | Mon Sep 03 08:00:00 IDT 2012 | Mon Oct 01 08:00:00 IST 2012
706 | None | Connection between Bored Tunnel and Retrival Shaft | Mon Aug 16 08:00:00 IDT 2010 | Tue Jul 01 08:00:00 IDT 2014
707 | TT_TASK | Submission preparation & ICE checking | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 25 08:00:00 IST 2010
708 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
709 | TT_TASK | Re-submission preparation & ICE checking | Sat Oct 23 08:00:00 IST 2010 | Sun Nov 28 08:00:00 IST 2010
710 | TT_TASK | Engineer's review | Sat Oct 06 08:00:00 IST 2012 | Sat Nov 03 08:00:00 IST 2012
711 | TT_TASK | Submission for RDO/BD consultation | Sun Feb 10 08:00:00 IST 2013 | Sun Mar 10 08:00:00 IST 2013
712 | TT_TASK | Re-submission for RDO/BD consultation | Tue Dec 17 08:00:00 IST 2013 | Tue Jan 14 08:00:00 IST 2014
713 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
714 | None | Junction between Main Tunnel and Cross Passages | Mon Oct 04 08:00:00 IST 2010 | Sun Sep 07 08:00:00 IDT 2014
715 | TT_TASK | Submission preparation & ICE checking | Mon Oct 04 08:00:00 IST 2010 | Tue Nov 23 08:00:00 IST 2010
716 | TT_TASK | Engineer's review | Thu Feb 07 08:00:00 IST 2013 | Thu Mar 07 08:00:00 IST 2013
717 | TT_TASK | Submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
718 | TT_TASK | Re-submission preparation & ICE checking | Tue Jul 01 08:00:00 IDT 2014 | Sun Aug 10 08:00:00 IDT 2014
719 | TT_TASK | Engineer's review | Sun Aug 10 08:00:00 IDT 2014 | Sun Sep 07 08:00:00 IDT 2014
720 | TT_TASK | Re-submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
721 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
722 | None | Design of Temporary Works | Sat May 01 08:00:00 IDT 2010 | Fri Aug 29 08:00:00 IDT 2014
723 | None | Ground Treatment Works for TBM Break-in | Sat May 01 08:00:00 IDT 2010 | Tue Nov 02 08:00:00 IST 2010
724 | TT_TASK | Submission preparation & ICE checking | Sat May 01 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
725 | TT_TASK | Engineer's review | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 12 08:00:00 IDT 2010
726 | TT_TASK | Re-submission preparation & ICE checking | Wed Jun 30 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
727 | TT_TASK | Engineer's review | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
728 | TT_TASK | Submission for RDO/BD consultation | Tue Aug 31 08:00:00 IDT 2010 | Tue Sep 28 08:00:00 IST 2010
729 | TT_TASK | Re-submission for RDO/BD consultation | Tue Oct 05 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
730 | START_MILESTONE | Construction drawings issuance | Tue Nov 02 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
731 | None | Geotechnical Assessment Report | Mon Jun 14 08:00:00 IDT 2010 | Mon Dec 26 08:00:00 IST 2011
732 | TT_TASK | Submission preparation & ICE checking | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010
733 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
734 | TT_TASK | Re-submission preparation & ICE checking | Thu Oct 21 08:00:00 IST 2010 | Fri Nov 05 08:00:00 IST 2010
735 | TT_TASK | Engineer's review | Fri Nov 05 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
736 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
737 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
738 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
739 | None | Groundwater Assessment Report | Mon Jul 26 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
740 | TT_TASK | Submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010
741 | TT_TASK | Engineer's review | Tue Sep 07 08:00:00 IDT 2010 | Tue Oct 05 08:00:00 IST 2010
742 | TT_TASK | Re-submission preparation & ICE checking | Wed Nov 03 08:00:00 IST 2010 | Sun Nov 21 08:00:00 IST 2010
743 | TT_TASK | Engineer's review | Tue Nov 23 08:00:00 IST 2010 | Tue Dec 21 08:00:00 IST 2010
744 | TT_TASK | Submission for RDO/BD consultation | Wed Oct 06 08:00:00 IST 2010 | Wed Nov 03 08:00:00 IST 2010
745 | TT_TASK | Re-submission for RDO/BD consultation | Sat Oct 23 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
746 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
747 | None | Ground Freezing and Temporary Support of Cross Passages | Sat Jan 01 08:00:00 IST 2011 | Fri Aug 29 08:00:00 IDT 2014
748 | TT_TASK | Submission preparation & ICE checking | Sat Jan 01 08:00:00 IST 2011 | Sat Mar 12 08:00:00 IST 2011
749 | TT_TASK | Engineer's review | Fri Nov 25 08:00:00 IST 2011 | Fri Dec 23 08:00:00 IST 2011
750 | TT_TASK | Re-submission preparation & ICE checking | Fri Feb 15 08:00:00 IST 2013 | Mon Apr 01 08:00:00 IDT 2013
751 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
752 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
753 | TT_TASK | Re-submission for RDO/BD consultation | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014
754 | START_MILESTONE | Construction drawings issuance | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014
755 | None | Bulk Head for TBM Removal | Mon May 31 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
756 | TT_TASK | Submission preparation & ICE checking | Mon May 31 08:00:00 IDT 2010 | Mon Aug 09 08:00:00 IDT 2010
757 | TT_TASK | Engineer's review | Fri Jul 30 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
758 | TT_TASK | Re-submission preparation & ICE checking | Thu Aug 12 08:00:00 IDT 2010 | Sun Sep 26 08:00:00 IST 2010
759 | TT_TASK | Engineer's review | Thu Sep 16 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
760 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
761 | None | Prediction of Ground Movement | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
762 | None | Report on the Prediction of Ground Movement and and Assessment on effect of EBS | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
763 | TT_TASK | Submission preparation & ICE checking | Mon Jul 12 08:00:00 IDT 2010 | Tue Aug 17 08:00:00 IDT 2010
764 | TT_TASK | Engineer's review | Sun Aug 22 08:00:00 IDT 2010 | Sun Sep 19 08:00:00 IST 2010
765 | TT_TASK | Re-submission preparation & ICE checking | Wed Sep 29 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
766 | TT_TASK | Engineer's review | Wed Oct 13 08:00:00 IST 2010 | Wed Nov 10 08:00:00 IST 2010
767 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
768 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
769 | START_MILESTONE | Construction drawings issuance | Tue Dec 27 08:00:00 IST 2011 | Tue Dec 27 08:00:00 IST 2011
770 | None | Instrumentation and Montoring Plans | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
771 | None | Instrumentation Plan | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
772 | TT_TASK | Submission preparation & ICE checking | Mon May 03 08:00:00 IDT 2010 | Fri May 28 08:00:00 IDT 2010
773 | TT_TASK | Engineer's review | Tue Jun 08 08:00:00 IDT 2010 | Tue Jul 06 08:00:00 IDT 2010
774 | TT_TASK | Re-submission preparation & ICE checking | Wed Jul 28 08:00:00 IDT 2010 | Sun Aug 15 08:00:00 IDT 2010
775 | TT_TASK | Engineer's review | Tue Aug 10 08:00:00 IDT 2010 | Tue Sep 07 08:00:00 IDT 2010
776 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
777 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
778 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
779 | None | Additional Ground Investigation Plans and Laboratory | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
780 | None | Further GI Plan and Lab Test Schedule | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
781 | TT_TASK | Submission preparation & ICE checking | Tue May 31 08:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011
782 | TT_TASK | Engineer's review | Thu Jul 14 08:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011
783 | TT_TASK | Re-submission preparation & ICE checking | Mon Oct 31 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
784 | TT_TASK | Engineer's review | Sat Nov 19 08:00:00 IST 2011 | Sat Dec 17 08:00:00 IST 2011
785 | TT_TASK | Submission for RDO/BD consultation | Sat Dec 17 08:00:00 IST 2011 | Sat Jan 14 08:00:00 IST 2012
786 | TT_TASK | Re-submission for RDO/BD consultation | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
787 | START_MILESTONE | Construction drawings issuance | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 08:00:00 IST 2013
788 | None | Procurement | Mon Mar 15 08:00:00 IST 2010 | Mon Sep 07 17:00:00 IDT 2015
789 | None | TBM Manufacture and Delivery | Mon Mar 15 08:00:00 IST 2010 | Thu Nov 01 08:00:00 IST 2012
790 | TT_TASK | Confirmation of purchase order on TBM manufacture | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
791 | FINISH_MILESTONE | Submit PO to the Engineer | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
792 | TT_TASK | Shop drawing preparation and submission | Thu Jul 15 08:00:00 IDT 2010 | Wed Aug 04 08:00:00 IDT 2010
793 | TT_TASK | Shop drawing review by the Engineer | Tue Aug 24 08:00:00 IDT 2010 | Tue Sep 21 08:00:00 IST 2010
794 | TT_TASK | Resubmission of shop drawings | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 25 08:00:00 IST 2010
795 | TT_TASK | Engineer's approval of shop drawings | Thu Nov 18 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
796 | TT_TASK | Shop drawings issued for manufacture | Thu Dec 16 08:00:00 IST 2010 | Fri Dec 31 08:00:00 IST 2010
797 | TT_TASK | Manufacturing & purchase parts for TBM #1 | Mon Aug 23 08:00:00 IDT 2010 | Mon Nov 01 08:00:00 IST 2010
798 | TT_TASK | TBM #1 factory preassembly and packing | Thu Oct 07 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
799 | TT_TASK | TBM #1 delivery to workshop | Fri Nov 19 08:00:00 IST 2010 | Sun Dec 19 08:00:00 IST 2010
800 | TT_TASK | TBM #1 workshop assembly | Fri Jan 07 08:00:00 IST 2011 | Fri Mar 18 08:00:00 IST 2011
801 | TT_TASK | TBM #1 test runs, acceptance, dis-assembly and p | Mon May 16 08:00:00 IDT 2011 | Wed Jun 15 08:00:00 IDT 2011
802 | TT_TASK | TBM #1 delivery to Shenzhen | Wed May 25 08:00:00 IDT 2011 | Sat Jun 04 08:00:00 IDT 2011
803 | FINISH_MILESTONE | TBM #1 delivery to HGP shaft | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
804 | TT_TASK | TBM #1 on-site assembly, T&C @ HGP Shaft | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
805 | TT_TASK | TBM #1 free walk-thru to commencement position | Fri Apr 27 08:00:00 IDT 2012 | Thu May 17 08:00:00 IDT 2012
806 | FINISH_MILESTONE | TBM #1 ready to commence drive at HGP by GSG Contractor | Wed Jul 04 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
807 | TT_TASK | Manufacturing & purchase parts for TBM #2 | Thu Dec 16 08:00:00 IST 2010 | Thu Feb 24 08:00:00 IST 2011
808 | TT_TASK | TBM #2 factory preassembly and packing | Mon Feb 14 08:00:00 IST 2011 | Mon Apr 25 08:00:00 IDT 2011
809 | TT_TASK | TBM #2 delivery to workshop | Sat Mar 05 08:00:00 IST 2011 | Mon Apr 04 08:00:00 IDT 2011
810 | TT_TASK | TBM #2 workshop assembly | Mon May 30 08:00:00 IDT 2011 | Mon Aug 08 08:00:00 IDT 2011
811 | TT_TASK | TBM #2 test runs, acceptance, dis-assembly and p | Mon Aug 22 08:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011
812 | TT_TASK | TBM #2 delivery to temporary storage at Nansha | Mon Sep 19 08:00:00 IDT 2011 | Thu Sep 22 08:00:00 IDT 2011
813 | TT_TASK | TBM #2 delivery to Shenzhen | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
814 | FINISH_MILESTONE | TBM #2 delivery to HGP shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
815 | TT_TASK | TBM #2 on-site assembly, T&C @ HGP Shaft | Thu Apr 05 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
816 | TT_TASK | TBM #2 free walk-thru to commencement position | Mon Oct 01 08:00:00 IST 2012 | Sun Oct 21 08:00:00 IST 2012
817 | FINISH_MILESTONE | TBM #2 ready to commence drive at HGP by GSG Con | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012
818 | None | TBM Ground Support Equipment | Thu Jul 08 08:00:00 IDT 2010 | Mon Nov 05 08:00:00 IST 2012
819 | TT_TASK | Confirm order for slurry treatment plant (STP) | Thu Jul 08 08:00:00 IDT 2010 | Thu Jul 15 08:00:00 IDT 2010
820 | TT_TASK | STP shop drawing preparation and submission | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010
821 | TT_TASK | STP shop drawing review by the Engineer | Wed Dec 01 08:00:00 IST 2010 | Wed Dec 29 08:00:00 IST 2010
822 | TT_TASK | STP procurement of components and materials | Thu Dec 09 08:00:00 IST 2010 | Sun Jan 23 08:00:00 IST 2011
823 | TT_TASK | STP resubmission of shop drawings | Mon Jan 10 08:00:00 IST 2011 | Mon Jan 24 08:00:00 IST 2011
824 | TT_TASK | STP Engineer's approval of shop drawings | Tue Apr 05 08:00:00 IDT 2011 | Tue May 03 08:00:00 IDT 2011
825 | TT_TASK | STP shop drawings issued for manufacture | Mon Mar 14 08:00:00 IST 2011 | Mon Mar 21 08:00:00 IST 2011
826 | TT_TASK | STP sub-unit assembly | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 08:00:00 IDT 2011
827 | TT_TASK | STP final assembly at factory | Wed Mar 23 08:00:00 IST 2011 | Sat Apr 02 08:00:00 IDT 2011
828 | TT_TASK | STP factory testing | Wed Mar 30 08:00:00 IST 2011 | Sat Apr 09 08:00:00 IDT 2011
829 | TT_TASK | STP packaging and transportation to docks | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 15 08:00:00 IDT 2011
830 | TT_TASK | STP shipping to Shenzhen, customs clearance and forwarding | Mon Apr 04 08:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011
831 | FINISH_MILESTONE | STP delivery to HGP works area | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 12 08:00:00 IDT 2011
832 | TT_TASK | STP on-site assembly | Wed Sep 28 08:00:00 IDT 2011 | Sat Oct 22 08:00:00 IST 2011
833 | TT_TASK | STP on-site self testing and commissioning | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 08:00:00 IST 2012
834 | TT_TASK | STP on-site testing and commissioning with TBM#1 | Mon Jun 18 08:00:00 IDT 2012 | Fri Jun 29 08:00:00 IDT 2012
835 | TT_TASK | STP on-site testing and commissioning with TBM#2 | Wed Oct 03 08:00:00 IST 2012 | Sun Oct 14 08:00:00 IST 2012
836 | FINISH_MILESTONE | STP ready to commence operations for TBM #1 | Mon Jun 18 08:00:00 IDT 2012 | Mon Jun 18 08:00:00 IDT 2012
837 | FINISH_MILESTONE | STP ready to commence operations for TBM #2 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
838 | None | Tunnel Lining Segments | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 07 17:00:00 IDT 2015
839 | START_MILESTONE | Confirmation of purchase order on segment manufacturer | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
840 | TT_TASK | Shop drawings issued for manufacture | Mon Aug 29 08:00:00 IDT 2011 | Sat Sep 10 08:00:00 IDT 2011
841 | TT_TASK | Pre-casting trials | Thu Nov 03 08:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011
842 | TT_TASK | Engineer's approval of trial segments | Thu Dec 15 08:00:00 IST 2011 | Thu Jan 12 08:00:00 IST 2012
843 | TT_TASK | Manufacture 926 Tunnel Rings (SZ) | Wed Feb 01 08:00:00 IST 2012 | Fri Jul 20 08:00:00 IDT 2012
844 | TT_TASK | Manufacture 163 Tunnel Rings (SZ) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 25 08:00:00 IST 2012
845 | TT_TASK | Manufacture 105 Tunnel Rings (SZ) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012
846 | TT_TASK | Manufacture 98 Tunnel Rings (SZ) | Wed Oct 31 08:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012
847 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 26 08:00:00 IST 2012
848 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sun Jan 13 08:00:00 IST 2013 | Thu Feb 07 08:00:00 IST 2013
849 | TT_TASK | Manufacture 60 Tunnel Rings (SZ) | Sun Feb 24 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013
850 | TT_TASK | Manufacture 81 Tunnel Rings (HK) | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 08:00:00 IDT 2013
851 | TT_TASK | Manufacture 76 Tunnel Rings (HK) | Sun Jun 30 08:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013
852 | TT_TASK | Manufacture 75 Tunnel Rings (HK) | Mon Jul 01 08:00:00 IDT 2013 | Fri Jul 26 08:00:00 IDT 2013
853 | TT_TASK | Manufacture 88 Tunnel Rings (HK) | Thu Aug 01 08:00:00 IDT 2013 | Sun Aug 25 08:00:00 IDT 2013
854 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Sun Sep 01 08:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013
855 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Fri Jan 24 08:00:00 IST 2014
856 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
857 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
858 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Jul 01 08:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014
859 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014
860 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
861 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Mon Feb 16 07:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
862 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Mar 03 07:00:00 IST 2015 | Fri Mar 27 17:00:00 IDT 2015
863 | TT_TASK | Manufacture 60 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Sat May 02 17:00:00 IDT 2015
864 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Fri May 15 17:00:00 IDT 2015
865 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Sun Aug 09 07:00:00 IDT 2015 | Wed Sep 02 17:00:00 IDT 2015
866 | TT_TASK | Manufacture 10 Tunnel Rings (HK) | Thu Sep 03 07:00:00 IDT 2015 | Mon Sep 07 17:00:00 IDT 2015
867 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (SZ rings) | Wed Aug 01 08:00:00 IDT 2012 | Wed Dec 26 08:00:00 IST 2012
868 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (HK rings) | Sat Nov 30 08:00:00 IST 2013 | Sun Oct 12 08:00:00 IDT 2014
869 | None | Segment Mould Design, Fabrication and Delivery | Mon May 16 08:00:00 IDT 2011 | Wed Feb 15 08:00:00 IST 2012
870 | START_MILESTONE | Confirm order for moulds | Mon May 16 08:00:00 IDT 2011 | Mon May 16 08:00:00 IDT 2011
871 | TT_TASK | Design and planning | Mon May 16 08:00:00 IDT 2011 | Thu Jun 09 08:00:00 IDT 2011
872 | TT_TASK | Design mould drawings for manufacture | Fri Jul 08 08:00:00 IDT 2011 | Sun Aug 07 08:00:00 IDT 2011
873 | TT_TASK | Materials procurement | Fri Jul 08 08:00:00 IDT 2011 | Thu Jul 28 08:00:00 IDT 2011
874 | TT_TASK | Factory assembly | Mon Jul 18 08:00:00 IDT 2011 | Fri Sep 16 08:00:00 IDT 2011
875 | TT_TASK | Shipping and delivery to Shenzhen - 1st batch (3 sets) | Sat Nov 05 08:00:00 IST 2011 | Thu Nov 10 08:00:00 IST 2011
876 | TT_TASK | Shipping and delivery to Shenzhen - 2nd batch (3 sets) | Fri Feb 10 08:00:00 IST 2012 | Wed Feb 15 08:00:00 IST 2012
877 | TT_TASK | Mould erection and commissioning ready for production in precast yard | Thu Nov 10 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
878 | None | Other Procurement Items | Tue Nov 02 08:00:00 IST 2010 | Sun Apr 06 08:00:00 IDT 2014
879 | TT_TASK | Transformer and substation procurement | Tue May 31 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
880 | TT_TASK | Procure temporary electrics subcontractor | Wed Jun 01 08:00:00 IDT 2011 | Fri Jul 01 08:00:00 IDT 2011
881 | TT_TASK | Place order for ready mixed concrete | Fri Mar 01 08:00:00 IST 2013 | Sat Apr 06 08:00:00 IDT 2013
882 | TT_TASK | Procure other major construction plant and equip | Tue Mar 01 08:00:00 IST 2011 | Mon May 30 08:00:00 IDT 2011
883 | TT_TASK | Place order for rebar supply | Mon Oct 31 08:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011
884 | TT_TASK | Rental agreement for off site office accommodation | Tue Nov 02 08:00:00 IST 2010 | Thu Dec 02 08:00:00 IST 2010
885 | TT_TASK | Procure tunnel personnel electronic tagging system | Sat Nov 30 08:00:00 IST 2013 | Sat Jan 11 08:00:00 IST 2014
886 | TT_TASK | Procure tunnel ventilation system | Thu Mar 01 08:00:00 IST 2012 | Tue Apr 10 08:00:00 IDT 2012
887 | TT_TASK | Procure ground freezing specialist subcontractor | Sat Mar 01 08:00:00 IST 2014 | Sun Apr 06 08:00:00 IDT 2014
888 | None | Site Mobilisation | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
889 | TT_TASK | Initial project staff assignments | Mon Mar 15 08:00:00 IST 2010 | Sun Jun 13 08:00:00 IDT 2010
890 | TT_TASK | Establish Works Areas at HGP | Wed Dec 01 08:00:00 IST 2010 | Tue Jan 18 08:00:00 IST 2011
891 | TT_TASK | Establish Works Areas at MPV | Fri Feb 01 08:00:00 IST 2013 | Sat Mar 09 08:00:00 IST 2013
892 | TT_TASK | Establish and operate Project Office in Hong Kong | Thu Apr 22 08:00:00 IDT 2010 | Fri Feb 18 08:00:00 IST 2011
893 | TT_TASK | Establish and operate Project Office in Shenzhen | Mon Jan 10 08:00:00 IST 2011 | Sat Oct 01 08:00:00 IDT 2016
894 | TT_TASK | Establish and operate Project Office in Mai Po | Tue Mar 15 08:00:00 IST 2011 | Fri Jul 25 08:00:00 IDT 2014
895 | START_MILESTONE | Commencement to operate compound at Mai Po, Area 1.19, for DLP | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
1 | None | 826 As-built Programme | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
2 | None | 826 - HGP to Mai Po Tunnels, Revised Master Prog | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
3 | None | Tender and Contract Details | Wed Mar 10 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
4 | None | Tender Actions | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
5 | START_MILESTONE | Contract Award (LoA) | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
6 | None | Critical Contract Dates | Mon Mar 15 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
7 | START_MILESTONE | Stated Contract Commencement Date (Cl 64) | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 15 08:00:00 IST 2010
8 | FINISH_MILESTONE | Table 3, Ref 3A - Delivery of the first TBM to HGP | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
9 | FINISH_MILESTONE | Table 3, Ref 3B - All works in Works Area 1.6 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
10 | FINISH_MILESTONE | Table 3, Ref 3C - Delivery of the second TBM to HGP | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
11 | FINISH_MILESTONE | Table 4, Ref 4A - Achieve Deg. 1 for both Up and Down Track Tunnels | Thu Mar 31 17:00:00 IDT 2016 | Thu Mar 31 17:00:00 IDT 2016
12 | FINISH_MILESTONE | Table 1 - Completion of the Whole of the Works (wk13/2015) | Thu Jun 01 17:00:00 IDT 2017 | Thu Jun 01 17:00:00 IDT 2017
13 | None | Other Programme Data | Thu May 09 08:00:00 IDT 2013 | Sat Apr 01 07:00:00 IDT 2017
14 | START_MILESTONE | GSG Contractor to hand over S623 to Cont' 826 at HK Boundary | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013
15 | START_MILESTONE | GSG Contractor to hand over S624 to Cont' 826 at HK Boundary | Thu May 09 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
16 | START_MILESTONE | Notification to Contract 846 for cable bracket installation | Sun Nov 22 07:00:00 IST 2015 | Sun Nov 22 07:00:00 IST 2015
17 | FINISH_MILESTONE | Provision of TBM Retrieval Shaft at MPV | Wed Oct 01 07:00:00 IDT 2014 | Wed Oct 01 07:00:00 IDT 2014
18 | START_MILESTONE | OHL Power On, by Designated Contractor 830 | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
19 | None | Access Dates for Designated Contractors | Sun May 01 07:00:00 IDT 2016 | Thu Dec 01 07:00:00 IST 2016
20 | START_MILESTONE | 827, X-passage Doors - Door Frame Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
21 | START_MILESTONE | 827, X-passage Doors - Doors Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
22 | START_MILESTONE | 830, Trackwork and OHL - Up-track | Sun May 01 07:00:00 IDT 2016 | Sun May 01 07:00:00 IDT 2016
23 | START_MILESTONE | 830, Trackwork and OHL - Down-track | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
24 | START_MILESTONE | 841A, Signalling System, Trackside Eqpt - Both tunnels | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
25 | START_MILESTONE | 846, Trackside Aux - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
26 | START_MILESTONE | 849, Radio Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
27 | START_MILESTONE | 850, Passenger Mobile Communications Systems - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
28 | START_MILESTONE | 851, Fixed Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
29 | START_MILESTONE | 8203, Constrn Stage Mobile Phone Network - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
30 | None | Interface Contractor Programme - GSG | Wed Dec 01 08:00:00 IST 2010 | Sat Mar 01 07:00:00 IST 2014
31 | FINISH_MILESTONE | Complete Huanggang Park shaft construction | Mon Mar 26 08:00:00 IST 2012 | Mon Mar 26 08:00:00 IST 2012
32 | TT_TASK | Drill & Blast Tunnel (to HK) | Wed Dec 01 08:00:00 IST 2010 | Tue Sep 27 08:00:00 IDT 2011
33 | TT_TASK | S623 Excavate 242m (SZ) (s.rock) | Tue Jul 03 08:00:00 IDT 2012 | Sat Oct 06 08:00:00 IST 2012
34 | TT_TASK | S623 Conduct General Maintenance | Sun Oct 07 08:00:00 IST 2012 | Wed Oct 10 08:00:00 IST 2012
35 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 484m) | Wed Oct 10 08:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012
36 | TT_TASK | S623 Conduct General Maintenance | Sun Nov 18 08:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012
37 | TT_TASK | S623 Excavate 220m (SZ) (s.rock/total 704m) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 29 08:00:00 IST 2012
38 | TT_TASK | S623 Conduct General Maintenance | Tue Jan 08 08:00:00 IST 2013 | Sat Jan 12 08:00:00 IST 2013
39 | TT_TASK | S623 Excavate 150m (SZ) (m.rock/total 854m) | Sat Jan 12 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
40 | TT_TASK | S623 Conduct General Maintenance | Wed Feb 20 08:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013
41 | TT_TASK | S623 Excavate 50m (SZ) (s.rock/total 904m) | Thu Feb 28 08:00:00 IST 2013 | Fri Mar 08 08:00:00 IST 2013
42 | TT_TASK | S623 Conduct General Maintenance | Sun Apr 21 08:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013
43 | TT_TASK | S623 Excavate 100m (SZ) (rock/total 1004m) | Mon Apr 22 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
44 | TT_TASK | S623 Conduct General Maintenance | Sat Jun 08 10:38:00 IDT 2013 | Mon Jun 10 10:38:00 IDT 2013
45 | TT_TASK | S623 Excavate 470m (SZ) (rock/total 1474m) | Wed May 15 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
46 | TT_TASK | S623 Conduct General Maintenance | Fri Sep 13 08:00:00 IDT 2013 | Sun Sep 15 08:00:00 IDT 2013
47 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Aug 15 08:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013
48 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013
49 | TT_TASK | S623 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Oct 31 08:00:00 IST 2013 | Sun Nov 10 08:00:00 IST 2013
50 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013
51 | TT_TASK | S623 Excavate 84m (SZ) (c.rock/total 1856m) | Thu Oct 31 08:00:00 IST 2013 | Sat Nov 02 08:00:00 IST 2013
52 | FINISH_MILESTONE | Complete TBM Excavation Down Track (SZ) | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 08:00:00 IST 2013
53 | TT_TASK | S624 Excavate 100m (SZ) (s.rock) | Mon Nov 05 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
54 | TT_TASK | S624 Conduct General Maintenance | Mon Dec 10 08:00:00 IST 2012 | Thu Dec 13 08:00:00 IST 2012
55 | TT_TASK | S624 Excavate 142m (SZ) (s.rock/total 242m) | Thu Dec 13 08:00:00 IST 2012 | Sun Jan 06 08:00:00 IST 2013
56 | TT_TASK | S624 Conduct General Maintenance | Sat Jan 05 08:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013
57 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 484m) | Tue Jan 08 08:00:00 IST 2013 | Sun Feb 17 08:00:00 IST 2013
58 | TT_TASK | S624 Conduct General Maintenance | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 08:00:00 IST 2013
59 | TT_TASK | S624 Excavate 220m (SZ) (s.rock/total 704m) | Tue Feb 19 08:00:00 IST 2013 | Thu Mar 28 08:00:00 IST 2013
60 | TT_TASK | S624 Conduct General Maintenance | Fri Jun 28 08:58:00 IDT 2013 | Mon Jul 01 08:58:00 IDT 2013
61 | TT_TASK | S624 Excavate 150m (SZ) (m.rock/total 854m) | Tue Jul 02 08:58:00 IDT 2013 | Mon Jul 22 08:58:00 IDT 2013
62 | TT_TASK | S624 Conduct General Maintenance | Wed Jul 24 08:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013
63 | TT_TASK | S624 Excavate 50m (SZ) (s.rock/total 904m) | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
64 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 08:00:00 IDT 2013
65 | TT_TASK | S624 Excavate 100m (SZ) (s/m.rock/total 1004m) | Tue Aug 06 08:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013
66 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 26 08:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013
67 | TT_TASK | S624 Excavate 470m (SZ) (s/m.rock/total 1474m) | Fri Sep 13 08:00:00 IDT 2013 | Sun Dec 01 08:00:00 IST 2013
68 | TT_TASK | S624 Conduct General Maintenance | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
69 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Jan 30 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
70 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
71 | TT_TASK | S624 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Jan 30 08:00:00 IST 2014 | Sun Feb 09 08:00:00 IST 2014
72 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
73 | TT_TASK | S624 Excavate 92m (SZ) (c.rock/total 1864m) | Thu Jan 30 08:00:00 IST 2014 | Tue Feb 11 08:00:00 IST 2014
74 | FINISH_MILESTONE | Complete TBM Excavation Up Track (SZ) | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
75 | None | Interface Contractor Programme - 825 | Tue Sep 21 08:00:00 IST 2010 | Thu Dec 01 07:00:00 IST 2016
76 | FINISH_MILESTONE | TBM shaft for Contract 826 within Works Area 1.5 | Tue Jun 09 11:00:00 IDT 2015 | Tue Jun 09 11:00:00 IDT 2015
77 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - first time | Tue Sep 21 08:00:00 IST 2010 | Tue Sep 21 08:00:00 IST 2010
78 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - second time | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
79 | TT_TASK | Cut & cover tunnel Bay 1 tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 20 08:00:00 IST 2014
80 | TT_TASK | Cut & cover tunnel Bay 2 tunnel construction | Sat Nov 30 08:00:00 IST 2013 | Mon Feb 17 08:00:00 IST 2014
81 | FINISH_MILESTONE | 826 to complete all works at interface and allow 825 access | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
82 | TT_TASK | 825 complete stitch joint to 826 tunnel | Sun May 01 07:00:00 IDT 2016 | Sat Jun 25 17:00:00 IDT 2016
83 | FINISH_MILESTONE | Return of Works Area 1.5 to 825 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
84 | None | Interface Contractor Programme - 830 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
85 | TT_TASK | Allow concrete pumping access for Contract 830 within Works Area 1.5 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
86 | None | Works Areas | Mon Sep 20 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
87 | None | Access Dates | Mon Sep 20 08:00:00 IST 2010 | Thu Nov 05 07:00:00 IST 2015
88 | START_MILESTONE | Works Area 1.3 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
89 | START_MILESTONE | Works Area 1.4A (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
90 | START_MILESTONE | Works Area 1.4B first time (36/2010, 13 Sep 10) | Mon Sep 20 08:00:00 IST 2010 | Mon Sep 20 08:00:00 IST 2010
91 | START_MILESTONE | Works Area 1.4B second time (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
92 | START_MILESTONE | Works Area 1.5 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
93 | START_MILESTONE | Works Area 1.6 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
94 | START_MILESTONE | Works Area 1.16 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
95 | START_MILESTONE | Works Area 1.17 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
96 | START_MILESTONE | Works Area 1.19 (47/2010, 29 Nov 10) | Mon Nov 29 08:00:00 IST 2010 | Mon Nov 29 08:00:00 IST 2010
97 | START_MILESTONE | Works Area 1.21 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
98 | None | Return Dates | Fri Dec 17 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
99 | FINISH_MILESTONE | Works Area 1.3 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
100 | FINISH_MILESTONE | Works Area 1.4A (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
101 | FINISH_MILESTONE | Works Area 1.4B first time (01/2011, 9 Jan 11) | Fri Dec 17 08:00:00 IST 2010 | Fri Dec 17 08:00:00 IST 2010
102 | FINISH_MILESTONE | Works Area 1.4B second time (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
103 | FINISH_MILESTONE | Works Area 1.5 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
104 | FINISH_MILESTONE | Works Area 1.6 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
105 | FINISH_MILESTONE | Works Area 1.16 (36/2013, 8 Sep 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
106 | FINISH_MILESTONE | Works Area 1.17 (50/2013, 15 Dec 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
107 | FINISH_MILESTONE | Works Area 1.19 (10 May 16) | Tue Feb 28 17:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017
108 | FINISH_MILESTONE | Works Area 1.21 (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
109 | None | Specified Milestone Dates | Sun Apr 25 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
110 | None | Cost Centre A | Sun Jun 27 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
111 | FINISH_MILESTONE | A1 (25/2010, 27 Jun 10) - Contractor's Submissions | Sun Jun 27 08:00:00 IDT 2010 | Sun Jun 27 08:00:00 IDT 2010
112 | FINISH_MILESTONE | A2 (51/2010, 26 Dec 10) - Approval of TBM Tunnelling method Statement | Wed Jan 05 08:00:00 IST 2011 | Wed Jan 05 08:00:00 IST 2011
113 | FINISH_MILESTONE | A3 (08/2011, 27 Feb 11) - Implementation of Specified Plans and Programming | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
114 | FINISH_MILESTONE | A4 (38/2011, 25 Sep 11) - Delivery of 2 nos. TBM to HGP Launching Shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
115 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of the MS of Construction of Cross Passages | Thu Feb 23 08:00:00 IST 2012 | Thu Feb 23 08:00:00 IST 2012
116 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of Detailed Interface Require Specific with Designated Contractor | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
117 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Implementation of Specified Plans | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
118 | FINISH_MILESTONE | A6 (08/2012, 26 Feb 12) - Implementation of Specified Plans and Programme | Fri Feb 24 08:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012
119 | FINISH_MILESTONE | A7 (25/2012, 24 Jun 12) - Approval of Detailed Interface Require Specific with Designated Contractor | Tue Jul 31 08:00:00 IDT 2012 | Tue Jul 31 08:00:00 IDT 2012
120 | FINISH_MILESTONE | A8 (34/2012, 26 Aug 12) - Implementation of Specified Plans | Wed Aug 22 08:00:00 IDT 2012 | Wed Aug 22 08:00:00 IDT 2012
121 | FINISH_MILESTONE | *A9 (48/2014, 30 Nov 14) - Complete 28% of the 1st tunnel drive | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 01 07:00:00 IST 2014
122 | FINISH_MILESTONE | A9a (08/2013, 24 Feb 13) - Implementation of Specific Plans and Program | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
123 | FINISH_MILESTONE | *A9b (08/2014, 1 May 14) - Complete 15% of the 1st tunnel drive | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
124 | FINISH_MILESTONE | A10 (34/2013, 25 Aug 13) - Implementation of Specific Plans | Tue Jul 15 17:00:00 IDT 2014 | Tue Jul 15 17:00:00 IDT 2014
125 | FINISH_MILESTONE | *A11 (51/2015, 27 Dec 15) - Achieve Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
126 | FINISH_MILESTONE | A12 (32/2014, 10 Aug 14) - Approval of Draft O & M Manuals and Draft As-built drawings | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
127 | FINISH_MILESTONE | A13 (06/2015, 8 Feb 15) - Approval of Operating & Maintenance Mauls | Fri Feb 24 17:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017
128 | None | Cost Centre B | Sun Apr 25 08:00:00 IDT 2010 | Fri Apr 01 07:00:00 IDT 2016
129 | FINISH_MILESTONE | B1.1 (16/2010, 25 Apr 10) - Provide Evidence that TBM | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
130 | FINISH_MILESTONE | B1a (25/2010, 27 Jun 10) - On-demand bond or bank guarantee | Sat Jun 26 08:00:00 IDT 2010 | Sat Jun 26 08:00:00 IDT 2010
131 | FINISH_MILESTONE | B1.2 (28/2010, 18 Jul 10) - Provide Evidence that the STP | Thu Jul 29 08:00:00 IDT 2010 | Thu Jul 29 08:00:00 IDT 2010
132 | FINISH_MILESTONE | B2 (21/2011, 29 May 11) - Delivery of the 1st TBM | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
133 | FINISH_MILESTONE | B2a (38/2011, 25 Sep 11) - Delivery of the 2nd TBM | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
134 | FINISH_MILESTONE | B3 (49/2013, 8 Dec 13) - Complete Final Disassembly of TBM | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
135 | None | Cost Centre C (UT/S624) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
136 | FINISH_MILESTONE | C1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
137 | FINISH_MILESTONE | *C2 (17/2014, 27 Apr 14) - Complete 10% Tunnel Drive & 70% Segments | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
138 | FINISH_MILESTONE | *C3 (52/2014, 28 Dec 14) - Complete 40% Tunnel Drive & 95% Segments | Mon Feb 23 07:00:00 IST 2015 | Mon Feb 23 07:00:00 IST 2015
139 | FINISH_MILESTONE | *C4 (26/2015, 28 Jun 15) - Complete 100% Tunnel Drive | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
140 | FINISH_MILESTONE | *C5 (35/2015, 30 Aug 15) -Complete 50% Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
141 | FINISH_MILESTONE | *C6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
142 | FINISH_MILESTONE | C7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
143 | None | Cost Centre D (DT/S623) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
144 | FINISH_MILESTONE | D1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
145 | FINISH_MILESTONE | D2 (10/2013, 10MAR13) - Complete 5% Tunnel Drive & 40% Segments | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
146 | FINISH_MILESTONE | *D3 (48/2014, 30 Nov 14) -Complete 28% Tunnel Drive & 85% Segments | Tue Jun 30 07:00:00 IDT 2015 | Tue Jun 30 07:00:00 IDT 2015
147 | FINISH_MILESTONE | *D4 (35/2015, 30 Aug 15) -Complete 100% Tunnel Drive | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
148 | FINISH_MILESTONE | *D5 (43/2015, 25 Oct 15) - Complete 50% of Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
149 | FINISH_MILESTONE | *D6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
150 | FINISH_MILESTONE | D7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
151 | None | Cost Centre E (CP) | Thu Dec 16 08:00:00 IST 2010 | Sat Dec 31 17:00:00 IST 2016
152 | FINISH_MILESTONE | E1 (01/2011, 9 Jan 11) - Complete Ground Treatment | Thu Dec 16 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
153 | FINISH_MILESTONE | E2 (08/2011, 27 Feb 11) - Submit instrumentation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
154 | FINISH_MILESTONE | E3 (34/2011, 28 Aug 11) - Submit instrumentation | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
155 | FINISH_MILESTONE | E4 (08/2012, 26 Feb 12) - Submit instrumentation | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 08:00:00 IST 2012
156 | FINISH_MILESTONE | E5 (34/2012, 26 Aug 12) - Submit instrumentation | Sat Aug 25 08:00:00 IDT 2012 | Sat Aug 25 08:00:00 IDT 2012
157 | FINISH_MILESTONE | E6 (08/2013, 24 Feb 13) - Submit instrumentation | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
158 | FINISH_MILESTONE | E7 (48/2013, 30 Nov 13) - Major ground treatment plant for CPs | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 01 07:00:00 IST 2015
159 | FINISH_MILESTONE | E8 (13/2015, 29 Mar 15) - Complete 4 Cross Passage Ground Treatment | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
160 | FINISH_MILESTONE | *E9 (51/2015, 20 Dec 15) - Deg 1 Completion in Cross Passage | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
161 | FINISH_MILESTONE | E10 (25/2016) - All Works Complete | Sat Dec 31 17:00:00 IST 2016 | Sat Dec 31 17:00:00 IST 2016
162 | None | Construction and Site Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
163 | None | Surface Operations in Works Areas | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
164 | None | Huanggang Park | Tue Nov 02 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
165 | TT_TASK | Establish MTRC Project Office in Shenzhen | Tue Nov 02 08:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010
166 | TT_TASK | Establish 826 HGP Site Office | Tue Nov 30 08:00:00 IST 2010 | Mon Jan 17 08:00:00 IST 2011
167 | TT_TASK | University Games Period | Mon Aug 01 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
168 | TT_TASK | Operation and maintenance of ground support facilities during tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Tue Oct 31 08:00:00 IST 2017
169 | None | Mai Po Retrieval Shaft | Fri Aug 06 08:00:00 IDT 2010 | Tue Apr 21 08:00:00 IDT 2015
170 | None | Ground Treatment Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Feb 01 08:00:00 IST 2011
171 | FINISH_MILESTONE | Submit Inspection and Testing Plan for ground treatment works | Fri Aug 06 08:00:00 IDT 2010 | Fri Aug 06 08:00:00 IDT 2010
172 | TT_TASK | Engineer's review on Inspection and Testing Plan | Fri Aug 06 08:00:00 IDT 2010 | Fri Sep 03 08:00:00 IDT 2010
173 | TT_TASK | Establish Works Area 1.4B with 825 Contractor | Mon Sep 20 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
174 | TT_TASK | Set up grouting plant | Tue Oct 05 08:00:00 IST 2010 | Fri Oct 15 08:00:00 IST 2010
175 | TT_TASK | Drilling - Down Track tunnel | Thu Oct 07 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
176 | TT_TASK | Drilling - Up Track tunnel | Mon Oct 18 08:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010
177 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 04 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
178 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 11 08:00:00 IST 2010 | Sat Nov 27 08:00:00 IST 2010
179 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
180 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
181 | TT_TASK | Permeability testing - Down Track tunnel | Tue Dec 07 08:00:00 IST 2010 | Mon Dec 13 08:00:00 IST 2010
182 | TT_TASK | Permeability testing - Up Track tunnel | Wed Dec 08 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
183 | TT_TASK | Demobilise grout plant | Mon Dec 13 08:00:00 IST 2010 | Sat Dec 18 08:00:00 IST 2010
184 | TT_TASK | Clear Works Area 1.4B for 825 Contractor's D.Wall | Mon Dec 13 08:00:00 IST 2010 | Wed Dec 22 08:00:00 IST 2010
185 | TT_TASK | Install instrumentation and monitoring equipment | Thu Oct 28 08:00:00 IST 2010 | Tue Feb 01 08:00:00 IST 2011
186 | None | Jet Grouting Works for TBM Break-out | Tue Dec 31 08:00:00 IST 2013 | Tue Nov 18 08:00:00 IST 2014
187 | TT_TASK | Submit Method Statement for Jet Grouting Works | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 27 08:00:00 IST 2014
188 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
189 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 22 08:00:00 IST 2014
190 | TT_TASK | Trial of Jet grouting | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 27 08:00:00 IST 2014
191 | TT_TASK | Jet Grouting Works | Fri Jul 18 08:00:00 IDT 2014 | Tue Nov 18 08:00:00 IST 2014
192 | None | Ground Freezing Plant | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
193 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Ground freezing | Tue Mar 24 08:00:00 IST 2015 | Tue Mar 24 08:00:00 IST 2015
194 | TT_TASK | Engineer's review on Inspection and Testing Plan | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
195 | None | TBM Drives from Boundary to Mai Po Shaft | Fri May 10 08:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
196 | None | Down Track - Ch.115+929 to Ch.117+400 | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 16 17:00:00 IST 2015
197 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
198 | TT_TASK | Continue S623 drive, ch. 115+929 to ch. 115+950 in soil | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013
199 | TT_TASK | Continue S623 drive, ch. 115+950 to ch. 115+983 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Sat Jan 04 08:00:00 IST 2014
200 | TT_TASK | Continue S623 drive, ch. 115+983 to ch. 116+050 in soil | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 08 08:00:00 IST 2014
201 | TT_TASK | Continue S623 drive, ch. 116+050 to ch. 116+213 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
202 | TT_TASK | Continue S623 drive, ch. 116+213 to ch. 116+230 in soil | Tue Apr 01 08:00:00 IDT 2014 | Thu Apr 03 08:00:00 IDT 2014
203 | TT_TASK | Continue S623 drive, ch. 116+230 to ch. 116+260 in marble | Tue Apr 01 08:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014
204 | TT_TASK | Continue S623 drive, ch. 116+260 to ch. 116+284 in marble | Tue Jul 01 08:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014
205 | TT_TASK | TBM Cutter Head Repair & S624 Overtaking Stoppage | Fri Aug 01 08:00:00 IDT 2014 | Fri Oct 24 08:00:00 IDT 2014
206 | TT_TASK | Continue S623 drive, ch. 116+284 to ch. 116+319 in marble | Fri Nov 21 07:00:00 IST 2014 | Mon Dec 01 17:00:00 IST 2014
207 | TT_TASK | Continue S623 drive, ch. 116+319 to ch. 116+349 in marble | Wed Feb 04 07:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
208 | TT_TASK | Continue S623 drive, ch. 116+349 to ch. 116+379 in marble | Sun Feb 01 07:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
209 | TT_TASK | Continue S623 drive, ch. 116+379 to ch. 116+408 in marble | Sun Mar 01 07:00:00 IST 2015 | Thu Mar 05 01:00:00 IST 2015
210 | TT_TASK | Continue S623 drive, ch. 116+408 to ch. 116+430 in marble | Sun Mar 01 07:00:00 IST 2015 | Sat Mar 07 17:00:00 IST 2015
211 | TT_TASK | Continue S623 drive, ch. 116+430 to ch. 116+600 in soil | Sun Mar 01 07:00:00 IST 2015 | Mon Mar 30 17:00:00 IDT 2015
212 | TT_TASK | Continue S623 drive, ch. 116+600 to ch. 116+694 in soil | Fri Jul 17 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
213 | TT_TASK | Continue S623 drive, ch. 116+694 to ch. 116+927 in Alluvial zone | Tue Jun 30 07:00:00 IDT 2015 | Thu Sep 17 17:00:00 IDT 2015
214 | TT_TASK | Continue S623 drive, ch. 116+927 to ch. 116+945 in soil | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
215 | TT_TASK | Continue S623 drive, ch. 116+945 to ch. 117+400 in soil | Tue Sep 29 07:00:00 IDT 2015 | Wed Dec 16 17:00:00 IST 2015
216 | TT_TASK | Pre-coring at diaphragm wall after TBM S623 arrival | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
217 | TT_TASK | TBM Breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
218 | None | S623 TBM Removal | Thu Oct 22 07:00:00 IDT 2015 | Thu Dec 01 07:00:00 IST 2016
219 | TT_TASK | Move TBM S623 front portion to cradle | Thu Oct 22 07:00:00 IDT 2015 | Tue Oct 27 17:00:00 IST 2015
220 | TT_TASK | Weld additional bracing brackets corbels | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
221 | TT_TASK | Install cradle on lateral shifting system | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
222 | TT_TASK | Move and shift TBM to dismantle location | Thu Apr 07 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
223 | TT_TASK | Dismantle Cutter Head & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
224 | TT_TASK | Dismantle TBM rear & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
225 | TT_TASK | Dismantle segment installation machine & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
226 | TT_TASK | Dismantle TBM middle sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
227 | TT_TASK | Dismantle TBM front sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
228 | TT_TASK | Dismantle S623 Link Bridge & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
229 | TT_TASK | Dismantle S623 Wagon #1 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
230 | TT_TASK | Dismantle S623 Wagon #2 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
231 | TT_TASK | Dismantle S623 Wagon #3 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
232 | TT_TASK | Dismantle S623 Wagon #4 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
233 | TT_TASK | Dismantle S623 Wagon #5 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
234 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N1 | Thu Jun 23 07:00:00 IDT 2016 | Thu Jun 23 07:00:00 IDT 2016
235 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N2 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
236 | TT_TASK | Site clearance | Fri Apr 01 07:00:00 IDT 2016 | Tue Sep 27 17:00:00 IDT 2016
237 | None | Up Track - Ch.115+940 to Ch.117+413 | Fri May 10 08:00:00 IDT 2013 | Fri Oct 09 17:00:00 IDT 2015
238 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Fri May 10 08:00:00 IDT 2013 | Sat May 11 08:00:00 IDT 2013
239 | TT_TASK | Continue S624 drive, ch. 115+939 to ch. 115+950 in soil | Fri May 09 08:00:00 IDT 2014 | Sat May 10 08:00:00 IDT 2014
240 | TT_TASK | Continue S624 drive, ch. 115+950 to ch. 115+987 in mixed ground | Fri May 09 08:00:00 IDT 2014 | Tue May 13 08:00:00 IDT 2014
241 | TT_TASK | Continue S624 drive, ch. 115+987 to ch. 116+050 in soil | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 08:00:00 IDT 2014
242 | TT_TASK | Continue S624 drive, ch. 116+050 to ch. 116+226 in mixed ground | Sun Jun 01 08:00:00 IDT 2014 | Wed Jul 02 08:00:00 IDT 2014
243 | TT_TASK | Continue S624 drive, ch. 116+226 to ch. 116+240 in soil/marble | Fri Aug 01 08:00:00 IDT 2014 | Sun Aug 03 08:00:00 IDT 2014
244 | TT_TASK | Continue S624 drive, ch. 116+240 to ch. 116+270 in marble | Fri Aug 01 08:00:00 IDT 2014 | Wed Aug 13 08:00:00 IDT 2014
245 | TT_TASK | Continue S624 drive, ch. 116+270 to ch. 116+300 in marble | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014
246 | TT_TASK | Continue S624 drive, ch. 116+300 to ch. 116+329 in marble | Wed Oct 01 08:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014
247 | TT_TASK | Continue S624 drive, ch. 116+329 to ch. 116+358 in marble | Sat Nov 01 07:00:00 IST 2014 | Mon Nov 17 17:00:00 IST 2014
248 | TT_TASK | Continue S624 drive, ch. 116+358 to ch. 116+388 in marble | Sun Nov 23 07:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
249 | TT_TASK | Continue S624 drive, ch. 116+388 to ch. 116+415 in marble | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 02 17:00:00 IST 2015
250 | TT_TASK | Continue S624 drive, ch. 116+415 to ch. 116+430 in soil/marble | Sun Jan 11 07:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
251 | TT_TASK | Continue S624 drive, ch. 116+430 to ch. 116+600 in soil | Tue Jan 13 07:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
252 | TT_TASK | Continue S624 drive, ch. 116+600 to ch. 116+850 in soil/Alluv. zone | Wed Jan 21 07:00:00 IST 2015 | Thu Mar 05 17:00:00 IST 2015
253 | TT_TASK | Continue S624 drive, ch. 116+850 to ch. 116+930 in Alluv. zone | Tue Mar 31 07:00:00 IDT 2015 | Mon Apr 13 17:00:00 IDT 2015
254 | TT_TASK | Continue S624 drive, ch. 116+930 to ch. 117+413 in soil at Mai Po | Thu Jul 16 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
255 | TT_TASK | Pre-coring at diaphragm wall after TBM S624 arrival | Sat Aug 15 07:00:00 IDT 2015 | Mon Aug 17 17:00:00 IDT 2015
256 | TT_TASK | TBM S624 breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
257 | None | TBM Removal Preparation | Mon Dec 01 07:00:00 IST 2014 | Wed Nov 11 17:00:00 IST 2015
258 | TT_TASK | Prepare TTMS report for removal of TBM S624 & S623 | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 15 17:00:00 IST 2014
259 | TT_TASK | Working Group Meeting & SLG Meeting | Fri Jan 16 07:00:00 IST 2015 | Wed Apr 15 17:00:00 IDT 2015
260 | TT_TASK | Drawings' approval and endosement from RDO | Mon Feb 23 07:00:00 IST 2015 | Mon Mar 09 17:00:00 IST 2015
261 | TT_TASK | Submit advance notice to the HK Police | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
262 | TT_TASK | On stie preparation works | Mon Jul 13 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
263 | TT_TASK | Proof drilling for water tightness test of jet grout block | Wed Jul 01 07:00:00 IDT 2015 | Tue Jul 07 17:00:00 IDT 2015
264 | TT_TASK | Shaft bottom slab levelling | Fri Jul 24 07:00:00 IDT 2015 | Sat Jul 25 17:00:00 IDT 2015
265 | TT_TASK | Moving device and cradle installation | Thu Jul 23 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
266 | None | S624 TBM Removal | Tue Sep 29 07:00:00 IDT 2015 | Sun Nov 08 17:00:00 IST 2015
267 | TT_TASK | Move TBM S624 front portion to cradle | Tue Oct 13 07:00:00 IDT 2015 | Sun Oct 18 17:00:00 IDT 2015
268 | TT_TASK | Weld additional bracing brackets corbels | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
269 | TT_TASK | Install cradle on lateral shifting system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
270 | TT_TASK | Move and shift TBM to dismantle location | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
271 | TT_TASK | Dismantle Cutter Head & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
272 | TT_TASK | Dismantle TBM front sheild & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
273 | TT_TASK | Dismantle segment installation machine & Remove | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
274 | TT_TASK | Dismantle TBM middle sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
275 | TT_TASK | Dismantle TBM rear sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
276 | TT_TASK | Dismantle S624 Link Bridge & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
277 | TT_TASK | Dismantle S624 Wagon #1 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
278 | TT_TASK | Dismantle S624 Wagon #2 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
279 | TT_TASK | Dismantle S624 Wagon #3 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
280 | TT_TASK | Dismantle S624 Wagon #4 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
281 | TT_TASK | Dismantle S624 Wagon #5 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
282 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N1 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
283 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N2 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
284 | None | Cross Passages (HK) | Wed Oct 01 07:00:00 IDT 2014 | Thu Aug 04 17:00:00 IDT 2016
285 | None | Freezing Station A | Sat Oct 11 07:00:00 IDT 2014 | Mon Nov 09 17:00:00 IST 2015
286 | TT_TASK | Erect Freezing Station Platform | Sat Oct 11 07:00:00 IDT 2014 | Tue Oct 21 17:00:00 IDT 2014
287 | TT_TASK | Freezing Station Installation & Testing | Thu Jan 01 07:00:00 IST 2015 | Sat Jan 31 17:00:00 IST 2015
288 | TT_TASK | Remove Freezing Station A | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
289 | None | Cross Passage #1. Ch.116+030 | Wed Oct 01 07:00:00 IDT 2014 | Tue May 10 17:00:00 IDT 2016
290 | TT_TASK | Erect Temporary Drilling Platform | Wed Oct 01 07:00:00 IDT 2014 | Fri Oct 10 17:00:00 IDT 2014
291 | TT_TASK | Drill & Install Freezing Pipe | Mon Dec 01 07:00:00 IST 2014 | Wed Jan 14 17:00:00 IST 2015
292 | TT_TASK | Install temporary support including ring support (Up-track) | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 15 17:00:00 IST 2015
293 | TT_TASK | Install temporary support including ring support (Down-track) | Mon Feb 23 07:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
294 | TT_TASK | Intall safe door | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 25 17:00:00 IDT 2015
295 | TT_TASK | Install freezing & monitoring system | Mon Feb 23 07:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
296 | TT_TASK | Conduct Ground Freezing | Sun Mar 01 07:00:00 IST 2015 | Tue Apr 14 17:00:00 IDT 2015
297 | TT_TASK | Maintain ground freezing during construction of CP | Tue Apr 21 07:00:00 IDT 2015 | Sun Jun 14 17:00:00 IDT 2015
298 | TT_TASK | Tunnel segment cutting & removal | Tue Apr 21 07:00:00 IDT 2015 | Wed Apr 22 17:00:00 IDT 2015
299 | TT_TASK | Excavate and temporary support | Tue Apr 21 07:00:00 IDT 2015 | Sat May 23 17:00:00 IDT 2015
300 | TT_TASK | Tunnel segment removal | Tue Aug 04 07:00:00 IDT 2015 | Mon Aug 10 17:00:00 IDT 2015
301 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Jul 03 07:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
302 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 08 17:00:00 IDT 2015
303 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
304 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
305 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
306 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
307 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
308 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
309 | TT_TASK | Remove formwork | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
310 | TT_TASK | Concrete achieved the design strength | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
311 | TT_TASK | Remove temporary works | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
312 | TT_TASK | Remove Freezing Plant | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
313 | TT_TASK | Thawing & Proof Grouting | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
314 | TT_TASK | Make Good Freezing Pipe Hole | Sun May 01 07:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
315 | None | Cross Passage #2. Ch.116+195 | Mon Feb 23 07:00:00 IST 2015 | Sun Apr 10 17:00:00 IDT 2016
316 | TT_TASK | Erect Temporary Drilling Platform | Mon Feb 23 07:00:00 IST 2015 | Wed Feb 25 17:00:00 IST 2015
317 | TT_TASK | Drill & Install Freezing Pipe | Mon Feb 23 07:00:00 IST 2015 | Fri Apr 10 17:00:00 IDT 2015
318 | TT_TASK | Install temporary support (including ring support) | Tue Apr 21 07:00:00 IDT 2015 | Tue May 05 17:00:00 IDT 2015
319 | TT_TASK | Install safe door | Mon Jun 01 07:00:00 IDT 2015 | Thu Jun 04 17:00:00 IDT 2015
320 | TT_TASK | Install freezing & monitoring system | Tue Apr 21 07:00:00 IDT 2015 | Thu Apr 23 17:00:00 IDT 2015
321 | TT_TASK | Conduct Ground Freezing | Tue Apr 21 07:00:00 IDT 2015 | Tue Jun 16 17:00:00 IDT 2015
322 | TT_TASK | Maintain ground freezing during construction of CP | Fri Jul 24 07:00:00 IDT 2015 | Mon Sep 21 17:00:00 IDT 2015
323 | TT_TASK | Tunnel segment cutting & removal | Fri Jul 24 07:00:00 IDT 2015 | Thu Jul 30 17:00:00 IDT 2015
324 | TT_TASK | Excavate and temporary support | Sun Jul 26 07:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
325 | TT_TASK | Tunnel segment removal | Mon Aug 03 07:00:00 IDT 2015 | Tue Aug 04 17:00:00 IDT 2015
326 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
327 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
328 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
329 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
330 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
331 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
332 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
333 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
334 | TT_TASK | Remove formwork | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
335 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
336 | TT_TASK | Remove temporary works | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
337 | TT_TASK | Remove Freezing Pipes | Sat Nov 14 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
338 | TT_TASK | Thawing & Proof Grouting | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
339 | TT_TASK | Make Good Freezing Pipe Holes | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
340 | None | Freezing Station B | Mon Jun 01 07:00:00 IDT 2015 | Thu Aug 04 17:00:00 IDT 2016
341 | TT_TASK | Erect Freezing Station Platform | Mon Jun 01 07:00:00 IDT 2015 | Sat Jun 20 17:00:00 IDT 2015
342 | TT_TASK | Freezing Station Installation & Testing | Sun Jun 21 07:00:00 IDT 2015 | Fri Jul 10 17:00:00 IDT 2015
343 | TT_TASK | Remove Station B | Fri Jul 22 07:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016
344 | None | Cross Passage #3. Ch. 116+445 | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
345 | TT_TASK | Erect Temporary Drilling Platform | Tue Apr 21 07:00:00 IDT 2015 | Sun Apr 26 17:00:00 IDT 2015
346 | TT_TASK | Drill & Install Freezing Pipe | Tue Apr 21 07:00:00 IDT 2015 | Fri Jun 05 17:00:00 IDT 2015
347 | TT_TASK | Install temporary support (including ring support) | Sun Jul 19 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
348 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
349 | TT_TASK | Install freezing & monitoring system | Wed Jul 01 07:00:00 IDT 2015 | Fri Jul 03 17:00:00 IDT 2015
350 | TT_TASK | Conduct Ground Freezing | Sat Jul 04 07:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
351 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Sep 29 07:00:00 IDT 2015 | Fri Dec 18 17:00:00 IST 2015
352 | TT_TASK | Tunnel segment cutting & removal at U/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
353 | TT_TASK | Excavate and temporary support | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 31 17:00:00 IST 2015
354 | TT_TASK | Tunnel segment removal at D/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
355 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
356 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
357 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
358 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
359 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 12 17:00:00 IST 2015
360 | TT_TASK | Lining concreting (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
361 | TT_TASK | Lining concrete curing (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
362 | TT_TASK | Make Good Freezing Pipe Hole | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
363 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
364 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
365 | TT_TASK | Remove temp. works, ring support and temp. platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
366 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
367 | None | Cross Passage #4. Ch. 116+671 | Mon Jul 06 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
368 | TT_TASK | Erect Temporary Drilling Platform | Sun Jul 19 07:00:00 IDT 2015 | Thu Jul 23 17:00:00 IDT 2015
369 | TT_TASK | Drill & Install Freezing Pipe | Mon Jul 06 07:00:00 IDT 2015 | Thu Aug 20 17:00:00 IDT 2015
370 | TT_TASK | Install temporary support (including ring support) | Tue Sep 29 07:00:00 IDT 2015 | Tue Oct 13 17:00:00 IDT 2015
371 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
372 | TT_TASK | Install freezing & monitoring system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
373 | TT_TASK | Conduct Ground Freezing | Tue Sep 29 07:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
374 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Thu Nov 05 07:00:00 IST 2015 | Fri Feb 19 17:00:00 IST 2016
375 | TT_TASK | Tunnel segment cutting & removal at U/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
376 | TT_TASK | Excavate and temporary support | Mon Nov 09 07:00:00 IST 2015 | Wed Nov 25 17:00:00 IST 2015
377 | TT_TASK | Earthing, Waterproof works and waterproof test | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
378 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
379 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
380 | TT_TASK | Lining concrete curing (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
381 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
382 | TT_TASK | Lining concreting (side walls and roof) | Tue Nov 10 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
383 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
384 | TT_TASK | Remove formwork | Fri Apr 08 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
385 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
386 | TT_TASK | Remove temp. works and ring support | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
387 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
388 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
389 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
390 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Sat Nov 07 17:00:00 IST 2015
391 | TT_TASK | Erect temp. working platform | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
392 | TT_TASK | Drilling remaining holes at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
393 | TT_TASK | Install ring support at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
394 | TT_TASK | Tunnel segment removal at D/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
395 | None | Cross Passage #5. Ch. 116+966 | Wed Jul 01 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
396 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+066); last gantry passed CP5 | Wed Jul 01 07:00:00 IDT 2015 | Wed Jul 01 07:00:00 IDT 2015
397 | TT_TASK | Erect Temporary Drilling Platform at U/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
398 | START_MILESTONE | TBM S623 C/W exited Alluvial zone at S1425/Ch. 116+927 (* Note1) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
399 | TT_TASK | TBM S623 C/W boring from Ch. 116+927 to Ch. 116+986 (CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
400 | TT_TASK | Drill & Install Freezing Pipe at U/T | Sat Oct 10 07:00:00 IDT 2015 | Tue Nov 24 17:00:00 IST 2015
401 | TT_TASK | Raise track rail, slurry pipes diversion, install temp. support at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
402 | TT_TASK | Install Ring Support | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
403 | TT_TASK | Install freezing & monitoring system | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
404 | TT_TASK | Freezing system Test & Commissioning | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
405 | TT_TASK | Conduct Ground Freezing (Active phase) | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
406 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Dec 01 07:00:00 IST 2015 | Sun Mar 20 17:00:00 IST 2016
407 | TT_TASK | Install safe door (both sides) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
408 | TT_TASK | Tunnel segment cutting & removal at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
409 | TT_TASK | Excavate and temporary support (excavation from D/T) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
410 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
411 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
412 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
413 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
414 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
415 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
416 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
417 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
418 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
419 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
420 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
421 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
422 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
423 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Fri Nov 27 17:00:00 IST 2015
424 | TT_TASK | TBM S623 C/W boring from Ch.. 116+986 to Ch117+086 (last gantry passed CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 16 17:00:00 IDT 2015
425 | TT_TASK | Erect Temporary Drilling Platorm at D/T | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
426 | TT_TASK | Drilling remaining holes at D/T after S623 gantries passed | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 27 17:00:00 IST 2015
427 | TT_TASK | Install ring support at D/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
428 | None | Cross Passage #6. Ch. 117+216 | Sat Aug 01 07:00:00 IDT 2015 | Wed Jun 15 17:00:00 IDT 2016
429 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Sat Aug 01 07:00:00 IDT 2015 | Sat Aug 01 07:00:00 IDT 2015
430 | TT_TASK | Erect Drilling Platform at U/T | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
431 | TT_TASK | Drill ground freezing holes at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
432 | TT_TASK | Install Ring Support at U/T | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
433 | TT_TASK | Install freezing & monitoring system at U/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
434 | TT_TASK | Freezing system Test & Commissioning at U/T, Station B | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
435 | TT_TASK | Conduct Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Thu May 19 17:00:00 IDT 2016
436 | LEVEL_OF_EFFORT | Maintain Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Wed Jun 15 17:00:00 IDT 2016
437 | TT_TASK | Install safe door (both sides) | Sun Apr 10 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
438 | TT_TASK | Tunnel segment removal | Sat Apr 16 07:00:00 IDT 2016 | Wed Apr 20 17:00:00 IDT 2016
439 | TT_TASK | Excavate and temporary support (excavation from U/T side only) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
440 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
441 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
442 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
443 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
444 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
445 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
446 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
447 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
448 | TT_TASK | Remove formwork & Remove safe doors | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
449 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
450 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
451 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
452 | TT_TASK | Make Good Freezing Pipe Hole | Mon Apr 11 07:00:00 IDT 2016 | Thu Apr 14 17:00:00 IDT 2016
453 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Mon Apr 11 17:00:00 IDT 2016
454 | START_MILESTONE | S623 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
455 | TT_TASK | Erect Working Platform at D/T | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
456 | TT_TASK | Drill ground freezing holes at D/T | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
457 | TT_TASK | Install freezing & monitoring system at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
458 | TT_TASK | Ring support installation at D/T | Wed Apr 06 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
459 | None | Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
460 | None | Down Track Tunnel Finishes | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
461 | None | Tunnel Invert Slab (DT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 30 17:00:00 IDT 2016
462 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m-64=25m) | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
463 | TT_TASK | Invert Slab at CP1 (30m) | Sun May 29 07:00:00 IDT 2016 | Mon May 30 17:00:00 IDT 2016
464 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) | Sat May 21 07:00:00 IDT 2016 | Sat May 28 17:00:00 IDT 2016
465 | TT_TASK | Invert Slab at CP2 (30m) | Sat May 21 07:00:00 IDT 2016 | Sun May 22 17:00:00 IDT 2016
466 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Sun May 08 07:00:00 IDT 2016 | Fri May 20 17:00:00 IDT 2016
467 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
468 | TT_TASK | Invert Slab between CP3 and CP4 (226-45=181m) | Fri Apr 29 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
469 | TT_TASK | Invert Slab at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
470 | TT_TASK | Invert Slab between CP4 and CP5 (296-59=237m) | Thu Apr 14 07:00:00 IDT 2016 | Thu Apr 28 17:00:00 IDT 2016
471 | TT_TASK | Invert Slab at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
472 | TT_TASK | Invert Slab between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
473 | TT_TASK | Invert Slab at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
474 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (14m) | Thu Apr 07 07:00:00 IDT 2016 | Fri Apr 08 17:00:00 IDT 2016
475 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Thu Apr 07 07:00:00 IDT 2016 | Sat Apr 16 17:00:00 IDT 2016
476 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
477 | None | Lower Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
478 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
479 | TT_TASK | Lower Wkys at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
480 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
481 | TT_TASK | Lower Wks at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
482 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
483 | TT_TASK | Lower Wkys at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
484 | TT_TASK | Lower Wkys between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
485 | TT_TASK | Lower Wkys at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
486 | TT_TASK | Lower Wkys between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
487 | TT_TASK | Lower Wkys at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
488 | TT_TASK | Lower Wkys between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
489 | TT_TASK | Lower Wkys at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
490 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
491 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
492 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
493 | None | Upper Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
494 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
495 | TT_TASK | Upper Wky at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
496 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
497 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
498 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
499 | TT_TASK | Upper Wky at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
500 | TT_TASK | Upper Wky between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
501 | TT_TASK | Upper Wky at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
502 | TT_TASK | Upper Wky between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
503 | TT_TASK | Upper Wky at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
504 | TT_TASK | Upper Wky between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
505 | TT_TASK | Upper Wky at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
506 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
507 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
508 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
509 | None | DT Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Sat Dec 24 17:00:00 IST 2016
510 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
511 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
512 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
513 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
514 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
515 | None | Double Gates (DT) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
516 | TT_TASK | Install double gates at 20m south of CP6 | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
517 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
518 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
519 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
520 | None | Up Track Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 22 17:00:00 IST 2016
521 | None | Tunnel Invert Slab (UT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 02 17:00:00 IDT 2016
522 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m) | Tue Apr 26 07:00:00 IDT 2016 | Sun May 01 17:00:00 IDT 2016
523 | TT_TASK | Invert Slab at CP1 (30m) | Tue Apr 26 07:00:00 IDT 2016 | Wed Apr 27 17:00:00 IDT 2016
524 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) incl. Station A area | Mon Apr 18 07:00:00 IDT 2016 | Mon Apr 25 17:00:00 IDT 2016
525 | TT_TASK | Invert Slab at CP2 (30m) | Mon Apr 18 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
526 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Tue Apr 05 07:00:00 IDT 2016 | Sun Apr 17 17:00:00 IDT 2016
527 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
528 | TT_TASK | Invert Slab between CP3 and CP4 (226-47-34=145m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
529 | TT_TASK | Invert Slab at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
530 | TT_TASK | Invert Slab at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
531 | TT_TASK | Invert Slab between CP4 and CP5 (296-51=245m) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
532 | TT_TASK | Invert Slab at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
533 | TT_TASK | Invert Slab between CP5 and CP6 (250-32=218m) | Sat Dec 19 07:00:00 IST 2015 | Thu Dec 31 17:00:00 IST 2015
534 | TT_TASK | Invert Slab at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
535 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (20m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
536 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
537 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
538 | None | Lower Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
539 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
540 | TT_TASK | Lower Wkys at CP1 (30m) | Mon May 16 07:00:00 IDT 2016 | Tue May 17 17:00:00 IDT 2016
541 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
542 | TT_TASK | Lower Wkys at CP2 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
543 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
544 | TT_TASK | Lower Wkys at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
545 | TT_TASK | Lower Wkys between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
546 | TT_TASK | Lower Wkys at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
547 | TT_TASK | Lower Wkys at CP4 (64m) | Sat Apr 16 07:00:00 IDT 2016 | Mon Apr 18 17:00:00 IDT 2016
548 | TT_TASK | Lower Wkys between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
549 | TT_TASK | Lower Wkys at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
550 | TT_TASK | Lower Wkys between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
551 | TT_TASK | Lower Wkys at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
552 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
553 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
554 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
555 | None | Upper Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
556 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
557 | TT_TASK | Upper Wky at CP1 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
558 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
559 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
560 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
561 | TT_TASK | Upper Wky at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
562 | TT_TASK | Upper Wky between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
563 | TT_TASK | Upper Wky at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
564 | TT_TASK | Upper Wky at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
565 | TT_TASK | Upper Wky between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
566 | TT_TASK | Upper Wky at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
567 | TT_TASK | Upper Wky between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
568 | TT_TASK | Upper Wky at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
569 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
570 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
571 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
572 | None | Up Track Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Thu Dec 22 17:00:00 IST 2016
573 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
574 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
575 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Thu Dec 22 17:00:00 IST 2016
576 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
577 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
578 | None | UT Double Gates | Thu Nov 05 07:00:00 IST 2015 | Wed Apr 06 17:00:00 IDT 2016
579 | TT_TASK | Install double gates at 20m south of CP6 | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
580 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Wed Nov 11 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
581 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
582 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
583 | None | Tunnel Finishes to Completion | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
584 | None | Down Track | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
585 | TT_TASK | Operation and maintenance of temporary services | Fri Apr 08 07:00:00 IDT 2016 | Sun Mar 05 17:00:00 IST 2017
586 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
587 | None | Up Track | Wed Jun 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
588 | TT_TASK | Operation and maintenance of temporary services | Wed Jun 01 07:00:00 IDT 2016 | Thu Oct 06 17:00:00 IDT 2016
589 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
590 | None | Commissioning, Inspections and Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
591 | RESOURCE_DEPENDENT | Site Cleaning, Inspection for Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
592 | FINISH_MILESTONE | Submit draft as-built drawings (Z8.2) and draft O&M Manuals | Sat Dec 24 17:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
593 | FINISH_MILESTONE | Submit approved Design Data (Z8.4) | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
594 | FINISH_MILESTONE | Submit final as-built drawings and O&M Manuals | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
595 | TT_TASK | Inspect & Certify completion of whole works | Sat Mar 25 07:00:00 IDT 2017 | Fri Mar 31 17:00:00 IDT 2017
596 | None | Contract Preliminaries | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
597 | None | Designs and Submissions | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
598 | None | Principle Method Statements, Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
599 | None | Management Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Sun Oct 30 08:00:00 IST 2011
600 | TT_TASK | Submit System Assurance Plan (App P, P3.1) | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
601 | TT_TASK | Engineer's review on System Assurance Plan | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
602 | TT_TASK | Submit Health and Safety Plan (G3.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
603 | TT_TASK | Engineer's review on Health and Safety Plan | Wed May 05 08:00:00 IDT 2010 | Wed Jun 02 08:00:00 IDT 2010
604 | TT_TASK | Submit Quality Assurance Plan (G9.2.1) | Thu Apr 15 08:00:00 IDT 2010 | Thu May 13 08:00:00 IDT 2010
605 | TT_TASK | Engineer's review on Quality Assurance Plan | Wed May 12 08:00:00 IDT 2010 | Wed Jun 09 08:00:00 IDT 2010
606 | TT_TASK | Submit Prelimiary Master Programme (G4.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
607 | TT_TASK | Engineer's review on Prelimiary Master Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
608 | TT_TASK | Submit first Three-Month Rolling Programme (G4.8 | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 29 08:00:00 IDT 2010
609 | TT_TASK | Engineer's review on first Three-Month Rolling P | Fri Apr 02 08:00:00 IDT 2010 | Fri Apr 30 08:00:00 IDT 2010
610 | TT_TASK | Submit Time-chainage Programme (G4.11.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
611 | TT_TASK | Engineer's review on Time-chainage Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
612 | TT_TASK | Submit Design Schedule (App Z) | Mon May 03 08:00:00 IDT 2010 | Mon May 17 08:00:00 IDT 2010
613 | TT_TASK | Engineer's review on Design Schedule | Fri May 28 08:00:00 IDT 2010 | Fri Jun 25 08:00:00 IDT 2010
614 | TT_TASK | Submit Subcontractor Management Plan (App S) | Sat May 15 08:00:00 IDT 2010 | Mon Jun 14 08:00:00 IDT 2010
615 | TT_TASK | Engineer's review on Subcontractor Management Pl | Tue Jun 15 08:00:00 IDT 2010 | Tue Jul 13 08:00:00 IDT 2010
616 | TT_TASK | Submit Groundwater Monitoring and Emergency Resp | Thu Apr 22 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
617 | TT_TASK | Engineer's review on Groundwater Monitoring and | Fri Jun 04 08:00:00 IDT 2010 | Fri Jul 02 08:00:00 IDT 2010
618 | TT_TASK | Submit Water Pollution Control Measures and Moni | Thu Apr 15 08:00:00 IDT 2010 | Sun May 30 08:00:00 IDT 2010
619 | TT_TASK | Engineer's review on Water Pollution Control Mea | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
620 | TT_TASK | Submit Waste Management Plan (P22.8.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
621 | TT_TASK | Engineer's review on Waste Management Plan | Tue May 18 08:00:00 IDT 2010 | Tue Jun 15 08:00:00 IDT 2010
622 | TT_TASK | Submit the Plan for the Design for Safety and Co | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
623 | TT_TASK | Engineer's review on Plan for the Design for Saf | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
624 | TT_TASK | Submit Air Quality Management Plan (P22.4.4) | Fri Apr 09 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
625 | TT_TASK | Engineer's review on Air Quality Management Plan | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
626 | TT_TASK | Submit TBM manufacturiing and delivery programme | Sat May 22 08:00:00 IDT 2010 | Sat Jun 19 08:00:00 IDT 2010
627 | TT_TASK | Engineer's review on TBM manufacturiing and deli | Wed Jun 02 08:00:00 IDT 2010 | Wed Jun 30 08:00:00 IDT 2010
628 | TT_TASK | Submit Environmental Management Plan (G5.1.10) | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
629 | TT_TASK | Engineer's review on Environmental Management Pl | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
630 | TT_TASK | Submit interfacing documentation for System-wide | Mon Aug 01 08:00:00 IDT 2011 | Sun Oct 30 08:00:00 IST 2011
631 | TT_TASK | Engineer's review on interfacing documentation f | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
632 | None | Method Statements | Fri Apr 09 08:00:00 IDT 2010 | Wed Jun 17 17:00:00 IDT 2015
633 | TT_TASK | Submit Geotechnical Instruments installation | Fri Jun 18 08:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010
634 | TT_TASK | Engineer's review on Geotechnical Instruments installation | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
635 | TT_TASK | Submit Survey control network | Fri Apr 09 08:00:00 IDT 2010 | Mon May 24 08:00:00 IDT 2010
636 | TT_TASK | Engineer's review on Survey control network | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
637 | TT_TASK | Submit MS for surveying and survey control for tunnelling works | Mon Jun 14 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
638 | TT_TASK | Engineer's review on MS for surveying and survey control for tunnelling works | Sat Aug 07 08:00:00 IDT 2010 | Sat Sep 04 08:00:00 IDT 2010
639 | TT_TASK | Submit a Ground Treatment Works spoil disposal plan | Tue Jun 08 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
640 | TT_TASK | Engineer's review on Ground Treatment Works spoil disposal plan | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
641 | TT_TASK | Submit MS for ground treatment | Sun May 09 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
642 | TT_TASK | Engineer's review on MS for ground treatment | Fri Jun 25 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
643 | TT_TASK | Submit TBM MS for transportation and erection of the TBMs (X.17.1.1) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
644 | TT_TASK | Engineer's review on TBM MS for transportation and erection of the TBMs | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
645 | TT_TASK | Submit TBM MS for operation of the TBM (X17.1.3) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
646 | TT_TASK | Engineer's review on TBM MS for operation of the TBM | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
647 | TT_TASK | Submit MS for instrumentation and monitoring works in Ramsar & WPC areas | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 29 08:00:00 IDT 2011
648 | TT_TASK | Engineer's review on MS for instrumentation and monitoring works in Ramsar & WPC | Tue Mar 08 08:00:00 IST 2011 | Tue Apr 05 08:00:00 IDT 2011
649 | TT_TASK | Submit TBM MS for determining ground conditions ahead of the face (X17.1.5) (CS569) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
650 | TT_TASK | Engineer's review on TBM MS for determining ground conditions ahead of the face | Fri Apr 17 07:00:00 IDT 2015 | Thu May 14 17:00:00 IDT 2015
651 | TT_TASK | Submit MS for cross passage construction | Mon Jul 04 08:00:00 IDT 2011 | Mon Aug 01 08:00:00 IDT 2011
652 | TT_TASK | Engineer's review on MS for cross passage construction | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 26 08:00:00 IDT 2011
653 | TT_TASK | Submit TBM MS for commencing the initial drives (X17.1.2) (CS80) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
654 | TT_TASK | Engineer's review on TBM MS for commencing the initial drives | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
655 | TT_TASK | Submit TBM MS for setting out and controlling the tunnel alignment (Survey MS CS21) | Tue May 11 07:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
656 | TT_TASK | Engineer's review on TBM MS for setting out & contolling the tunnel alignment | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
657 | TT_TASK | Submit TBM MS for monitoring ground loss and settlement monitoring (X17.1.6) (CS36) | Tue Nov 30 07:00:00 IST 2010 | Tue Nov 30 07:00:00 IST 2010
658 | TT_TASK | Engineer's review on TBM MS for monitoring ground loss & settlement monitoring | Wed Aug 11 07:00:00 IDT 2010 | Wed Aug 11 07:00:00 IDT 2010
659 | TT_TASK | Submit TBM MS for hyperbaric interventions (X17.1.7) (CS520) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
660 | TT_TASK | Engineer's review on TBM MS for hyperbaric interventions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
661 | TT_TASK | Submit MS for the identification and removal of obstructions (P11.11) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
662 | TT_TASK | Engineer's review on MS for the identification & removal of obstructions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
663 | TT_TASK | Submit TBM MS for tunnelling under sensitive structures (X17.1.10) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
664 | TT_TASK | Engineer's review on TBM MS for tunnelling under sensitive structures | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
665 | TT_TASK | Submit TBM MS for TBM dismantling (X17.1.9) (CS652) | Fri Feb 20 07:00:00 IST 2015 | Wed May 20 17:00:00 IDT 2015
666 | TT_TASK | Engineer's review on TBM MS for TBM dismantling | Thu May 21 07:00:00 IDT 2015 | Wed Jun 17 17:00:00 IDT 2015
667 | TT_TASK | Submit TBM MS for junctions with shafts (X17.1.8) (CS246) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
668 | TT_TASK | Engineer's review on TBM MS for junctions with shafts | Thu Jun 23 07:00:00 IDT 2011 | Wed Jul 20 17:00:00 IDT 2011
669 | TT_TASK | Submit MS for ground freezing works (CS686) | Mon Dec 12 08:00:00 IST 2011 | Fri Feb 10 08:00:00 IST 2012
670 | TT_TASK | Engineer's review on MS for ground freezing work | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 16 08:00:00 IDT 2012
671 | TT_TASK | Submit MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 01 08:00:00 IST 2014
672 | TT_TASK | Engineer's review on MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
673 | TT_TASK | Submit Methods of Construction | Thu May 27 08:00:00 IDT 2010 | Thu Jun 17 08:00:00 IDT 2010
674 | TT_TASK | Engineer's review on Methods of Construction | Fri Jun 18 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
675 | TT_TASK | Submit TBM Spoil Disposal Plan (HK) | Wed Jun 23 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
676 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
677 | TT_TASK | Submit TBM Spoil Disposal Plan (SZ) | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 21 08:00:00 IST 2013
678 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 23 08:00:00 IST 2014
679 | None | Submissions to Government Departments | Sat May 29 08:00:00 IDT 2010 | Tue Jun 03 09:00:00 IDT 2014
680 | TT_TASK | Apply for the initial batch of Frontier Closed Area Permits | Sat May 29 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
681 | TT_TASK | Submit Emergency Rescue proposals and procedures | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
682 | TT_TASK | Engineer's review on Emergency Rescue proposals and procedures | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 28 08:00:00 IST 2013
683 | TT_TASK | Application and obtain approval of Construction Noise Permits | Fri Apr 04 09:00:00 IDT 2014 | Tue Jun 03 09:00:00 IDT 2014
684 | None | Temporary Works Design Submissions | Thu Apr 22 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
685 | TT_TASK | Submit site logistics plans (initial layout) | Thu Apr 22 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
686 | TT_TASK | Engineer's review on site logistics plans (initial layout) | Fri Jul 23 08:00:00 IDT 2010 | Fri Aug 20 08:00:00 IDT 2010
687 | TT_TASK | Submit designs for the Engineer's Office | Mon Jul 12 08:00:00 IDT 2010 | Fri Sep 10 08:00:00 IDT 2010
688 | TT_TASK | Engineer's review on designs for the Engineer's | Mon Aug 23 08:00:00 IDT 2010 | Mon Sep 20 08:00:00 IST 2010
689 | TT_TASK | Submit temporary ventilation system design | Mon Aug 01 08:00:00 IDT 2011 | Fri Sep 30 08:00:00 IDT 2011
690 | TT_TASK | Engineer's review on temporary ventilation syste | Sat Aug 20 08:00:00 IDT 2011 | Sat Sep 17 08:00:00 IDT 2011
691 | None | Design of Permanent Works | Tue Jun 01 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
692 | None | Tunnel Permanent Lining | Tue Jun 01 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
693 | TT_TASK | Submission preparation & ICE checking | Tue Jun 01 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
694 | TT_TASK | Engineer's review | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
695 | TT_TASK | Re-submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Tue Aug 31 08:00:00 IDT 2010
696 | TT_TASK | Engineer's review | Wed Aug 04 08:00:00 IDT 2010 | Wed Sep 01 08:00:00 IDT 2010
697 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
698 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
699 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
700 | None | Permanent Tunnel Lining of Cross Passages | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
701 | None | AIP Submission | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
702 | TT_TASK | Submission preparation | Mon Jun 28 08:00:00 IDT 2010 | Sat Aug 07 08:00:00 IDT 2010
703 | TT_TASK | Engineer's review | Sat Aug 14 08:00:00 IDT 2010 | Sat Sep 11 08:00:00 IDT 2010
704 | TT_TASK | Re-submission preparation | Fri Aug 03 08:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012
705 | TT_TASK | Engineer's review | Mon Sep 03 08:00:00 IDT 2012 | Mon Oct 01 08:00:00 IST 2012
706 | None | Connection between Bored Tunnel and Retrival Shaft | Mon Aug 16 08:00:00 IDT 2010 | Tue Jul 01 08:00:00 IDT 2014
707 | TT_TASK | Submission preparation & ICE checking | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 25 08:00:00 IST 2010
708 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
709 | TT_TASK | Re-submission preparation & ICE checking | Sat Oct 23 08:00:00 IST 2010 | Sun Nov 28 08:00:00 IST 2010
710 | TT_TASK | Engineer's review | Sat Oct 06 08:00:00 IST 2012 | Sat Nov 03 08:00:00 IST 2012
711 | TT_TASK | Submission for RDO/BD consultation | Sun Feb 10 08:00:00 IST 2013 | Sun Mar 10 08:00:00 IST 2013
712 | TT_TASK | Re-submission for RDO/BD consultation | Tue Dec 17 08:00:00 IST 2013 | Tue Jan 14 08:00:00 IST 2014
713 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
714 | None | Junction between Main Tunnel and Cross Passages | Mon Oct 04 08:00:00 IST 2010 | Sun Sep 07 08:00:00 IDT 2014
715 | TT_TASK | Submission preparation & ICE checking | Mon Oct 04 08:00:00 IST 2010 | Tue Nov 23 08:00:00 IST 2010
716 | TT_TASK | Engineer's review | Thu Feb 07 08:00:00 IST 2013 | Thu Mar 07 08:00:00 IST 2013
717 | TT_TASK | Submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
718 | TT_TASK | Re-submission preparation & ICE checking | Tue Jul 01 08:00:00 IDT 2014 | Sun Aug 10 08:00:00 IDT 2014
719 | TT_TASK | Engineer's review | Sun Aug 10 08:00:00 IDT 2014 | Sun Sep 07 08:00:00 IDT 2014
720 | TT_TASK | Re-submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
721 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
722 | None | Design of Temporary Works | Sat May 01 08:00:00 IDT 2010 | Fri Aug 29 08:00:00 IDT 2014
723 | None | Ground Treatment Works for TBM Break-in | Sat May 01 08:00:00 IDT 2010 | Tue Nov 02 08:00:00 IST 2010
724 | TT_TASK | Submission preparation & ICE checking | Sat May 01 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
725 | TT_TASK | Engineer's review | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 12 08:00:00 IDT 2010
726 | TT_TASK | Re-submission preparation & ICE checking | Wed Jun 30 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
727 | TT_TASK | Engineer's review | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
728 | TT_TASK | Submission for RDO/BD consultation | Tue Aug 31 08:00:00 IDT 2010 | Tue Sep 28 08:00:00 IST 2010
729 | TT_TASK | Re-submission for RDO/BD consultation | Tue Oct 05 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
730 | START_MILESTONE | Construction drawings issuance | Tue Nov 02 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
731 | None | Geotechnical Assessment Report | Mon Jun 14 08:00:00 IDT 2010 | Mon Dec 26 08:00:00 IST 2011
732 | TT_TASK | Submission preparation & ICE checking | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010
733 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
734 | TT_TASK | Re-submission preparation & ICE checking | Thu Oct 21 08:00:00 IST 2010 | Fri Nov 05 08:00:00 IST 2010
735 | TT_TASK | Engineer's review | Fri Nov 05 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
736 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
737 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
738 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
739 | None | Groundwater Assessment Report | Mon Jul 26 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
740 | TT_TASK | Submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010
741 | TT_TASK | Engineer's review | Tue Sep 07 08:00:00 IDT 2010 | Tue Oct 05 08:00:00 IST 2010
742 | TT_TASK | Re-submission preparation & ICE checking | Wed Nov 03 08:00:00 IST 2010 | Sun Nov 21 08:00:00 IST 2010
743 | TT_TASK | Engineer's review | Tue Nov 23 08:00:00 IST 2010 | Tue Dec 21 08:00:00 IST 2010
744 | TT_TASK | Submission for RDO/BD consultation | Wed Oct 06 08:00:00 IST 2010 | Wed Nov 03 08:00:00 IST 2010
745 | TT_TASK | Re-submission for RDO/BD consultation | Sat Oct 23 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
746 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
747 | None | Ground Freezing and Temporary Support of Cross Passages | Sat Jan 01 08:00:00 IST 2011 | Fri Aug 29 08:00:00 IDT 2014
748 | TT_TASK | Submission preparation & ICE checking | Sat Jan 01 08:00:00 IST 2011 | Sat Mar 12 08:00:00 IST 2011
749 | TT_TASK | Engineer's review | Fri Nov 25 08:00:00 IST 2011 | Fri Dec 23 08:00:00 IST 2011
750 | TT_TASK | Re-submission preparation & ICE checking | Fri Feb 15 08:00:00 IST 2013 | Mon Apr 01 08:00:00 IDT 2013
751 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
752 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
753 | TT_TASK | Re-submission for RDO/BD consultation | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014
754 | START_MILESTONE | Construction drawings issuance | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014
755 | None | Bulk Head for TBM Removal | Mon May 31 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
756 | TT_TASK | Submission preparation & ICE checking | Mon May 31 08:00:00 IDT 2010 | Mon Aug 09 08:00:00 IDT 2010
757 | TT_TASK | Engineer's review | Fri Jul 30 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
758 | TT_TASK | Re-submission preparation & ICE checking | Thu Aug 12 08:00:00 IDT 2010 | Sun Sep 26 08:00:00 IST 2010
759 | TT_TASK | Engineer's review | Thu Sep 16 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
760 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
761 | None | Prediction of Ground Movement | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
762 | None | Report on the Prediction of Ground Movement and and Assessment on effect of EBS | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
763 | TT_TASK | Submission preparation & ICE checking | Mon Jul 12 08:00:00 IDT 2010 | Tue Aug 17 08:00:00 IDT 2010
764 | TT_TASK | Engineer's review | Sun Aug 22 08:00:00 IDT 2010 | Sun Sep 19 08:00:00 IST 2010
765 | TT_TASK | Re-submission preparation & ICE checking | Wed Sep 29 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
766 | TT_TASK | Engineer's review | Wed Oct 13 08:00:00 IST 2010 | Wed Nov 10 08:00:00 IST 2010
767 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
768 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
769 | START_MILESTONE | Construction drawings issuance | Tue Dec 27 08:00:00 IST 2011 | Tue Dec 27 08:00:00 IST 2011
770 | None | Instrumentation and Montoring Plans | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
771 | None | Instrumentation Plan | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
772 | TT_TASK | Submission preparation & ICE checking | Mon May 03 08:00:00 IDT 2010 | Fri May 28 08:00:00 IDT 2010
773 | TT_TASK | Engineer's review | Tue Jun 08 08:00:00 IDT 2010 | Tue Jul 06 08:00:00 IDT 2010
774 | TT_TASK | Re-submission preparation & ICE checking | Wed Jul 28 08:00:00 IDT 2010 | Sun Aug 15 08:00:00 IDT 2010
775 | TT_TASK | Engineer's review | Tue Aug 10 08:00:00 IDT 2010 | Tue Sep 07 08:00:00 IDT 2010
776 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
777 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
778 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
779 | None | Additional Ground Investigation Plans and Laboratory | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
780 | None | Further GI Plan and Lab Test Schedule | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
781 | TT_TASK | Submission preparation & ICE checking | Tue May 31 08:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011
782 | TT_TASK | Engineer's review | Thu Jul 14 08:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011
783 | TT_TASK | Re-submission preparation & ICE checking | Mon Oct 31 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
784 | TT_TASK | Engineer's review | Sat Nov 19 08:00:00 IST 2011 | Sat Dec 17 08:00:00 IST 2011
785 | TT_TASK | Submission for RDO/BD consultation | Sat Dec 17 08:00:00 IST 2011 | Sat Jan 14 08:00:00 IST 2012
786 | TT_TASK | Re-submission for RDO/BD consultation | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
787 | START_MILESTONE | Construction drawings issuance | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 08:00:00 IST 2013
788 | None | Procurement | Mon Mar 15 08:00:00 IST 2010 | Mon Sep 07 17:00:00 IDT 2015
789 | None | TBM Manufacture and Delivery | Mon Mar 15 08:00:00 IST 2010 | Thu Nov 01 08:00:00 IST 2012
790 | TT_TASK | Confirmation of purchase order on TBM manufacture | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
791 | FINISH_MILESTONE | Submit PO to the Engineer | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
792 | TT_TASK | Shop drawing preparation and submission | Thu Jul 15 08:00:00 IDT 2010 | Wed Aug 04 08:00:00 IDT 2010
793 | TT_TASK | Shop drawing review by the Engineer | Tue Aug 24 08:00:00 IDT 2010 | Tue Sep 21 08:00:00 IST 2010
794 | TT_TASK | Resubmission of shop drawings | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 25 08:00:00 IST 2010
795 | TT_TASK | Engineer's approval of shop drawings | Thu Nov 18 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
796 | TT_TASK | Shop drawings issued for manufacture | Thu Dec 16 08:00:00 IST 2010 | Fri Dec 31 08:00:00 IST 2010
797 | TT_TASK | Manufacturing & purchase parts for TBM #1 | Mon Aug 23 08:00:00 IDT 2010 | Mon Nov 01 08:00:00 IST 2010
798 | TT_TASK | TBM #1 factory preassembly and packing | Thu Oct 07 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
799 | TT_TASK | TBM #1 delivery to workshop | Fri Nov 19 08:00:00 IST 2010 | Sun Dec 19 08:00:00 IST 2010
800 | TT_TASK | TBM #1 workshop assembly | Fri Jan 07 08:00:00 IST 2011 | Fri Mar 18 08:00:00 IST 2011
801 | TT_TASK | TBM #1 test runs, acceptance, dis-assembly and p | Mon May 16 08:00:00 IDT 2011 | Wed Jun 15 08:00:00 IDT 2011
802 | TT_TASK | TBM #1 delivery to Shenzhen | Wed May 25 08:00:00 IDT 2011 | Sat Jun 04 08:00:00 IDT 2011
803 | FINISH_MILESTONE | TBM #1 delivery to HGP shaft | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
804 | TT_TASK | TBM #1 on-site assembly, T&C @ HGP Shaft | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
805 | TT_TASK | TBM #1 free walk-thru to commencement position | Fri Apr 27 08:00:00 IDT 2012 | Thu May 17 08:00:00 IDT 2012
806 | FINISH_MILESTONE | TBM #1 ready to commence drive at HGP by GSG Contractor | Wed Jul 04 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
807 | TT_TASK | Manufacturing & purchase parts for TBM #2 | Thu Dec 16 08:00:00 IST 2010 | Thu Feb 24 08:00:00 IST 2011
808 | TT_TASK | TBM #2 factory preassembly and packing | Mon Feb 14 08:00:00 IST 2011 | Mon Apr 25 08:00:00 IDT 2011
809 | TT_TASK | TBM #2 delivery to workshop | Sat Mar 05 08:00:00 IST 2011 | Mon Apr 04 08:00:00 IDT 2011
810 | TT_TASK | TBM #2 workshop assembly | Mon May 30 08:00:00 IDT 2011 | Mon Aug 08 08:00:00 IDT 2011
811 | TT_TASK | TBM #2 test runs, acceptance, dis-assembly and p | Mon Aug 22 08:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011
812 | TT_TASK | TBM #2 delivery to temporary storage at Nansha | Mon Sep 19 08:00:00 IDT 2011 | Thu Sep 22 08:00:00 IDT 2011
813 | TT_TASK | TBM #2 delivery to Shenzhen | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
814 | FINISH_MILESTONE | TBM #2 delivery to HGP shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
815 | TT_TASK | TBM #2 on-site assembly, T&C @ HGP Shaft | Thu Apr 05 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
816 | TT_TASK | TBM #2 free walk-thru to commencement position | Mon Oct 01 08:00:00 IST 2012 | Sun Oct 21 08:00:00 IST 2012
817 | FINISH_MILESTONE | TBM #2 ready to commence drive at HGP by GSG Con | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012
818 | None | TBM Ground Support Equipment | Thu Jul 08 08:00:00 IDT 2010 | Mon Nov 05 08:00:00 IST 2012
819 | TT_TASK | Confirm order for slurry treatment plant (STP) | Thu Jul 08 08:00:00 IDT 2010 | Thu Jul 15 08:00:00 IDT 2010
820 | TT_TASK | STP shop drawing preparation and submission | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010
821 | TT_TASK | STP shop drawing review by the Engineer | Wed Dec 01 08:00:00 IST 2010 | Wed Dec 29 08:00:00 IST 2010
822 | TT_TASK | STP procurement of components and materials | Thu Dec 09 08:00:00 IST 2010 | Sun Jan 23 08:00:00 IST 2011
823 | TT_TASK | STP resubmission of shop drawings | Mon Jan 10 08:00:00 IST 2011 | Mon Jan 24 08:00:00 IST 2011
824 | TT_TASK | STP Engineer's approval of shop drawings | Tue Apr 05 08:00:00 IDT 2011 | Tue May 03 08:00:00 IDT 2011
825 | TT_TASK | STP shop drawings issued for manufacture | Mon Mar 14 08:00:00 IST 2011 | Mon Mar 21 08:00:00 IST 2011
826 | TT_TASK | STP sub-unit assembly | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 08:00:00 IDT 2011
827 | TT_TASK | STP final assembly at factory | Wed Mar 23 08:00:00 IST 2011 | Sat Apr 02 08:00:00 IDT 2011
828 | TT_TASK | STP factory testing | Wed Mar 30 08:00:00 IST 2011 | Sat Apr 09 08:00:00 IDT 2011
829 | TT_TASK | STP packaging and transportation to docks | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 15 08:00:00 IDT 2011
830 | TT_TASK | STP shipping to Shenzhen, customs clearance and forwarding | Mon Apr 04 08:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011
831 | FINISH_MILESTONE | STP delivery to HGP works area | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 12 08:00:00 IDT 2011
832 | TT_TASK | STP on-site assembly | Wed Sep 28 08:00:00 IDT 2011 | Sat Oct 22 08:00:00 IST 2011
833 | TT_TASK | STP on-site self testing and commissioning | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 08:00:00 IST 2012
834 | TT_TASK | STP on-site testing and commissioning with TBM#1 | Mon Jun 18 08:00:00 IDT 2012 | Fri Jun 29 08:00:00 IDT 2012
835 | TT_TASK | STP on-site testing and commissioning with TBM#2 | Wed Oct 03 08:00:00 IST 2012 | Sun Oct 14 08:00:00 IST 2012
836 | FINISH_MILESTONE | STP ready to commence operations for TBM #1 | Mon Jun 18 08:00:00 IDT 2012 | Mon Jun 18 08:00:00 IDT 2012
837 | FINISH_MILESTONE | STP ready to commence operations for TBM #2 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
838 | None | Tunnel Lining Segments | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 07 17:00:00 IDT 2015
839 | START_MILESTONE | Confirmation of purchase order on segment manufacturer | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
840 | TT_TASK | Shop drawings issued for manufacture | Mon Aug 29 08:00:00 IDT 2011 | Sat Sep 10 08:00:00 IDT 2011
841 | TT_TASK | Pre-casting trials | Thu Nov 03 08:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011
842 | TT_TASK | Engineer's approval of trial segments | Thu Dec 15 08:00:00 IST 2011 | Thu Jan 12 08:00:00 IST 2012
843 | TT_TASK | Manufacture 926 Tunnel Rings (SZ) | Wed Feb 01 08:00:00 IST 2012 | Fri Jul 20 08:00:00 IDT 2012
844 | TT_TASK | Manufacture 163 Tunnel Rings (SZ) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 25 08:00:00 IST 2012
845 | TT_TASK | Manufacture 105 Tunnel Rings (SZ) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012
846 | TT_TASK | Manufacture 98 Tunnel Rings (SZ) | Wed Oct 31 08:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012
847 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 26 08:00:00 IST 2012
848 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sun Jan 13 08:00:00 IST 2013 | Thu Feb 07 08:00:00 IST 2013
849 | TT_TASK | Manufacture 60 Tunnel Rings (SZ) | Sun Feb 24 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013
850 | TT_TASK | Manufacture 81 Tunnel Rings (HK) | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 08:00:00 IDT 2013
851 | TT_TASK | Manufacture 76 Tunnel Rings (HK) | Sun Jun 30 08:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013
852 | TT_TASK | Manufacture 75 Tunnel Rings (HK) | Mon Jul 01 08:00:00 IDT 2013 | Fri Jul 26 08:00:00 IDT 2013
853 | TT_TASK | Manufacture 88 Tunnel Rings (HK) | Thu Aug 01 08:00:00 IDT 2013 | Sun Aug 25 08:00:00 IDT 2013
854 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Sun Sep 01 08:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013
855 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Fri Jan 24 08:00:00 IST 2014
856 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
857 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
858 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Jul 01 08:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014
859 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014
860 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
861 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Mon Feb 16 07:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
862 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Mar 03 07:00:00 IST 2015 | Fri Mar 27 17:00:00 IDT 2015
863 | TT_TASK | Manufacture 60 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Sat May 02 17:00:00 IDT 2015
864 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Fri May 15 17:00:00 IDT 2015
865 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Sun Aug 09 07:00:00 IDT 2015 | Wed Sep 02 17:00:00 IDT 2015
866 | TT_TASK | Manufacture 10 Tunnel Rings (HK) | Thu Sep 03 07:00:00 IDT 2015 | Mon Sep 07 17:00:00 IDT 2015
867 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (SZ rings) | Wed Aug 01 08:00:00 IDT 2012 | Wed Dec 26 08:00:00 IST 2012
868 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (HK rings) | Sat Nov 30 08:00:00 IST 2013 | Sun Oct 12 08:00:00 IDT 2014
869 | None | Segment Mould Design, Fabrication and Delivery | Mon May 16 08:00:00 IDT 2011 | Wed Feb 15 08:00:00 IST 2012
870 | START_MILESTONE | Confirm order for moulds | Mon May 16 08:00:00 IDT 2011 | Mon May 16 08:00:00 IDT 2011
871 | TT_TASK | Design and planning | Mon May 16 08:00:00 IDT 2011 | Thu Jun 09 08:00:00 IDT 2011
872 | TT_TASK | Design mould drawings for manufacture | Fri Jul 08 08:00:00 IDT 2011 | Sun Aug 07 08:00:00 IDT 2011
873 | TT_TASK | Materials procurement | Fri Jul 08 08:00:00 IDT 2011 | Thu Jul 28 08:00:00 IDT 2011
874 | TT_TASK | Factory assembly | Mon Jul 18 08:00:00 IDT 2011 | Fri Sep 16 08:00:00 IDT 2011
875 | TT_TASK | Shipping and delivery to Shenzhen - 1st batch (3 sets) | Sat Nov 05 08:00:00 IST 2011 | Thu Nov 10 08:00:00 IST 2011
876 | TT_TASK | Shipping and delivery to Shenzhen - 2nd batch (3 sets) | Fri Feb 10 08:00:00 IST 2012 | Wed Feb 15 08:00:00 IST 2012
877 | TT_TASK | Mould erection and commissioning ready for production in precast yard | Thu Nov 10 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
878 | None | Other Procurement Items | Tue Nov 02 08:00:00 IST 2010 | Sun Apr 06 08:00:00 IDT 2014
879 | TT_TASK | Transformer and substation procurement | Tue May 31 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
880 | TT_TASK | Procure temporary electrics subcontractor | Wed Jun 01 08:00:00 IDT 2011 | Fri Jul 01 08:00:00 IDT 2011
881 | TT_TASK | Place order for ready mixed concrete | Fri Mar 01 08:00:00 IST 2013 | Sat Apr 06 08:00:00 IDT 2013
882 | TT_TASK | Procure other major construction plant and equip | Tue Mar 01 08:00:00 IST 2011 | Mon May 30 08:00:00 IDT 2011
883 | TT_TASK | Place order for rebar supply | Mon Oct 31 08:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011
884 | TT_TASK | Rental agreement for off site office accommodation | Tue Nov 02 08:00:00 IST 2010 | Thu Dec 02 08:00:00 IST 2010
885 | TT_TASK | Procure tunnel personnel electronic tagging system | Sat Nov 30 08:00:00 IST 2013 | Sat Jan 11 08:00:00 IST 2014
886 | TT_TASK | Procure tunnel ventilation system | Thu Mar 01 08:00:00 IST 2012 | Tue Apr 10 08:00:00 IDT 2012
887 | TT_TASK | Procure ground freezing specialist subcontractor | Sat Mar 01 08:00:00 IST 2014 | Sun Apr 06 08:00:00 IDT 2014
888 | None | Site Mobilisation | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
889 | TT_TASK | Initial project staff assignments | Mon Mar 15 08:00:00 IST 2010 | Sun Jun 13 08:00:00 IDT 2010
890 | TT_TASK | Establish Works Areas at HGP | Wed Dec 01 08:00:00 IST 2010 | Tue Jan 18 08:00:00 IST 2011
891 | TT_TASK | Establish Works Areas at MPV | Fri Feb 01 08:00:00 IST 2013 | Sat Mar 09 08:00:00 IST 2013
892 | TT_TASK | Establish and operate Project Office in Hong Kong | Thu Apr 22 08:00:00 IDT 2010 | Fri Feb 18 08:00:00 IST 2011
893 | TT_TASK | Establish and operate Project Office in Shenzhen | Mon Jan 10 08:00:00 IST 2011 | Sat Oct 01 08:00:00 IDT 2016
894 | TT_TASK | Establish and operate Project Office in Mai Po | Tue Mar 15 08:00:00 IST 2011 | Fri Jul 25 08:00:00 IDT 2014
895 | START_MILESTONE | Commencement to operate compound at Mai Po, Area 1.19, for DLP | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
1 | None | 826 As-built Programme | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
2 | None | 826 - HGP to Mai Po Tunnels, Revised Master Prog | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
3 | None | Tender and Contract Details | Wed Mar 10 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
4 | None | Tender Actions | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
5 | START_MILESTONE | Contract Award (LoA) | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
6 | None | Critical Contract Dates | Mon Mar 15 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
7 | START_MILESTONE | Stated Contract Commencement Date (Cl 64) | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 15 08:00:00 IST 2010
8 | FINISH_MILESTONE | Table 3, Ref 3A - Delivery of the first TBM to HGP | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
9 | FINISH_MILESTONE | Table 3, Ref 3B - All works in Works Area 1.6 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
10 | FINISH_MILESTONE | Table 3, Ref 3C - Delivery of the second TBM to HGP | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
11 | FINISH_MILESTONE | Table 4, Ref 4A - Achieve Deg. 1 for both Up and Down Track Tunnels | Thu Mar 31 17:00:00 IDT 2016 | Thu Mar 31 17:00:00 IDT 2016
12 | FINISH_MILESTONE | Table 1 - Completion of the Whole of the Works (wk13/2015) | Thu Jun 01 17:00:00 IDT 2017 | Thu Jun 01 17:00:00 IDT 2017
13 | None | Other Programme Data | Thu May 09 08:00:00 IDT 2013 | Sat Apr 01 07:00:00 IDT 2017
14 | START_MILESTONE | GSG Contractor to hand over S623 to Cont' 826 at HK Boundary | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013
15 | START_MILESTONE | GSG Contractor to hand over S624 to Cont' 826 at HK Boundary | Thu May 09 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
16 | START_MILESTONE | Notification to Contract 846 for cable bracket installation | Sun Nov 22 07:00:00 IST 2015 | Sun Nov 22 07:00:00 IST 2015
17 | FINISH_MILESTONE | Provision of TBM Retrieval Shaft at MPV | Wed Oct 01 07:00:00 IDT 2014 | Wed Oct 01 07:00:00 IDT 2014
18 | START_MILESTONE | OHL Power On, by Designated Contractor 830 | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
19 | None | Access Dates for Designated Contractors | Sun May 01 07:00:00 IDT 2016 | Thu Dec 01 07:00:00 IST 2016
20 | START_MILESTONE | 827, X-passage Doors - Door Frame Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
21 | START_MILESTONE | 827, X-passage Doors - Doors Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
22 | START_MILESTONE | 830, Trackwork and OHL - Up-track | Sun May 01 07:00:00 IDT 2016 | Sun May 01 07:00:00 IDT 2016
23 | START_MILESTONE | 830, Trackwork and OHL - Down-track | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
24 | START_MILESTONE | 841A, Signalling System, Trackside Eqpt - Both tunnels | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
25 | START_MILESTONE | 846, Trackside Aux - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
26 | START_MILESTONE | 849, Radio Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
27 | START_MILESTONE | 850, Passenger Mobile Communications Systems - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
28 | START_MILESTONE | 851, Fixed Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
29 | START_MILESTONE | 8203, Constrn Stage Mobile Phone Network - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
30 | None | Interface Contractor Programme - GSG | Wed Dec 01 08:00:00 IST 2010 | Sat Mar 01 07:00:00 IST 2014
31 | FINISH_MILESTONE | Complete Huanggang Park shaft construction | Mon Mar 26 08:00:00 IST 2012 | Mon Mar 26 08:00:00 IST 2012
32 | TT_TASK | Drill & Blast Tunnel (to HK) | Wed Dec 01 08:00:00 IST 2010 | Tue Sep 27 08:00:00 IDT 2011
33 | TT_TASK | S623 Excavate 242m (SZ) (s.rock) | Tue Jul 03 08:00:00 IDT 2012 | Sat Oct 06 08:00:00 IST 2012
34 | TT_TASK | S623 Conduct General Maintenance | Sun Oct 07 08:00:00 IST 2012 | Wed Oct 10 08:00:00 IST 2012
35 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 484m) | Wed Oct 10 08:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012
36 | TT_TASK | S623 Conduct General Maintenance | Sun Nov 18 08:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012
37 | TT_TASK | S623 Excavate 220m (SZ) (s.rock/total 704m) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 29 08:00:00 IST 2012
38 | TT_TASK | S623 Conduct General Maintenance | Tue Jan 08 08:00:00 IST 2013 | Sat Jan 12 08:00:00 IST 2013
39 | TT_TASK | S623 Excavate 150m (SZ) (m.rock/total 854m) | Sat Jan 12 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
40 | TT_TASK | S623 Conduct General Maintenance | Wed Feb 20 08:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013
41 | TT_TASK | S623 Excavate 50m (SZ) (s.rock/total 904m) | Thu Feb 28 08:00:00 IST 2013 | Fri Mar 08 08:00:00 IST 2013
42 | TT_TASK | S623 Conduct General Maintenance | Sun Apr 21 08:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013
43 | TT_TASK | S623 Excavate 100m (SZ) (rock/total 1004m) | Mon Apr 22 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
44 | TT_TASK | S623 Conduct General Maintenance | Sat Jun 08 10:38:00 IDT 2013 | Mon Jun 10 10:38:00 IDT 2013
45 | TT_TASK | S623 Excavate 470m (SZ) (rock/total 1474m) | Wed May 15 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
46 | TT_TASK | S623 Conduct General Maintenance | Fri Sep 13 08:00:00 IDT 2013 | Sun Sep 15 08:00:00 IDT 2013
47 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Aug 15 08:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013
48 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013
49 | TT_TASK | S623 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Oct 31 08:00:00 IST 2013 | Sun Nov 10 08:00:00 IST 2013
50 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013
51 | TT_TASK | S623 Excavate 84m (SZ) (c.rock/total 1856m) | Thu Oct 31 08:00:00 IST 2013 | Sat Nov 02 08:00:00 IST 2013
52 | FINISH_MILESTONE | Complete TBM Excavation Down Track (SZ) | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 08:00:00 IST 2013
53 | TT_TASK | S624 Excavate 100m (SZ) (s.rock) | Mon Nov 05 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
54 | TT_TASK | S624 Conduct General Maintenance | Mon Dec 10 08:00:00 IST 2012 | Thu Dec 13 08:00:00 IST 2012
55 | TT_TASK | S624 Excavate 142m (SZ) (s.rock/total 242m) | Thu Dec 13 08:00:00 IST 2012 | Sun Jan 06 08:00:00 IST 2013
56 | TT_TASK | S624 Conduct General Maintenance | Sat Jan 05 08:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013
57 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 484m) | Tue Jan 08 08:00:00 IST 2013 | Sun Feb 17 08:00:00 IST 2013
58 | TT_TASK | S624 Conduct General Maintenance | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 08:00:00 IST 2013
59 | TT_TASK | S624 Excavate 220m (SZ) (s.rock/total 704m) | Tue Feb 19 08:00:00 IST 2013 | Thu Mar 28 08:00:00 IST 2013
60 | TT_TASK | S624 Conduct General Maintenance | Fri Jun 28 08:58:00 IDT 2013 | Mon Jul 01 08:58:00 IDT 2013
61 | TT_TASK | S624 Excavate 150m (SZ) (m.rock/total 854m) | Tue Jul 02 08:58:00 IDT 2013 | Mon Jul 22 08:58:00 IDT 2013
62 | TT_TASK | S624 Conduct General Maintenance | Wed Jul 24 08:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013
63 | TT_TASK | S624 Excavate 50m (SZ) (s.rock/total 904m) | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
64 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 08:00:00 IDT 2013
65 | TT_TASK | S624 Excavate 100m (SZ) (s/m.rock/total 1004m) | Tue Aug 06 08:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013
66 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 26 08:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013
67 | TT_TASK | S624 Excavate 470m (SZ) (s/m.rock/total 1474m) | Fri Sep 13 08:00:00 IDT 2013 | Sun Dec 01 08:00:00 IST 2013
68 | TT_TASK | S624 Conduct General Maintenance | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
69 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Jan 30 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
70 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
71 | TT_TASK | S624 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Jan 30 08:00:00 IST 2014 | Sun Feb 09 08:00:00 IST 2014
72 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
73 | TT_TASK | S624 Excavate 92m (SZ) (c.rock/total 1864m) | Thu Jan 30 08:00:00 IST 2014 | Tue Feb 11 08:00:00 IST 2014
74 | FINISH_MILESTONE | Complete TBM Excavation Up Track (SZ) | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
75 | None | Interface Contractor Programme - 825 | Tue Sep 21 08:00:00 IST 2010 | Thu Dec 01 07:00:00 IST 2016
76 | FINISH_MILESTONE | TBM shaft for Contract 826 within Works Area 1.5 | Tue Jun 09 11:00:00 IDT 2015 | Tue Jun 09 11:00:00 IDT 2015
77 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - first time | Tue Sep 21 08:00:00 IST 2010 | Tue Sep 21 08:00:00 IST 2010
78 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - second time | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
79 | TT_TASK | Cut & cover tunnel Bay 1 tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 20 08:00:00 IST 2014
80 | TT_TASK | Cut & cover tunnel Bay 2 tunnel construction | Sat Nov 30 08:00:00 IST 2013 | Mon Feb 17 08:00:00 IST 2014
81 | FINISH_MILESTONE | 826 to complete all works at interface and allow 825 access | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
82 | TT_TASK | 825 complete stitch joint to 826 tunnel | Sun May 01 07:00:00 IDT 2016 | Sat Jun 25 17:00:00 IDT 2016
83 | FINISH_MILESTONE | Return of Works Area 1.5 to 825 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
84 | None | Interface Contractor Programme - 830 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
85 | TT_TASK | Allow concrete pumping access for Contract 830 within Works Area 1.5 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
86 | None | Works Areas | Mon Sep 20 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
87 | None | Access Dates | Mon Sep 20 08:00:00 IST 2010 | Thu Nov 05 07:00:00 IST 2015
88 | START_MILESTONE | Works Area 1.3 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
89 | START_MILESTONE | Works Area 1.4A (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
90 | START_MILESTONE | Works Area 1.4B first time (36/2010, 13 Sep 10) | Mon Sep 20 08:00:00 IST 2010 | Mon Sep 20 08:00:00 IST 2010
91 | START_MILESTONE | Works Area 1.4B second time (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
92 | START_MILESTONE | Works Area 1.5 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
93 | START_MILESTONE | Works Area 1.6 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
94 | START_MILESTONE | Works Area 1.16 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
95 | START_MILESTONE | Works Area 1.17 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
96 | START_MILESTONE | Works Area 1.19 (47/2010, 29 Nov 10) | Mon Nov 29 08:00:00 IST 2010 | Mon Nov 29 08:00:00 IST 2010
97 | START_MILESTONE | Works Area 1.21 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
98 | None | Return Dates | Fri Dec 17 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
99 | FINISH_MILESTONE | Works Area 1.3 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
100 | FINISH_MILESTONE | Works Area 1.4A (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
101 | FINISH_MILESTONE | Works Area 1.4B first time (01/2011, 9 Jan 11) | Fri Dec 17 08:00:00 IST 2010 | Fri Dec 17 08:00:00 IST 2010
102 | FINISH_MILESTONE | Works Area 1.4B second time (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
103 | FINISH_MILESTONE | Works Area 1.5 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
104 | FINISH_MILESTONE | Works Area 1.6 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
105 | FINISH_MILESTONE | Works Area 1.16 (36/2013, 8 Sep 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
106 | FINISH_MILESTONE | Works Area 1.17 (50/2013, 15 Dec 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
107 | FINISH_MILESTONE | Works Area 1.19 (10 May 16) | Tue Feb 28 17:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017
108 | FINISH_MILESTONE | Works Area 1.21 (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
109 | None | Specified Milestone Dates | Sun Apr 25 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
110 | None | Cost Centre A | Sun Jun 27 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
111 | FINISH_MILESTONE | A1 (25/2010, 27 Jun 10) - Contractor's Submissions | Sun Jun 27 08:00:00 IDT 2010 | Sun Jun 27 08:00:00 IDT 2010
112 | FINISH_MILESTONE | A2 (51/2010, 26 Dec 10) - Approval of TBM Tunnelling method Statement | Wed Jan 05 08:00:00 IST 2011 | Wed Jan 05 08:00:00 IST 2011
113 | FINISH_MILESTONE | A3 (08/2011, 27 Feb 11) - Implementation of Specified Plans and Programming | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
114 | FINISH_MILESTONE | A4 (38/2011, 25 Sep 11) - Delivery of 2 nos. TBM to HGP Launching Shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
115 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of the MS of Construction of Cross Passages | Thu Feb 23 08:00:00 IST 2012 | Thu Feb 23 08:00:00 IST 2012
116 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of Detailed Interface Require Specific with Designated Contractor | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
117 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Implementation of Specified Plans | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
118 | FINISH_MILESTONE | A6 (08/2012, 26 Feb 12) - Implementation of Specified Plans and Programme | Fri Feb 24 08:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012
119 | FINISH_MILESTONE | A7 (25/2012, 24 Jun 12) - Approval of Detailed Interface Require Specific with Designated Contractor | Tue Jul 31 08:00:00 IDT 2012 | Tue Jul 31 08:00:00 IDT 2012
120 | FINISH_MILESTONE | A8 (34/2012, 26 Aug 12) - Implementation of Specified Plans | Wed Aug 22 08:00:00 IDT 2012 | Wed Aug 22 08:00:00 IDT 2012
121 | FINISH_MILESTONE | *A9 (48/2014, 30 Nov 14) - Complete 28% of the 1st tunnel drive | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 01 07:00:00 IST 2014
122 | FINISH_MILESTONE | A9a (08/2013, 24 Feb 13) - Implementation of Specific Plans and Program | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
123 | FINISH_MILESTONE | *A9b (08/2014, 1 May 14) - Complete 15% of the 1st tunnel drive | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
124 | FINISH_MILESTONE | A10 (34/2013, 25 Aug 13) - Implementation of Specific Plans | Tue Jul 15 17:00:00 IDT 2014 | Tue Jul 15 17:00:00 IDT 2014
125 | FINISH_MILESTONE | *A11 (51/2015, 27 Dec 15) - Achieve Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
126 | FINISH_MILESTONE | A12 (32/2014, 10 Aug 14) - Approval of Draft O & M Manuals and Draft As-built drawings | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
127 | FINISH_MILESTONE | A13 (06/2015, 8 Feb 15) - Approval of Operating & Maintenance Mauls | Fri Feb 24 17:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017
128 | None | Cost Centre B | Sun Apr 25 08:00:00 IDT 2010 | Fri Apr 01 07:00:00 IDT 2016
129 | FINISH_MILESTONE | B1.1 (16/2010, 25 Apr 10) - Provide Evidence that TBM | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
130 | FINISH_MILESTONE | B1a (25/2010, 27 Jun 10) - On-demand bond or bank guarantee | Sat Jun 26 08:00:00 IDT 2010 | Sat Jun 26 08:00:00 IDT 2010
131 | FINISH_MILESTONE | B1.2 (28/2010, 18 Jul 10) - Provide Evidence that the STP | Thu Jul 29 08:00:00 IDT 2010 | Thu Jul 29 08:00:00 IDT 2010
132 | FINISH_MILESTONE | B2 (21/2011, 29 May 11) - Delivery of the 1st TBM | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
133 | FINISH_MILESTONE | B2a (38/2011, 25 Sep 11) - Delivery of the 2nd TBM | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
134 | FINISH_MILESTONE | B3 (49/2013, 8 Dec 13) - Complete Final Disassembly of TBM | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
135 | None | Cost Centre C (UT/S624) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
136 | FINISH_MILESTONE | C1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
137 | FINISH_MILESTONE | *C2 (17/2014, 27 Apr 14) - Complete 10% Tunnel Drive & 70% Segments | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
138 | FINISH_MILESTONE | *C3 (52/2014, 28 Dec 14) - Complete 40% Tunnel Drive & 95% Segments | Mon Feb 23 07:00:00 IST 2015 | Mon Feb 23 07:00:00 IST 2015
139 | FINISH_MILESTONE | *C4 (26/2015, 28 Jun 15) - Complete 100% Tunnel Drive | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
140 | FINISH_MILESTONE | *C5 (35/2015, 30 Aug 15) -Complete 50% Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
141 | FINISH_MILESTONE | *C6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
142 | FINISH_MILESTONE | C7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
143 | None | Cost Centre D (DT/S623) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
144 | FINISH_MILESTONE | D1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
145 | FINISH_MILESTONE | D2 (10/2013, 10MAR13) - Complete 5% Tunnel Drive & 40% Segments | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
146 | FINISH_MILESTONE | *D3 (48/2014, 30 Nov 14) -Complete 28% Tunnel Drive & 85% Segments | Tue Jun 30 07:00:00 IDT 2015 | Tue Jun 30 07:00:00 IDT 2015
147 | FINISH_MILESTONE | *D4 (35/2015, 30 Aug 15) -Complete 100% Tunnel Drive | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
148 | FINISH_MILESTONE | *D5 (43/2015, 25 Oct 15) - Complete 50% of Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
149 | FINISH_MILESTONE | *D6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
150 | FINISH_MILESTONE | D7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
151 | None | Cost Centre E (CP) | Thu Dec 16 08:00:00 IST 2010 | Sat Dec 31 17:00:00 IST 2016
152 | FINISH_MILESTONE | E1 (01/2011, 9 Jan 11) - Complete Ground Treatment | Thu Dec 16 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
153 | FINISH_MILESTONE | E2 (08/2011, 27 Feb 11) - Submit instrumentation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
154 | FINISH_MILESTONE | E3 (34/2011, 28 Aug 11) - Submit instrumentation | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
155 | FINISH_MILESTONE | E4 (08/2012, 26 Feb 12) - Submit instrumentation | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 08:00:00 IST 2012
156 | FINISH_MILESTONE | E5 (34/2012, 26 Aug 12) - Submit instrumentation | Sat Aug 25 08:00:00 IDT 2012 | Sat Aug 25 08:00:00 IDT 2012
157 | FINISH_MILESTONE | E6 (08/2013, 24 Feb 13) - Submit instrumentation | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
158 | FINISH_MILESTONE | E7 (48/2013, 30 Nov 13) - Major ground treatment plant for CPs | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 01 07:00:00 IST 2015
159 | FINISH_MILESTONE | E8 (13/2015, 29 Mar 15) - Complete 4 Cross Passage Ground Treatment | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
160 | FINISH_MILESTONE | *E9 (51/2015, 20 Dec 15) - Deg 1 Completion in Cross Passage | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
161 | FINISH_MILESTONE | E10 (25/2016) - All Works Complete | Sat Dec 31 17:00:00 IST 2016 | Sat Dec 31 17:00:00 IST 2016
162 | None | Construction and Site Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
163 | None | Surface Operations in Works Areas | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
164 | None | Huanggang Park | Tue Nov 02 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
165 | TT_TASK | Establish MTRC Project Office in Shenzhen | Tue Nov 02 08:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010
166 | TT_TASK | Establish 826 HGP Site Office | Tue Nov 30 08:00:00 IST 2010 | Mon Jan 17 08:00:00 IST 2011
167 | TT_TASK | University Games Period | Mon Aug 01 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
168 | TT_TASK | Operation and maintenance of ground support facilities during tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Tue Oct 31 08:00:00 IST 2017
169 | None | Mai Po Retrieval Shaft | Fri Aug 06 08:00:00 IDT 2010 | Tue Apr 21 08:00:00 IDT 2015
170 | None | Ground Treatment Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Feb 01 08:00:00 IST 2011
171 | FINISH_MILESTONE | Submit Inspection and Testing Plan for ground treatment works | Fri Aug 06 08:00:00 IDT 2010 | Fri Aug 06 08:00:00 IDT 2010
172 | TT_TASK | Engineer's review on Inspection and Testing Plan | Fri Aug 06 08:00:00 IDT 2010 | Fri Sep 03 08:00:00 IDT 2010
173 | TT_TASK | Establish Works Area 1.4B with 825 Contractor | Mon Sep 20 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
174 | TT_TASK | Set up grouting plant | Tue Oct 05 08:00:00 IST 2010 | Fri Oct 15 08:00:00 IST 2010
175 | TT_TASK | Drilling - Down Track tunnel | Thu Oct 07 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
176 | TT_TASK | Drilling - Up Track tunnel | Mon Oct 18 08:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010
177 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 04 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
178 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 11 08:00:00 IST 2010 | Sat Nov 27 08:00:00 IST 2010
179 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
180 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
181 | TT_TASK | Permeability testing - Down Track tunnel | Tue Dec 07 08:00:00 IST 2010 | Mon Dec 13 08:00:00 IST 2010
182 | TT_TASK | Permeability testing - Up Track tunnel | Wed Dec 08 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
183 | TT_TASK | Demobilise grout plant | Mon Dec 13 08:00:00 IST 2010 | Sat Dec 18 08:00:00 IST 2010
184 | TT_TASK | Clear Works Area 1.4B for 825 Contractor's D.Wall | Mon Dec 13 08:00:00 IST 2010 | Wed Dec 22 08:00:00 IST 2010
185 | TT_TASK | Install instrumentation and monitoring equipment | Thu Oct 28 08:00:00 IST 2010 | Tue Feb 01 08:00:00 IST 2011
186 | None | Jet Grouting Works for TBM Break-out | Tue Dec 31 08:00:00 IST 2013 | Tue Nov 18 08:00:00 IST 2014
187 | TT_TASK | Submit Method Statement for Jet Grouting Works | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 27 08:00:00 IST 2014
188 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
189 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 22 08:00:00 IST 2014
190 | TT_TASK | Trial of Jet grouting | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 27 08:00:00 IST 2014
191 | TT_TASK | Jet Grouting Works | Fri Jul 18 08:00:00 IDT 2014 | Tue Nov 18 08:00:00 IST 2014
192 | None | Ground Freezing Plant | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
193 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Ground freezing | Tue Mar 24 08:00:00 IST 2015 | Tue Mar 24 08:00:00 IST 2015
194 | TT_TASK | Engineer's review on Inspection and Testing Plan | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
195 | None | TBM Drives from Boundary to Mai Po Shaft | Fri May 10 08:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
196 | None | Down Track - Ch.115+929 to Ch.117+400 | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 16 17:00:00 IST 2015
197 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
198 | TT_TASK | Continue S623 drive, ch. 115+929 to ch. 115+950 in soil | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013
199 | TT_TASK | Continue S623 drive, ch. 115+950 to ch. 115+983 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Sat Jan 04 08:00:00 IST 2014
200 | TT_TASK | Continue S623 drive, ch. 115+983 to ch. 116+050 in soil | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 08 08:00:00 IST 2014
201 | TT_TASK | Continue S623 drive, ch. 116+050 to ch. 116+213 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
202 | TT_TASK | Continue S623 drive, ch. 116+213 to ch. 116+230 in soil | Tue Apr 01 08:00:00 IDT 2014 | Thu Apr 03 08:00:00 IDT 2014
203 | TT_TASK | Continue S623 drive, ch. 116+230 to ch. 116+260 in marble | Tue Apr 01 08:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014
204 | TT_TASK | Continue S623 drive, ch. 116+260 to ch. 116+284 in marble | Tue Jul 01 08:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014
205 | TT_TASK | TBM Cutter Head Repair & S624 Overtaking Stoppage | Fri Aug 01 08:00:00 IDT 2014 | Fri Oct 24 08:00:00 IDT 2014
206 | TT_TASK | Continue S623 drive, ch. 116+284 to ch. 116+319 in marble | Fri Nov 21 07:00:00 IST 2014 | Mon Dec 01 17:00:00 IST 2014
207 | TT_TASK | Continue S623 drive, ch. 116+319 to ch. 116+349 in marble | Wed Feb 04 07:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
208 | TT_TASK | Continue S623 drive, ch. 116+349 to ch. 116+379 in marble | Sun Feb 01 07:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
209 | TT_TASK | Continue S623 drive, ch. 116+379 to ch. 116+408 in marble | Sun Mar 01 07:00:00 IST 2015 | Thu Mar 05 01:00:00 IST 2015
210 | TT_TASK | Continue S623 drive, ch. 116+408 to ch. 116+430 in marble | Sun Mar 01 07:00:00 IST 2015 | Sat Mar 07 17:00:00 IST 2015
211 | TT_TASK | Continue S623 drive, ch. 116+430 to ch. 116+600 in soil | Sun Mar 01 07:00:00 IST 2015 | Mon Mar 30 17:00:00 IDT 2015
212 | TT_TASK | Continue S623 drive, ch. 116+600 to ch. 116+694 in soil | Fri Jul 17 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
213 | TT_TASK | Continue S623 drive, ch. 116+694 to ch. 116+927 in Alluvial zone | Tue Jun 30 07:00:00 IDT 2015 | Thu Sep 17 17:00:00 IDT 2015
214 | TT_TASK | Continue S623 drive, ch. 116+927 to ch. 116+945 in soil | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
215 | TT_TASK | Continue S623 drive, ch. 116+945 to ch. 117+400 in soil | Tue Sep 29 07:00:00 IDT 2015 | Wed Dec 16 17:00:00 IST 2015
216 | TT_TASK | Pre-coring at diaphragm wall after TBM S623 arrival | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
217 | TT_TASK | TBM Breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
218 | None | S623 TBM Removal | Thu Oct 22 07:00:00 IDT 2015 | Thu Dec 01 07:00:00 IST 2016
219 | TT_TASK | Move TBM S623 front portion to cradle | Thu Oct 22 07:00:00 IDT 2015 | Tue Oct 27 17:00:00 IST 2015
220 | TT_TASK | Weld additional bracing brackets corbels | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
221 | TT_TASK | Install cradle on lateral shifting system | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
222 | TT_TASK | Move and shift TBM to dismantle location | Thu Apr 07 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
223 | TT_TASK | Dismantle Cutter Head & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
224 | TT_TASK | Dismantle TBM rear & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
225 | TT_TASK | Dismantle segment installation machine & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
226 | TT_TASK | Dismantle TBM middle sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
227 | TT_TASK | Dismantle TBM front sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
228 | TT_TASK | Dismantle S623 Link Bridge & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
229 | TT_TASK | Dismantle S623 Wagon #1 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
230 | TT_TASK | Dismantle S623 Wagon #2 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
231 | TT_TASK | Dismantle S623 Wagon #3 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
232 | TT_TASK | Dismantle S623 Wagon #4 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
233 | TT_TASK | Dismantle S623 Wagon #5 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
234 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N1 | Thu Jun 23 07:00:00 IDT 2016 | Thu Jun 23 07:00:00 IDT 2016
235 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N2 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
236 | TT_TASK | Site clearance | Fri Apr 01 07:00:00 IDT 2016 | Tue Sep 27 17:00:00 IDT 2016
237 | None | Up Track - Ch.115+940 to Ch.117+413 | Fri May 10 08:00:00 IDT 2013 | Fri Oct 09 17:00:00 IDT 2015
238 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Fri May 10 08:00:00 IDT 2013 | Sat May 11 08:00:00 IDT 2013
239 | TT_TASK | Continue S624 drive, ch. 115+939 to ch. 115+950 in soil | Fri May 09 08:00:00 IDT 2014 | Sat May 10 08:00:00 IDT 2014
240 | TT_TASK | Continue S624 drive, ch. 115+950 to ch. 115+987 in mixed ground | Fri May 09 08:00:00 IDT 2014 | Tue May 13 08:00:00 IDT 2014
241 | TT_TASK | Continue S624 drive, ch. 115+987 to ch. 116+050 in soil | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 08:00:00 IDT 2014
242 | TT_TASK | Continue S624 drive, ch. 116+050 to ch. 116+226 in mixed ground | Sun Jun 01 08:00:00 IDT 2014 | Wed Jul 02 08:00:00 IDT 2014
243 | TT_TASK | Continue S624 drive, ch. 116+226 to ch. 116+240 in soil/marble | Fri Aug 01 08:00:00 IDT 2014 | Sun Aug 03 08:00:00 IDT 2014
244 | TT_TASK | Continue S624 drive, ch. 116+240 to ch. 116+270 in marble | Fri Aug 01 08:00:00 IDT 2014 | Wed Aug 13 08:00:00 IDT 2014
245 | TT_TASK | Continue S624 drive, ch. 116+270 to ch. 116+300 in marble | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014
246 | TT_TASK | Continue S624 drive, ch. 116+300 to ch. 116+329 in marble | Wed Oct 01 08:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014
247 | TT_TASK | Continue S624 drive, ch. 116+329 to ch. 116+358 in marble | Sat Nov 01 07:00:00 IST 2014 | Mon Nov 17 17:00:00 IST 2014
248 | TT_TASK | Continue S624 drive, ch. 116+358 to ch. 116+388 in marble | Sun Nov 23 07:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
249 | TT_TASK | Continue S624 drive, ch. 116+388 to ch. 116+415 in marble | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 02 17:00:00 IST 2015
250 | TT_TASK | Continue S624 drive, ch. 116+415 to ch. 116+430 in soil/marble | Sun Jan 11 07:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
251 | TT_TASK | Continue S624 drive, ch. 116+430 to ch. 116+600 in soil | Tue Jan 13 07:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
252 | TT_TASK | Continue S624 drive, ch. 116+600 to ch. 116+850 in soil/Alluv. zone | Wed Jan 21 07:00:00 IST 2015 | Thu Mar 05 17:00:00 IST 2015
253 | TT_TASK | Continue S624 drive, ch. 116+850 to ch. 116+930 in Alluv. zone | Tue Mar 31 07:00:00 IDT 2015 | Mon Apr 13 17:00:00 IDT 2015
254 | TT_TASK | Continue S624 drive, ch. 116+930 to ch. 117+413 in soil at Mai Po | Thu Jul 16 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
255 | TT_TASK | Pre-coring at diaphragm wall after TBM S624 arrival | Sat Aug 15 07:00:00 IDT 2015 | Mon Aug 17 17:00:00 IDT 2015
256 | TT_TASK | TBM S624 breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
257 | None | TBM Removal Preparation | Mon Dec 01 07:00:00 IST 2014 | Wed Nov 11 17:00:00 IST 2015
258 | TT_TASK | Prepare TTMS report for removal of TBM S624 & S623 | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 15 17:00:00 IST 2014
259 | TT_TASK | Working Group Meeting & SLG Meeting | Fri Jan 16 07:00:00 IST 2015 | Wed Apr 15 17:00:00 IDT 2015
260 | TT_TASK | Drawings' approval and endosement from RDO | Mon Feb 23 07:00:00 IST 2015 | Mon Mar 09 17:00:00 IST 2015
261 | TT_TASK | Submit advance notice to the HK Police | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
262 | TT_TASK | On stie preparation works | Mon Jul 13 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
263 | TT_TASK | Proof drilling for water tightness test of jet grout block | Wed Jul 01 07:00:00 IDT 2015 | Tue Jul 07 17:00:00 IDT 2015
264 | TT_TASK | Shaft bottom slab levelling | Fri Jul 24 07:00:00 IDT 2015 | Sat Jul 25 17:00:00 IDT 2015
265 | TT_TASK | Moving device and cradle installation | Thu Jul 23 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
266 | None | S624 TBM Removal | Tue Sep 29 07:00:00 IDT 2015 | Sun Nov 08 17:00:00 IST 2015
267 | TT_TASK | Move TBM S624 front portion to cradle | Tue Oct 13 07:00:00 IDT 2015 | Sun Oct 18 17:00:00 IDT 2015
268 | TT_TASK | Weld additional bracing brackets corbels | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
269 | TT_TASK | Install cradle on lateral shifting system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
270 | TT_TASK | Move and shift TBM to dismantle location | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
271 | TT_TASK | Dismantle Cutter Head & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
272 | TT_TASK | Dismantle TBM front sheild & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
273 | TT_TASK | Dismantle segment installation machine & Remove | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
274 | TT_TASK | Dismantle TBM middle sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
275 | TT_TASK | Dismantle TBM rear sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
276 | TT_TASK | Dismantle S624 Link Bridge & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
277 | TT_TASK | Dismantle S624 Wagon #1 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
278 | TT_TASK | Dismantle S624 Wagon #2 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
279 | TT_TASK | Dismantle S624 Wagon #3 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
280 | TT_TASK | Dismantle S624 Wagon #4 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
281 | TT_TASK | Dismantle S624 Wagon #5 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
282 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N1 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
283 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N2 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
284 | None | Cross Passages (HK) | Wed Oct 01 07:00:00 IDT 2014 | Thu Aug 04 17:00:00 IDT 2016
285 | None | Freezing Station A | Sat Oct 11 07:00:00 IDT 2014 | Mon Nov 09 17:00:00 IST 2015
286 | TT_TASK | Erect Freezing Station Platform | Sat Oct 11 07:00:00 IDT 2014 | Tue Oct 21 17:00:00 IDT 2014
287 | TT_TASK | Freezing Station Installation & Testing | Thu Jan 01 07:00:00 IST 2015 | Sat Jan 31 17:00:00 IST 2015
288 | TT_TASK | Remove Freezing Station A | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
289 | None | Cross Passage #1. Ch.116+030 | Wed Oct 01 07:00:00 IDT 2014 | Tue May 10 17:00:00 IDT 2016
290 | TT_TASK | Erect Temporary Drilling Platform | Wed Oct 01 07:00:00 IDT 2014 | Fri Oct 10 17:00:00 IDT 2014
291 | TT_TASK | Drill & Install Freezing Pipe | Mon Dec 01 07:00:00 IST 2014 | Wed Jan 14 17:00:00 IST 2015
292 | TT_TASK | Install temporary support including ring support (Up-track) | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 15 17:00:00 IST 2015
293 | TT_TASK | Install temporary support including ring support (Down-track) | Mon Feb 23 07:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
294 | TT_TASK | Intall safe door | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 25 17:00:00 IDT 2015
295 | TT_TASK | Install freezing & monitoring system | Mon Feb 23 07:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
296 | TT_TASK | Conduct Ground Freezing | Sun Mar 01 07:00:00 IST 2015 | Tue Apr 14 17:00:00 IDT 2015
297 | TT_TASK | Maintain ground freezing during construction of CP | Tue Apr 21 07:00:00 IDT 2015 | Sun Jun 14 17:00:00 IDT 2015
298 | TT_TASK | Tunnel segment cutting & removal | Tue Apr 21 07:00:00 IDT 2015 | Wed Apr 22 17:00:00 IDT 2015
299 | TT_TASK | Excavate and temporary support | Tue Apr 21 07:00:00 IDT 2015 | Sat May 23 17:00:00 IDT 2015
300 | TT_TASK | Tunnel segment removal | Tue Aug 04 07:00:00 IDT 2015 | Mon Aug 10 17:00:00 IDT 2015
301 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Jul 03 07:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
302 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 08 17:00:00 IDT 2015
303 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
304 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
305 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
306 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
307 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
308 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
309 | TT_TASK | Remove formwork | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
310 | TT_TASK | Concrete achieved the design strength | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
311 | TT_TASK | Remove temporary works | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
312 | TT_TASK | Remove Freezing Plant | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
313 | TT_TASK | Thawing & Proof Grouting | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
314 | TT_TASK | Make Good Freezing Pipe Hole | Sun May 01 07:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
315 | None | Cross Passage #2. Ch.116+195 | Mon Feb 23 07:00:00 IST 2015 | Sun Apr 10 17:00:00 IDT 2016
316 | TT_TASK | Erect Temporary Drilling Platform | Mon Feb 23 07:00:00 IST 2015 | Wed Feb 25 17:00:00 IST 2015
317 | TT_TASK | Drill & Install Freezing Pipe | Mon Feb 23 07:00:00 IST 2015 | Fri Apr 10 17:00:00 IDT 2015
318 | TT_TASK | Install temporary support (including ring support) | Tue Apr 21 07:00:00 IDT 2015 | Tue May 05 17:00:00 IDT 2015
319 | TT_TASK | Install safe door | Mon Jun 01 07:00:00 IDT 2015 | Thu Jun 04 17:00:00 IDT 2015
320 | TT_TASK | Install freezing & monitoring system | Tue Apr 21 07:00:00 IDT 2015 | Thu Apr 23 17:00:00 IDT 2015
321 | TT_TASK | Conduct Ground Freezing | Tue Apr 21 07:00:00 IDT 2015 | Tue Jun 16 17:00:00 IDT 2015
322 | TT_TASK | Maintain ground freezing during construction of CP | Fri Jul 24 07:00:00 IDT 2015 | Mon Sep 21 17:00:00 IDT 2015
323 | TT_TASK | Tunnel segment cutting & removal | Fri Jul 24 07:00:00 IDT 2015 | Thu Jul 30 17:00:00 IDT 2015
324 | TT_TASK | Excavate and temporary support | Sun Jul 26 07:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
325 | TT_TASK | Tunnel segment removal | Mon Aug 03 07:00:00 IDT 2015 | Tue Aug 04 17:00:00 IDT 2015
326 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
327 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
328 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
329 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
330 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
331 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
332 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
333 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
334 | TT_TASK | Remove formwork | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
335 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
336 | TT_TASK | Remove temporary works | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
337 | TT_TASK | Remove Freezing Pipes | Sat Nov 14 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
338 | TT_TASK | Thawing & Proof Grouting | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
339 | TT_TASK | Make Good Freezing Pipe Holes | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
340 | None | Freezing Station B | Mon Jun 01 07:00:00 IDT 2015 | Thu Aug 04 17:00:00 IDT 2016
341 | TT_TASK | Erect Freezing Station Platform | Mon Jun 01 07:00:00 IDT 2015 | Sat Jun 20 17:00:00 IDT 2015
342 | TT_TASK | Freezing Station Installation & Testing | Sun Jun 21 07:00:00 IDT 2015 | Fri Jul 10 17:00:00 IDT 2015
343 | TT_TASK | Remove Station B | Fri Jul 22 07:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016
344 | None | Cross Passage #3. Ch. 116+445 | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
345 | TT_TASK | Erect Temporary Drilling Platform | Tue Apr 21 07:00:00 IDT 2015 | Sun Apr 26 17:00:00 IDT 2015
346 | TT_TASK | Drill & Install Freezing Pipe | Tue Apr 21 07:00:00 IDT 2015 | Fri Jun 05 17:00:00 IDT 2015
347 | TT_TASK | Install temporary support (including ring support) | Sun Jul 19 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
348 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
349 | TT_TASK | Install freezing & monitoring system | Wed Jul 01 07:00:00 IDT 2015 | Fri Jul 03 17:00:00 IDT 2015
350 | TT_TASK | Conduct Ground Freezing | Sat Jul 04 07:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
351 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Sep 29 07:00:00 IDT 2015 | Fri Dec 18 17:00:00 IST 2015
352 | TT_TASK | Tunnel segment cutting & removal at U/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
353 | TT_TASK | Excavate and temporary support | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 31 17:00:00 IST 2015
354 | TT_TASK | Tunnel segment removal at D/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
355 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
356 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
357 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
358 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
359 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 12 17:00:00 IST 2015
360 | TT_TASK | Lining concreting (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
361 | TT_TASK | Lining concrete curing (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
362 | TT_TASK | Make Good Freezing Pipe Hole | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
363 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
364 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
365 | TT_TASK | Remove temp. works, ring support and temp. platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
366 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
367 | None | Cross Passage #4. Ch. 116+671 | Mon Jul 06 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
368 | TT_TASK | Erect Temporary Drilling Platform | Sun Jul 19 07:00:00 IDT 2015 | Thu Jul 23 17:00:00 IDT 2015
369 | TT_TASK | Drill & Install Freezing Pipe | Mon Jul 06 07:00:00 IDT 2015 | Thu Aug 20 17:00:00 IDT 2015
370 | TT_TASK | Install temporary support (including ring support) | Tue Sep 29 07:00:00 IDT 2015 | Tue Oct 13 17:00:00 IDT 2015
371 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
372 | TT_TASK | Install freezing & monitoring system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
373 | TT_TASK | Conduct Ground Freezing | Tue Sep 29 07:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
374 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Thu Nov 05 07:00:00 IST 2015 | Fri Feb 19 17:00:00 IST 2016
375 | TT_TASK | Tunnel segment cutting & removal at U/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
376 | TT_TASK | Excavate and temporary support | Mon Nov 09 07:00:00 IST 2015 | Wed Nov 25 17:00:00 IST 2015
377 | TT_TASK | Earthing, Waterproof works and waterproof test | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
378 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
379 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
380 | TT_TASK | Lining concrete curing (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
381 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
382 | TT_TASK | Lining concreting (side walls and roof) | Tue Nov 10 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
383 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
384 | TT_TASK | Remove formwork | Fri Apr 08 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
385 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
386 | TT_TASK | Remove temp. works and ring support | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
387 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
388 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
389 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
390 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Sat Nov 07 17:00:00 IST 2015
391 | TT_TASK | Erect temp. working platform | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
392 | TT_TASK | Drilling remaining holes at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
393 | TT_TASK | Install ring support at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
394 | TT_TASK | Tunnel segment removal at D/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
395 | None | Cross Passage #5. Ch. 116+966 | Wed Jul 01 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
396 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+066); last gantry passed CP5 | Wed Jul 01 07:00:00 IDT 2015 | Wed Jul 01 07:00:00 IDT 2015
397 | TT_TASK | Erect Temporary Drilling Platform at U/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
398 | START_MILESTONE | TBM S623 C/W exited Alluvial zone at S1425/Ch. 116+927 (* Note1) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
399 | TT_TASK | TBM S623 C/W boring from Ch. 116+927 to Ch. 116+986 (CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
400 | TT_TASK | Drill & Install Freezing Pipe at U/T | Sat Oct 10 07:00:00 IDT 2015 | Tue Nov 24 17:00:00 IST 2015
401 | TT_TASK | Raise track rail, slurry pipes diversion, install temp. support at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
402 | TT_TASK | Install Ring Support | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
403 | TT_TASK | Install freezing & monitoring system | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
404 | TT_TASK | Freezing system Test & Commissioning | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
405 | TT_TASK | Conduct Ground Freezing (Active phase) | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
406 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Dec 01 07:00:00 IST 2015 | Sun Mar 20 17:00:00 IST 2016
407 | TT_TASK | Install safe door (both sides) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
408 | TT_TASK | Tunnel segment cutting & removal at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
409 | TT_TASK | Excavate and temporary support (excavation from D/T) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
410 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
411 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
412 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
413 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
414 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
415 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
416 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
417 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
418 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
419 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
420 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
421 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
422 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
423 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Fri Nov 27 17:00:00 IST 2015
424 | TT_TASK | TBM S623 C/W boring from Ch.. 116+986 to Ch117+086 (last gantry passed CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 16 17:00:00 IDT 2015
425 | TT_TASK | Erect Temporary Drilling Platorm at D/T | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
426 | TT_TASK | Drilling remaining holes at D/T after S623 gantries passed | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 27 17:00:00 IST 2015
427 | TT_TASK | Install ring support at D/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
428 | None | Cross Passage #6. Ch. 117+216 | Sat Aug 01 07:00:00 IDT 2015 | Wed Jun 15 17:00:00 IDT 2016
429 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Sat Aug 01 07:00:00 IDT 2015 | Sat Aug 01 07:00:00 IDT 2015
430 | TT_TASK | Erect Drilling Platform at U/T | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
431 | TT_TASK | Drill ground freezing holes at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
432 | TT_TASK | Install Ring Support at U/T | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
433 | TT_TASK | Install freezing & monitoring system at U/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
434 | TT_TASK | Freezing system Test & Commissioning at U/T, Station B | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
435 | TT_TASK | Conduct Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Thu May 19 17:00:00 IDT 2016
436 | LEVEL_OF_EFFORT | Maintain Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Wed Jun 15 17:00:00 IDT 2016
437 | TT_TASK | Install safe door (both sides) | Sun Apr 10 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
438 | TT_TASK | Tunnel segment removal | Sat Apr 16 07:00:00 IDT 2016 | Wed Apr 20 17:00:00 IDT 2016
439 | TT_TASK | Excavate and temporary support (excavation from U/T side only) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
440 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
441 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
442 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
443 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
444 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
445 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
446 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
447 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
448 | TT_TASK | Remove formwork & Remove safe doors | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
449 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
450 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
451 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
452 | TT_TASK | Make Good Freezing Pipe Hole | Mon Apr 11 07:00:00 IDT 2016 | Thu Apr 14 17:00:00 IDT 2016
453 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Mon Apr 11 17:00:00 IDT 2016
454 | START_MILESTONE | S623 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
455 | TT_TASK | Erect Working Platform at D/T | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
456 | TT_TASK | Drill ground freezing holes at D/T | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
457 | TT_TASK | Install freezing & monitoring system at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
458 | TT_TASK | Ring support installation at D/T | Wed Apr 06 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
459 | None | Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
460 | None | Down Track Tunnel Finishes | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
461 | None | Tunnel Invert Slab (DT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 30 17:00:00 IDT 2016
462 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m-64=25m) | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
463 | TT_TASK | Invert Slab at CP1 (30m) | Sun May 29 07:00:00 IDT 2016 | Mon May 30 17:00:00 IDT 2016
464 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) | Sat May 21 07:00:00 IDT 2016 | Sat May 28 17:00:00 IDT 2016
465 | TT_TASK | Invert Slab at CP2 (30m) | Sat May 21 07:00:00 IDT 2016 | Sun May 22 17:00:00 IDT 2016
466 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Sun May 08 07:00:00 IDT 2016 | Fri May 20 17:00:00 IDT 2016
467 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
468 | TT_TASK | Invert Slab between CP3 and CP4 (226-45=181m) | Fri Apr 29 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
469 | TT_TASK | Invert Slab at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
470 | TT_TASK | Invert Slab between CP4 and CP5 (296-59=237m) | Thu Apr 14 07:00:00 IDT 2016 | Thu Apr 28 17:00:00 IDT 2016
471 | TT_TASK | Invert Slab at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
472 | TT_TASK | Invert Slab between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
473 | TT_TASK | Invert Slab at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
474 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (14m) | Thu Apr 07 07:00:00 IDT 2016 | Fri Apr 08 17:00:00 IDT 2016
475 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Thu Apr 07 07:00:00 IDT 2016 | Sat Apr 16 17:00:00 IDT 2016
476 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
477 | None | Lower Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
478 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
479 | TT_TASK | Lower Wkys at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
480 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
481 | TT_TASK | Lower Wks at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
482 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
483 | TT_TASK | Lower Wkys at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
484 | TT_TASK | Lower Wkys between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
485 | TT_TASK | Lower Wkys at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
486 | TT_TASK | Lower Wkys between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
487 | TT_TASK | Lower Wkys at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
488 | TT_TASK | Lower Wkys between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
489 | TT_TASK | Lower Wkys at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
490 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
491 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
492 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
493 | None | Upper Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
494 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
495 | TT_TASK | Upper Wky at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
496 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
497 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
498 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
499 | TT_TASK | Upper Wky at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
500 | TT_TASK | Upper Wky between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
501 | TT_TASK | Upper Wky at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
502 | TT_TASK | Upper Wky between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
503 | TT_TASK | Upper Wky at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
504 | TT_TASK | Upper Wky between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
505 | TT_TASK | Upper Wky at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
506 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
507 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
508 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
509 | None | DT Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Sat Dec 24 17:00:00 IST 2016
510 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
511 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
512 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
513 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
514 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
515 | None | Double Gates (DT) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
516 | TT_TASK | Install double gates at 20m south of CP6 | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
517 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
518 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
519 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
520 | None | Up Track Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 22 17:00:00 IST 2016
521 | None | Tunnel Invert Slab (UT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 02 17:00:00 IDT 2016
522 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m) | Tue Apr 26 07:00:00 IDT 2016 | Sun May 01 17:00:00 IDT 2016
523 | TT_TASK | Invert Slab at CP1 (30m) | Tue Apr 26 07:00:00 IDT 2016 | Wed Apr 27 17:00:00 IDT 2016
524 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) incl. Station A area | Mon Apr 18 07:00:00 IDT 2016 | Mon Apr 25 17:00:00 IDT 2016
525 | TT_TASK | Invert Slab at CP2 (30m) | Mon Apr 18 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
526 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Tue Apr 05 07:00:00 IDT 2016 | Sun Apr 17 17:00:00 IDT 2016
527 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
528 | TT_TASK | Invert Slab between CP3 and CP4 (226-47-34=145m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
529 | TT_TASK | Invert Slab at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
530 | TT_TASK | Invert Slab at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
531 | TT_TASK | Invert Slab between CP4 and CP5 (296-51=245m) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
532 | TT_TASK | Invert Slab at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
533 | TT_TASK | Invert Slab between CP5 and CP6 (250-32=218m) | Sat Dec 19 07:00:00 IST 2015 | Thu Dec 31 17:00:00 IST 2015
534 | TT_TASK | Invert Slab at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
535 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (20m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
536 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
537 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
538 | None | Lower Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
539 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
540 | TT_TASK | Lower Wkys at CP1 (30m) | Mon May 16 07:00:00 IDT 2016 | Tue May 17 17:00:00 IDT 2016
541 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
542 | TT_TASK | Lower Wkys at CP2 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
543 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
544 | TT_TASK | Lower Wkys at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
545 | TT_TASK | Lower Wkys between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
546 | TT_TASK | Lower Wkys at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
547 | TT_TASK | Lower Wkys at CP4 (64m) | Sat Apr 16 07:00:00 IDT 2016 | Mon Apr 18 17:00:00 IDT 2016
548 | TT_TASK | Lower Wkys between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
549 | TT_TASK | Lower Wkys at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
550 | TT_TASK | Lower Wkys between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
551 | TT_TASK | Lower Wkys at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
552 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
553 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
554 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
555 | None | Upper Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
556 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
557 | TT_TASK | Upper Wky at CP1 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
558 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
559 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
560 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
561 | TT_TASK | Upper Wky at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
562 | TT_TASK | Upper Wky between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
563 | TT_TASK | Upper Wky at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
564 | TT_TASK | Upper Wky at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
565 | TT_TASK | Upper Wky between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
566 | TT_TASK | Upper Wky at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
567 | TT_TASK | Upper Wky between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
568 | TT_TASK | Upper Wky at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
569 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
570 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
571 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
572 | None | Up Track Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Thu Dec 22 17:00:00 IST 2016
573 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
574 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
575 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Thu Dec 22 17:00:00 IST 2016
576 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
577 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
578 | None | UT Double Gates | Thu Nov 05 07:00:00 IST 2015 | Wed Apr 06 17:00:00 IDT 2016
579 | TT_TASK | Install double gates at 20m south of CP6 | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
580 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Wed Nov 11 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
581 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
582 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
583 | None | Tunnel Finishes to Completion | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
584 | None | Down Track | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
585 | TT_TASK | Operation and maintenance of temporary services | Fri Apr 08 07:00:00 IDT 2016 | Sun Mar 05 17:00:00 IST 2017
586 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
587 | None | Up Track | Wed Jun 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
588 | TT_TASK | Operation and maintenance of temporary services | Wed Jun 01 07:00:00 IDT 2016 | Thu Oct 06 17:00:00 IDT 2016
589 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
590 | None | Commissioning, Inspections and Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
591 | RESOURCE_DEPENDENT | Site Cleaning, Inspection for Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
592 | FINISH_MILESTONE | Submit draft as-built drawings (Z8.2) and draft O&M Manuals | Sat Dec 24 17:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
593 | FINISH_MILESTONE | Submit approved Design Data (Z8.4) | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
594 | FINISH_MILESTONE | Submit final as-built drawings and O&M Manuals | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
595 | TT_TASK | Inspect & Certify completion of whole works | Sat Mar 25 07:00:00 IDT 2017 | Fri Mar 31 17:00:00 IDT 2017
596 | None | Contract Preliminaries | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
597 | None | Designs and Submissions | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
598 | None | Principle Method Statements, Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
599 | None | Management Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Sun Oct 30 08:00:00 IST 2011
600 | TT_TASK | Submit System Assurance Plan (App P, P3.1) | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
601 | TT_TASK | Engineer's review on System Assurance Plan | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
602 | TT_TASK | Submit Health and Safety Plan (G3.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
603 | TT_TASK | Engineer's review on Health and Safety Plan | Wed May 05 08:00:00 IDT 2010 | Wed Jun 02 08:00:00 IDT 2010
604 | TT_TASK | Submit Quality Assurance Plan (G9.2.1) | Thu Apr 15 08:00:00 IDT 2010 | Thu May 13 08:00:00 IDT 2010
605 | TT_TASK | Engineer's review on Quality Assurance Plan | Wed May 12 08:00:00 IDT 2010 | Wed Jun 09 08:00:00 IDT 2010
606 | TT_TASK | Submit Prelimiary Master Programme (G4.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
607 | TT_TASK | Engineer's review on Prelimiary Master Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
608 | TT_TASK | Submit first Three-Month Rolling Programme (G4.8 | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 29 08:00:00 IDT 2010
609 | TT_TASK | Engineer's review on first Three-Month Rolling P | Fri Apr 02 08:00:00 IDT 2010 | Fri Apr 30 08:00:00 IDT 2010
610 | TT_TASK | Submit Time-chainage Programme (G4.11.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
611 | TT_TASK | Engineer's review on Time-chainage Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
612 | TT_TASK | Submit Design Schedule (App Z) | Mon May 03 08:00:00 IDT 2010 | Mon May 17 08:00:00 IDT 2010
613 | TT_TASK | Engineer's review on Design Schedule | Fri May 28 08:00:00 IDT 2010 | Fri Jun 25 08:00:00 IDT 2010
614 | TT_TASK | Submit Subcontractor Management Plan (App S) | Sat May 15 08:00:00 IDT 2010 | Mon Jun 14 08:00:00 IDT 2010
615 | TT_TASK | Engineer's review on Subcontractor Management Pl | Tue Jun 15 08:00:00 IDT 2010 | Tue Jul 13 08:00:00 IDT 2010
616 | TT_TASK | Submit Groundwater Monitoring and Emergency Resp | Thu Apr 22 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
617 | TT_TASK | Engineer's review on Groundwater Monitoring and | Fri Jun 04 08:00:00 IDT 2010 | Fri Jul 02 08:00:00 IDT 2010
618 | TT_TASK | Submit Water Pollution Control Measures and Moni | Thu Apr 15 08:00:00 IDT 2010 | Sun May 30 08:00:00 IDT 2010
619 | TT_TASK | Engineer's review on Water Pollution Control Mea | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
620 | TT_TASK | Submit Waste Management Plan (P22.8.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
621 | TT_TASK | Engineer's review on Waste Management Plan | Tue May 18 08:00:00 IDT 2010 | Tue Jun 15 08:00:00 IDT 2010
622 | TT_TASK | Submit the Plan for the Design for Safety and Co | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
623 | TT_TASK | Engineer's review on Plan for the Design for Saf | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
624 | TT_TASK | Submit Air Quality Management Plan (P22.4.4) | Fri Apr 09 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
625 | TT_TASK | Engineer's review on Air Quality Management Plan | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
626 | TT_TASK | Submit TBM manufacturiing and delivery programme | Sat May 22 08:00:00 IDT 2010 | Sat Jun 19 08:00:00 IDT 2010
627 | TT_TASK | Engineer's review on TBM manufacturiing and deli | Wed Jun 02 08:00:00 IDT 2010 | Wed Jun 30 08:00:00 IDT 2010
628 | TT_TASK | Submit Environmental Management Plan (G5.1.10) | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
629 | TT_TASK | Engineer's review on Environmental Management Pl | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
630 | TT_TASK | Submit interfacing documentation for System-wide | Mon Aug 01 08:00:00 IDT 2011 | Sun Oct 30 08:00:00 IST 2011
631 | TT_TASK | Engineer's review on interfacing documentation f | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
632 | None | Method Statements | Fri Apr 09 08:00:00 IDT 2010 | Wed Jun 17 17:00:00 IDT 2015
633 | TT_TASK | Submit Geotechnical Instruments installation | Fri Jun 18 08:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010
634 | TT_TASK | Engineer's review on Geotechnical Instruments installation | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
635 | TT_TASK | Submit Survey control network | Fri Apr 09 08:00:00 IDT 2010 | Mon May 24 08:00:00 IDT 2010
636 | TT_TASK | Engineer's review on Survey control network | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
637 | TT_TASK | Submit MS for surveying and survey control for tunnelling works | Mon Jun 14 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
638 | TT_TASK | Engineer's review on MS for surveying and survey control for tunnelling works | Sat Aug 07 08:00:00 IDT 2010 | Sat Sep 04 08:00:00 IDT 2010
639 | TT_TASK | Submit a Ground Treatment Works spoil disposal plan | Tue Jun 08 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
640 | TT_TASK | Engineer's review on Ground Treatment Works spoil disposal plan | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
641 | TT_TASK | Submit MS for ground treatment | Sun May 09 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
642 | TT_TASK | Engineer's review on MS for ground treatment | Fri Jun 25 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
643 | TT_TASK | Submit TBM MS for transportation and erection of the TBMs (X.17.1.1) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
644 | TT_TASK | Engineer's review on TBM MS for transportation and erection of the TBMs | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
645 | TT_TASK | Submit TBM MS for operation of the TBM (X17.1.3) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
646 | TT_TASK | Engineer's review on TBM MS for operation of the TBM | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
647 | TT_TASK | Submit MS for instrumentation and monitoring works in Ramsar & WPC areas | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 29 08:00:00 IDT 2011
648 | TT_TASK | Engineer's review on MS for instrumentation and monitoring works in Ramsar & WPC | Tue Mar 08 08:00:00 IST 2011 | Tue Apr 05 08:00:00 IDT 2011
649 | TT_TASK | Submit TBM MS for determining ground conditions ahead of the face (X17.1.5) (CS569) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
650 | TT_TASK | Engineer's review on TBM MS for determining ground conditions ahead of the face | Fri Apr 17 07:00:00 IDT 2015 | Thu May 14 17:00:00 IDT 2015
651 | TT_TASK | Submit MS for cross passage construction | Mon Jul 04 08:00:00 IDT 2011 | Mon Aug 01 08:00:00 IDT 2011
652 | TT_TASK | Engineer's review on MS for cross passage construction | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 26 08:00:00 IDT 2011
653 | TT_TASK | Submit TBM MS for commencing the initial drives (X17.1.2) (CS80) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
654 | TT_TASK | Engineer's review on TBM MS for commencing the initial drives | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
655 | TT_TASK | Submit TBM MS for setting out and controlling the tunnel alignment (Survey MS CS21) | Tue May 11 07:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
656 | TT_TASK | Engineer's review on TBM MS for setting out & contolling the tunnel alignment | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
657 | TT_TASK | Submit TBM MS for monitoring ground loss and settlement monitoring (X17.1.6) (CS36) | Tue Nov 30 07:00:00 IST 2010 | Tue Nov 30 07:00:00 IST 2010
658 | TT_TASK | Engineer's review on TBM MS for monitoring ground loss & settlement monitoring | Wed Aug 11 07:00:00 IDT 2010 | Wed Aug 11 07:00:00 IDT 2010
659 | TT_TASK | Submit TBM MS for hyperbaric interventions (X17.1.7) (CS520) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
660 | TT_TASK | Engineer's review on TBM MS for hyperbaric interventions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
661 | TT_TASK | Submit MS for the identification and removal of obstructions (P11.11) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
662 | TT_TASK | Engineer's review on MS for the identification & removal of obstructions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
663 | TT_TASK | Submit TBM MS for tunnelling under sensitive structures (X17.1.10) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
664 | TT_TASK | Engineer's review on TBM MS for tunnelling under sensitive structures | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
665 | TT_TASK | Submit TBM MS for TBM dismantling (X17.1.9) (CS652) | Fri Feb 20 07:00:00 IST 2015 | Wed May 20 17:00:00 IDT 2015
666 | TT_TASK | Engineer's review on TBM MS for TBM dismantling | Thu May 21 07:00:00 IDT 2015 | Wed Jun 17 17:00:00 IDT 2015
667 | TT_TASK | Submit TBM MS for junctions with shafts (X17.1.8) (CS246) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
668 | TT_TASK | Engineer's review on TBM MS for junctions with shafts | Thu Jun 23 07:00:00 IDT 2011 | Wed Jul 20 17:00:00 IDT 2011
669 | TT_TASK | Submit MS for ground freezing works (CS686) | Mon Dec 12 08:00:00 IST 2011 | Fri Feb 10 08:00:00 IST 2012
670 | TT_TASK | Engineer's review on MS for ground freezing work | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 16 08:00:00 IDT 2012
671 | TT_TASK | Submit MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 01 08:00:00 IST 2014
672 | TT_TASK | Engineer's review on MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
673 | TT_TASK | Submit Methods of Construction | Thu May 27 08:00:00 IDT 2010 | Thu Jun 17 08:00:00 IDT 2010
674 | TT_TASK | Engineer's review on Methods of Construction | Fri Jun 18 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
675 | TT_TASK | Submit TBM Spoil Disposal Plan (HK) | Wed Jun 23 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
676 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
677 | TT_TASK | Submit TBM Spoil Disposal Plan (SZ) | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 21 08:00:00 IST 2013
678 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 23 08:00:00 IST 2014
679 | None | Submissions to Government Departments | Sat May 29 08:00:00 IDT 2010 | Tue Jun 03 09:00:00 IDT 2014
680 | TT_TASK | Apply for the initial batch of Frontier Closed Area Permits | Sat May 29 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
681 | TT_TASK | Submit Emergency Rescue proposals and procedures | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
682 | TT_TASK | Engineer's review on Emergency Rescue proposals and procedures | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 28 08:00:00 IST 2013
683 | TT_TASK | Application and obtain approval of Construction Noise Permits | Fri Apr 04 09:00:00 IDT 2014 | Tue Jun 03 09:00:00 IDT 2014
684 | None | Temporary Works Design Submissions | Thu Apr 22 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
685 | TT_TASK | Submit site logistics plans (initial layout) | Thu Apr 22 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
686 | TT_TASK | Engineer's review on site logistics plans (initial layout) | Fri Jul 23 08:00:00 IDT 2010 | Fri Aug 20 08:00:00 IDT 2010
687 | TT_TASK | Submit designs for the Engineer's Office | Mon Jul 12 08:00:00 IDT 2010 | Fri Sep 10 08:00:00 IDT 2010
688 | TT_TASK | Engineer's review on designs for the Engineer's | Mon Aug 23 08:00:00 IDT 2010 | Mon Sep 20 08:00:00 IST 2010
689 | TT_TASK | Submit temporary ventilation system design | Mon Aug 01 08:00:00 IDT 2011 | Fri Sep 30 08:00:00 IDT 2011
690 | TT_TASK | Engineer's review on temporary ventilation syste | Sat Aug 20 08:00:00 IDT 2011 | Sat Sep 17 08:00:00 IDT 2011
691 | None | Design of Permanent Works | Tue Jun 01 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
692 | None | Tunnel Permanent Lining | Tue Jun 01 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
693 | TT_TASK | Submission preparation & ICE checking | Tue Jun 01 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
694 | TT_TASK | Engineer's review | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
695 | TT_TASK | Re-submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Tue Aug 31 08:00:00 IDT 2010
696 | TT_TASK | Engineer's review | Wed Aug 04 08:00:00 IDT 2010 | Wed Sep 01 08:00:00 IDT 2010
697 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
698 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
699 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
700 | None | Permanent Tunnel Lining of Cross Passages | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
701 | None | AIP Submission | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
702 | TT_TASK | Submission preparation | Mon Jun 28 08:00:00 IDT 2010 | Sat Aug 07 08:00:00 IDT 2010
703 | TT_TASK | Engineer's review | Sat Aug 14 08:00:00 IDT 2010 | Sat Sep 11 08:00:00 IDT 2010
704 | TT_TASK | Re-submission preparation | Fri Aug 03 08:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012
705 | TT_TASK | Engineer's review | Mon Sep 03 08:00:00 IDT 2012 | Mon Oct 01 08:00:00 IST 2012
706 | None | Connection between Bored Tunnel and Retrival Shaft | Mon Aug 16 08:00:00 IDT 2010 | Tue Jul 01 08:00:00 IDT 2014
707 | TT_TASK | Submission preparation & ICE checking | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 25 08:00:00 IST 2010
708 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
709 | TT_TASK | Re-submission preparation & ICE checking | Sat Oct 23 08:00:00 IST 2010 | Sun Nov 28 08:00:00 IST 2010
710 | TT_TASK | Engineer's review | Sat Oct 06 08:00:00 IST 2012 | Sat Nov 03 08:00:00 IST 2012
711 | TT_TASK | Submission for RDO/BD consultation | Sun Feb 10 08:00:00 IST 2013 | Sun Mar 10 08:00:00 IST 2013
712 | TT_TASK | Re-submission for RDO/BD consultation | Tue Dec 17 08:00:00 IST 2013 | Tue Jan 14 08:00:00 IST 2014
713 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
714 | None | Junction between Main Tunnel and Cross Passages | Mon Oct 04 08:00:00 IST 2010 | Sun Sep 07 08:00:00 IDT 2014
715 | TT_TASK | Submission preparation & ICE checking | Mon Oct 04 08:00:00 IST 2010 | Tue Nov 23 08:00:00 IST 2010
716 | TT_TASK | Engineer's review | Thu Feb 07 08:00:00 IST 2013 | Thu Mar 07 08:00:00 IST 2013
717 | TT_TASK | Submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
718 | TT_TASK | Re-submission preparation & ICE checking | Tue Jul 01 08:00:00 IDT 2014 | Sun Aug 10 08:00:00 IDT 2014
719 | TT_TASK | Engineer's review | Sun Aug 10 08:00:00 IDT 2014 | Sun Sep 07 08:00:00 IDT 2014
720 | TT_TASK | Re-submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
721 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
722 | None | Design of Temporary Works | Sat May 01 08:00:00 IDT 2010 | Fri Aug 29 08:00:00 IDT 2014
723 | None | Ground Treatment Works for TBM Break-in | Sat May 01 08:00:00 IDT 2010 | Tue Nov 02 08:00:00 IST 2010
724 | TT_TASK | Submission preparation & ICE checking | Sat May 01 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
725 | TT_TASK | Engineer's review | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 12 08:00:00 IDT 2010
726 | TT_TASK | Re-submission preparation & ICE checking | Wed Jun 30 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
727 | TT_TASK | Engineer's review | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
728 | TT_TASK | Submission for RDO/BD consultation | Tue Aug 31 08:00:00 IDT 2010 | Tue Sep 28 08:00:00 IST 2010
729 | TT_TASK | Re-submission for RDO/BD consultation | Tue Oct 05 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
730 | START_MILESTONE | Construction drawings issuance | Tue Nov 02 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
731 | None | Geotechnical Assessment Report | Mon Jun 14 08:00:00 IDT 2010 | Mon Dec 26 08:00:00 IST 2011
732 | TT_TASK | Submission preparation & ICE checking | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010
733 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
734 | TT_TASK | Re-submission preparation & ICE checking | Thu Oct 21 08:00:00 IST 2010 | Fri Nov 05 08:00:00 IST 2010
735 | TT_TASK | Engineer's review | Fri Nov 05 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
736 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
737 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
738 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
739 | None | Groundwater Assessment Report | Mon Jul 26 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
740 | TT_TASK | Submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010
741 | TT_TASK | Engineer's review | Tue Sep 07 08:00:00 IDT 2010 | Tue Oct 05 08:00:00 IST 2010
742 | TT_TASK | Re-submission preparation & ICE checking | Wed Nov 03 08:00:00 IST 2010 | Sun Nov 21 08:00:00 IST 2010
743 | TT_TASK | Engineer's review | Tue Nov 23 08:00:00 IST 2010 | Tue Dec 21 08:00:00 IST 2010
744 | TT_TASK | Submission for RDO/BD consultation | Wed Oct 06 08:00:00 IST 2010 | Wed Nov 03 08:00:00 IST 2010
745 | TT_TASK | Re-submission for RDO/BD consultation | Sat Oct 23 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
746 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
747 | None | Ground Freezing and Temporary Support of Cross Passages | Sat Jan 01 08:00:00 IST 2011 | Fri Aug 29 08:00:00 IDT 2014
748 | TT_TASK | Submission preparation & ICE checking | Sat Jan 01 08:00:00 IST 2011 | Sat Mar 12 08:00:00 IST 2011
749 | TT_TASK | Engineer's review | Fri Nov 25 08:00:00 IST 2011 | Fri Dec 23 08:00:00 IST 2011
750 | TT_TASK | Re-submission preparation & ICE checking | Fri Feb 15 08:00:00 IST 2013 | Mon Apr 01 08:00:00 IDT 2013
751 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
752 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
753 | TT_TASK | Re-submission for RDO/BD consultation | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014
754 | START_MILESTONE | Construction drawings issuance | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014
755 | None | Bulk Head for TBM Removal | Mon May 31 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
756 | TT_TASK | Submission preparation & ICE checking | Mon May 31 08:00:00 IDT 2010 | Mon Aug 09 08:00:00 IDT 2010
757 | TT_TASK | Engineer's review | Fri Jul 30 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
758 | TT_TASK | Re-submission preparation & ICE checking | Thu Aug 12 08:00:00 IDT 2010 | Sun Sep 26 08:00:00 IST 2010
759 | TT_TASK | Engineer's review | Thu Sep 16 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
760 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
761 | None | Prediction of Ground Movement | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
762 | None | Report on the Prediction of Ground Movement and and Assessment on effect of EBS | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
763 | TT_TASK | Submission preparation & ICE checking | Mon Jul 12 08:00:00 IDT 2010 | Tue Aug 17 08:00:00 IDT 2010
764 | TT_TASK | Engineer's review | Sun Aug 22 08:00:00 IDT 2010 | Sun Sep 19 08:00:00 IST 2010
765 | TT_TASK | Re-submission preparation & ICE checking | Wed Sep 29 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
766 | TT_TASK | Engineer's review | Wed Oct 13 08:00:00 IST 2010 | Wed Nov 10 08:00:00 IST 2010
767 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
768 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
769 | START_MILESTONE | Construction drawings issuance | Tue Dec 27 08:00:00 IST 2011 | Tue Dec 27 08:00:00 IST 2011
770 | None | Instrumentation and Montoring Plans | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
771 | None | Instrumentation Plan | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
772 | TT_TASK | Submission preparation & ICE checking | Mon May 03 08:00:00 IDT 2010 | Fri May 28 08:00:00 IDT 2010
773 | TT_TASK | Engineer's review | Tue Jun 08 08:00:00 IDT 2010 | Tue Jul 06 08:00:00 IDT 2010
774 | TT_TASK | Re-submission preparation & ICE checking | Wed Jul 28 08:00:00 IDT 2010 | Sun Aug 15 08:00:00 IDT 2010
775 | TT_TASK | Engineer's review | Tue Aug 10 08:00:00 IDT 2010 | Tue Sep 07 08:00:00 IDT 2010
776 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
777 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
778 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
779 | None | Additional Ground Investigation Plans and Laboratory | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
780 | None | Further GI Plan and Lab Test Schedule | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
781 | TT_TASK | Submission preparation & ICE checking | Tue May 31 08:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011
782 | TT_TASK | Engineer's review | Thu Jul 14 08:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011
783 | TT_TASK | Re-submission preparation & ICE checking | Mon Oct 31 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
784 | TT_TASK | Engineer's review | Sat Nov 19 08:00:00 IST 2011 | Sat Dec 17 08:00:00 IST 2011
785 | TT_TASK | Submission for RDO/BD consultation | Sat Dec 17 08:00:00 IST 2011 | Sat Jan 14 08:00:00 IST 2012
786 | TT_TASK | Re-submission for RDO/BD consultation | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
787 | START_MILESTONE | Construction drawings issuance | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 08:00:00 IST 2013
788 | None | Procurement | Mon Mar 15 08:00:00 IST 2010 | Mon Sep 07 17:00:00 IDT 2015
789 | None | TBM Manufacture and Delivery | Mon Mar 15 08:00:00 IST 2010 | Thu Nov 01 08:00:00 IST 2012
790 | TT_TASK | Confirmation of purchase order on TBM manufacture | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
791 | FINISH_MILESTONE | Submit PO to the Engineer | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
792 | TT_TASK | Shop drawing preparation and submission | Thu Jul 15 08:00:00 IDT 2010 | Wed Aug 04 08:00:00 IDT 2010
793 | TT_TASK | Shop drawing review by the Engineer | Tue Aug 24 08:00:00 IDT 2010 | Tue Sep 21 08:00:00 IST 2010
794 | TT_TASK | Resubmission of shop drawings | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 25 08:00:00 IST 2010
795 | TT_TASK | Engineer's approval of shop drawings | Thu Nov 18 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
796 | TT_TASK | Shop drawings issued for manufacture | Thu Dec 16 08:00:00 IST 2010 | Fri Dec 31 08:00:00 IST 2010
797 | TT_TASK | Manufacturing & purchase parts for TBM #1 | Mon Aug 23 08:00:00 IDT 2010 | Mon Nov 01 08:00:00 IST 2010
798 | TT_TASK | TBM #1 factory preassembly and packing | Thu Oct 07 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
799 | TT_TASK | TBM #1 delivery to workshop | Fri Nov 19 08:00:00 IST 2010 | Sun Dec 19 08:00:00 IST 2010
800 | TT_TASK | TBM #1 workshop assembly | Fri Jan 07 08:00:00 IST 2011 | Fri Mar 18 08:00:00 IST 2011
801 | TT_TASK | TBM #1 test runs, acceptance, dis-assembly and p | Mon May 16 08:00:00 IDT 2011 | Wed Jun 15 08:00:00 IDT 2011
802 | TT_TASK | TBM #1 delivery to Shenzhen | Wed May 25 08:00:00 IDT 2011 | Sat Jun 04 08:00:00 IDT 2011
803 | FINISH_MILESTONE | TBM #1 delivery to HGP shaft | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
804 | TT_TASK | TBM #1 on-site assembly, T&C @ HGP Shaft | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
805 | TT_TASK | TBM #1 free walk-thru to commencement position | Fri Apr 27 08:00:00 IDT 2012 | Thu May 17 08:00:00 IDT 2012
806 | FINISH_MILESTONE | TBM #1 ready to commence drive at HGP by GSG Contractor | Wed Jul 04 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
807 | TT_TASK | Manufacturing & purchase parts for TBM #2 | Thu Dec 16 08:00:00 IST 2010 | Thu Feb 24 08:00:00 IST 2011
808 | TT_TASK | TBM #2 factory preassembly and packing | Mon Feb 14 08:00:00 IST 2011 | Mon Apr 25 08:00:00 IDT 2011
809 | TT_TASK | TBM #2 delivery to workshop | Sat Mar 05 08:00:00 IST 2011 | Mon Apr 04 08:00:00 IDT 2011
810 | TT_TASK | TBM #2 workshop assembly | Mon May 30 08:00:00 IDT 2011 | Mon Aug 08 08:00:00 IDT 2011
811 | TT_TASK | TBM #2 test runs, acceptance, dis-assembly and p | Mon Aug 22 08:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011
812 | TT_TASK | TBM #2 delivery to temporary storage at Nansha | Mon Sep 19 08:00:00 IDT 2011 | Thu Sep 22 08:00:00 IDT 2011
813 | TT_TASK | TBM #2 delivery to Shenzhen | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
814 | FINISH_MILESTONE | TBM #2 delivery to HGP shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
815 | TT_TASK | TBM #2 on-site assembly, T&C @ HGP Shaft | Thu Apr 05 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
816 | TT_TASK | TBM #2 free walk-thru to commencement position | Mon Oct 01 08:00:00 IST 2012 | Sun Oct 21 08:00:00 IST 2012
817 | FINISH_MILESTONE | TBM #2 ready to commence drive at HGP by GSG Con | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012
818 | None | TBM Ground Support Equipment | Thu Jul 08 08:00:00 IDT 2010 | Mon Nov 05 08:00:00 IST 2012
819 | TT_TASK | Confirm order for slurry treatment plant (STP) | Thu Jul 08 08:00:00 IDT 2010 | Thu Jul 15 08:00:00 IDT 2010
820 | TT_TASK | STP shop drawing preparation and submission | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010
821 | TT_TASK | STP shop drawing review by the Engineer | Wed Dec 01 08:00:00 IST 2010 | Wed Dec 29 08:00:00 IST 2010
822 | TT_TASK | STP procurement of components and materials | Thu Dec 09 08:00:00 IST 2010 | Sun Jan 23 08:00:00 IST 2011
823 | TT_TASK | STP resubmission of shop drawings | Mon Jan 10 08:00:00 IST 2011 | Mon Jan 24 08:00:00 IST 2011
824 | TT_TASK | STP Engineer's approval of shop drawings | Tue Apr 05 08:00:00 IDT 2011 | Tue May 03 08:00:00 IDT 2011
825 | TT_TASK | STP shop drawings issued for manufacture | Mon Mar 14 08:00:00 IST 2011 | Mon Mar 21 08:00:00 IST 2011
826 | TT_TASK | STP sub-unit assembly | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 08:00:00 IDT 2011
827 | TT_TASK | STP final assembly at factory | Wed Mar 23 08:00:00 IST 2011 | Sat Apr 02 08:00:00 IDT 2011
828 | TT_TASK | STP factory testing | Wed Mar 30 08:00:00 IST 2011 | Sat Apr 09 08:00:00 IDT 2011
829 | TT_TASK | STP packaging and transportation to docks | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 15 08:00:00 IDT 2011
830 | TT_TASK | STP shipping to Shenzhen, customs clearance and forwarding | Mon Apr 04 08:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011
831 | FINISH_MILESTONE | STP delivery to HGP works area | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 12 08:00:00 IDT 2011
832 | TT_TASK | STP on-site assembly | Wed Sep 28 08:00:00 IDT 2011 | Sat Oct 22 08:00:00 IST 2011
833 | TT_TASK | STP on-site self testing and commissioning | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 08:00:00 IST 2012
834 | TT_TASK | STP on-site testing and commissioning with TBM#1 | Mon Jun 18 08:00:00 IDT 2012 | Fri Jun 29 08:00:00 IDT 2012
835 | TT_TASK | STP on-site testing and commissioning with TBM#2 | Wed Oct 03 08:00:00 IST 2012 | Sun Oct 14 08:00:00 IST 2012
836 | FINISH_MILESTONE | STP ready to commence operations for TBM #1 | Mon Jun 18 08:00:00 IDT 2012 | Mon Jun 18 08:00:00 IDT 2012
837 | FINISH_MILESTONE | STP ready to commence operations for TBM #2 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
838 | None | Tunnel Lining Segments | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 07 17:00:00 IDT 2015
839 | START_MILESTONE | Confirmation of purchase order on segment manufacturer | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
840 | TT_TASK | Shop drawings issued for manufacture | Mon Aug 29 08:00:00 IDT 2011 | Sat Sep 10 08:00:00 IDT 2011
841 | TT_TASK | Pre-casting trials | Thu Nov 03 08:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011
842 | TT_TASK | Engineer's approval of trial segments | Thu Dec 15 08:00:00 IST 2011 | Thu Jan 12 08:00:00 IST 2012
843 | TT_TASK | Manufacture 926 Tunnel Rings (SZ) | Wed Feb 01 08:00:00 IST 2012 | Fri Jul 20 08:00:00 IDT 2012
844 | TT_TASK | Manufacture 163 Tunnel Rings (SZ) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 25 08:00:00 IST 2012
845 | TT_TASK | Manufacture 105 Tunnel Rings (SZ) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012
846 | TT_TASK | Manufacture 98 Tunnel Rings (SZ) | Wed Oct 31 08:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012
847 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 26 08:00:00 IST 2012
848 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sun Jan 13 08:00:00 IST 2013 | Thu Feb 07 08:00:00 IST 2013
849 | TT_TASK | Manufacture 60 Tunnel Rings (SZ) | Sun Feb 24 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013
850 | TT_TASK | Manufacture 81 Tunnel Rings (HK) | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 08:00:00 IDT 2013
851 | TT_TASK | Manufacture 76 Tunnel Rings (HK) | Sun Jun 30 08:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013
852 | TT_TASK | Manufacture 75 Tunnel Rings (HK) | Mon Jul 01 08:00:00 IDT 2013 | Fri Jul 26 08:00:00 IDT 2013
853 | TT_TASK | Manufacture 88 Tunnel Rings (HK) | Thu Aug 01 08:00:00 IDT 2013 | Sun Aug 25 08:00:00 IDT 2013
854 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Sun Sep 01 08:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013
855 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Fri Jan 24 08:00:00 IST 2014
856 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
857 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
858 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Jul 01 08:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014
859 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014
860 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
861 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Mon Feb 16 07:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
862 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Mar 03 07:00:00 IST 2015 | Fri Mar 27 17:00:00 IDT 2015
863 | TT_TASK | Manufacture 60 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Sat May 02 17:00:00 IDT 2015
864 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Fri May 15 17:00:00 IDT 2015
865 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Sun Aug 09 07:00:00 IDT 2015 | Wed Sep 02 17:00:00 IDT 2015
866 | TT_TASK | Manufacture 10 Tunnel Rings (HK) | Thu Sep 03 07:00:00 IDT 2015 | Mon Sep 07 17:00:00 IDT 2015
867 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (SZ rings) | Wed Aug 01 08:00:00 IDT 2012 | Wed Dec 26 08:00:00 IST 2012
868 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (HK rings) | Sat Nov 30 08:00:00 IST 2013 | Sun Oct 12 08:00:00 IDT 2014
869 | None | Segment Mould Design, Fabrication and Delivery | Mon May 16 08:00:00 IDT 2011 | Wed Feb 15 08:00:00 IST 2012
870 | START_MILESTONE | Confirm order for moulds | Mon May 16 08:00:00 IDT 2011 | Mon May 16 08:00:00 IDT 2011
871 | TT_TASK | Design and planning | Mon May 16 08:00:00 IDT 2011 | Thu Jun 09 08:00:00 IDT 2011
872 | TT_TASK | Design mould drawings for manufacture | Fri Jul 08 08:00:00 IDT 2011 | Sun Aug 07 08:00:00 IDT 2011
873 | TT_TASK | Materials procurement | Fri Jul 08 08:00:00 IDT 2011 | Thu Jul 28 08:00:00 IDT 2011
874 | TT_TASK | Factory assembly | Mon Jul 18 08:00:00 IDT 2011 | Fri Sep 16 08:00:00 IDT 2011
875 | TT_TASK | Shipping and delivery to Shenzhen - 1st batch (3 sets) | Sat Nov 05 08:00:00 IST 2011 | Thu Nov 10 08:00:00 IST 2011
876 | TT_TASK | Shipping and delivery to Shenzhen - 2nd batch (3 sets) | Fri Feb 10 08:00:00 IST 2012 | Wed Feb 15 08:00:00 IST 2012
877 | TT_TASK | Mould erection and commissioning ready for production in precast yard | Thu Nov 10 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
878 | None | Other Procurement Items | Tue Nov 02 08:00:00 IST 2010 | Sun Apr 06 08:00:00 IDT 2014
879 | TT_TASK | Transformer and substation procurement | Tue May 31 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
880 | TT_TASK | Procure temporary electrics subcontractor | Wed Jun 01 08:00:00 IDT 2011 | Fri Jul 01 08:00:00 IDT 2011
881 | TT_TASK | Place order for ready mixed concrete | Fri Mar 01 08:00:00 IST 2013 | Sat Apr 06 08:00:00 IDT 2013
882 | TT_TASK | Procure other major construction plant and equip | Tue Mar 01 08:00:00 IST 2011 | Mon May 30 08:00:00 IDT 2011
883 | TT_TASK | Place order for rebar supply | Mon Oct 31 08:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011
884 | TT_TASK | Rental agreement for off site office accommodation | Tue Nov 02 08:00:00 IST 2010 | Thu Dec 02 08:00:00 IST 2010
885 | TT_TASK | Procure tunnel personnel electronic tagging system | Sat Nov 30 08:00:00 IST 2013 | Sat Jan 11 08:00:00 IST 2014
886 | TT_TASK | Procure tunnel ventilation system | Thu Mar 01 08:00:00 IST 2012 | Tue Apr 10 08:00:00 IDT 2012
887 | TT_TASK | Procure ground freezing specialist subcontractor | Sat Mar 01 08:00:00 IST 2014 | Sun Apr 06 08:00:00 IDT 2014
888 | None | Site Mobilisation | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
889 | TT_TASK | Initial project staff assignments | Mon Mar 15 08:00:00 IST 2010 | Sun Jun 13 08:00:00 IDT 2010
890 | TT_TASK | Establish Works Areas at HGP | Wed Dec 01 08:00:00 IST 2010 | Tue Jan 18 08:00:00 IST 2011
891 | TT_TASK | Establish Works Areas at MPV | Fri Feb 01 08:00:00 IST 2013 | Sat Mar 09 08:00:00 IST 2013
892 | TT_TASK | Establish and operate Project Office in Hong Kong | Thu Apr 22 08:00:00 IDT 2010 | Fri Feb 18 08:00:00 IST 2011
893 | TT_TASK | Establish and operate Project Office in Shenzhen | Mon Jan 10 08:00:00 IST 2011 | Sat Oct 01 08:00:00 IDT 2016
894 | TT_TASK | Establish and operate Project Office in Mai Po | Tue Mar 15 08:00:00 IST 2011 | Fri Jul 25 08:00:00 IDT 2014
895 | START_MILESTONE | Commencement to operate compound at Mai Po, Area 1.19, for DLP | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
1 | None | 826 As-built Programme | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
2 | None | 826 - HGP to Mai Po Tunnels, Revised Master Prog | Wed Mar 10 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
3 | None | Tender and Contract Details | Wed Mar 10 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
4 | None | Tender Actions | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
5 | START_MILESTONE | Contract Award (LoA) | Wed Mar 10 08:00:00 IST 2010 | Wed Mar 10 08:00:00 IST 2010
6 | None | Critical Contract Dates | Mon Mar 15 08:00:00 IST 2010 | Thu Jun 01 17:00:00 IDT 2017
7 | START_MILESTONE | Stated Contract Commencement Date (Cl 64) | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 15 08:00:00 IST 2010
8 | FINISH_MILESTONE | Table 3, Ref 3A - Delivery of the first TBM to HGP | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
9 | FINISH_MILESTONE | Table 3, Ref 3B - All works in Works Area 1.6 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
10 | FINISH_MILESTONE | Table 3, Ref 3C - Delivery of the second TBM to HGP | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
11 | FINISH_MILESTONE | Table 4, Ref 4A - Achieve Deg. 1 for both Up and Down Track Tunnels | Thu Mar 31 17:00:00 IDT 2016 | Thu Mar 31 17:00:00 IDT 2016
12 | FINISH_MILESTONE | Table 1 - Completion of the Whole of the Works (wk13/2015) | Thu Jun 01 17:00:00 IDT 2017 | Thu Jun 01 17:00:00 IDT 2017
13 | None | Other Programme Data | Thu May 09 08:00:00 IDT 2013 | Sat Apr 01 07:00:00 IDT 2017
14 | START_MILESTONE | GSG Contractor to hand over S623 to Cont' 826 at HK Boundary | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013
15 | START_MILESTONE | GSG Contractor to hand over S624 to Cont' 826 at HK Boundary | Thu May 09 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
16 | START_MILESTONE | Notification to Contract 846 for cable bracket installation | Sun Nov 22 07:00:00 IST 2015 | Sun Nov 22 07:00:00 IST 2015
17 | FINISH_MILESTONE | Provision of TBM Retrieval Shaft at MPV | Wed Oct 01 07:00:00 IDT 2014 | Wed Oct 01 07:00:00 IDT 2014
18 | START_MILESTONE | OHL Power On, by Designated Contractor 830 | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017
19 | None | Access Dates for Designated Contractors | Sun May 01 07:00:00 IDT 2016 | Thu Dec 01 07:00:00 IST 2016
20 | START_MILESTONE | 827, X-passage Doors - Door Frame Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
21 | START_MILESTONE | 827, X-passage Doors - Doors Installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
22 | START_MILESTONE | 830, Trackwork and OHL - Up-track | Sun May 01 07:00:00 IDT 2016 | Sun May 01 07:00:00 IDT 2016
23 | START_MILESTONE | 830, Trackwork and OHL - Down-track | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
24 | START_MILESTONE | 841A, Signalling System, Trackside Eqpt - Both tunnels | Wed Jun 01 07:00:00 IDT 2016 | Wed Jun 01 07:00:00 IDT 2016
25 | START_MILESTONE | 846, Trackside Aux - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
26 | START_MILESTONE | 849, Radio Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
27 | START_MILESTONE | 850, Passenger Mobile Communications Systems - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
28 | START_MILESTONE | 851, Fixed Comms - Both tunnels for installation | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
29 | START_MILESTONE | 8203, Constrn Stage Mobile Phone Network - Both tunnels | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
30 | None | Interface Contractor Programme - GSG | Wed Dec 01 08:00:00 IST 2010 | Sat Mar 01 07:00:00 IST 2014
31 | FINISH_MILESTONE | Complete Huanggang Park shaft construction | Mon Mar 26 08:00:00 IST 2012 | Mon Mar 26 08:00:00 IST 2012
32 | TT_TASK | Drill & Blast Tunnel (to HK) | Wed Dec 01 08:00:00 IST 2010 | Tue Sep 27 08:00:00 IDT 2011
33 | TT_TASK | S623 Excavate 242m (SZ) (s.rock) | Tue Jul 03 08:00:00 IDT 2012 | Sat Oct 06 08:00:00 IST 2012
34 | TT_TASK | S623 Conduct General Maintenance | Sun Oct 07 08:00:00 IST 2012 | Wed Oct 10 08:00:00 IST 2012
35 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 484m) | Wed Oct 10 08:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012
36 | TT_TASK | S623 Conduct General Maintenance | Sun Nov 18 08:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012
37 | TT_TASK | S623 Excavate 220m (SZ) (s.rock/total 704m) | Thu Nov 22 08:00:00 IST 2012 | Sat Dec 29 08:00:00 IST 2012
38 | TT_TASK | S623 Conduct General Maintenance | Tue Jan 08 08:00:00 IST 2013 | Sat Jan 12 08:00:00 IST 2013
39 | TT_TASK | S623 Excavate 150m (SZ) (m.rock/total 854m) | Sat Jan 12 08:00:00 IST 2013 | Wed Feb 06 08:00:00 IST 2013
40 | TT_TASK | S623 Conduct General Maintenance | Wed Feb 20 08:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013
41 | TT_TASK | S623 Excavate 50m (SZ) (s.rock/total 904m) | Thu Feb 28 08:00:00 IST 2013 | Fri Mar 08 08:00:00 IST 2013
42 | TT_TASK | S623 Conduct General Maintenance | Sun Apr 21 08:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013
43 | TT_TASK | S623 Excavate 100m (SZ) (rock/total 1004m) | Mon Apr 22 08:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013
44 | TT_TASK | S623 Conduct General Maintenance | Sat Jun 08 10:38:00 IDT 2013 | Mon Jun 10 10:38:00 IDT 2013
45 | TT_TASK | S623 Excavate 470m (SZ) (rock/total 1474m) | Wed May 15 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
46 | TT_TASK | S623 Conduct General Maintenance | Fri Sep 13 08:00:00 IDT 2013 | Sun Sep 15 08:00:00 IDT 2013
47 | TT_TASK | S623 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Aug 15 08:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013
48 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013
49 | TT_TASK | S623 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Oct 31 08:00:00 IST 2013 | Sun Nov 10 08:00:00 IST 2013
50 | TT_TASK | S623 Conduct General Maintenance | Thu Oct 31 08:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013
51 | TT_TASK | S623 Excavate 84m (SZ) (c.rock/total 1856m) | Thu Oct 31 08:00:00 IST 2013 | Sat Nov 02 08:00:00 IST 2013
52 | FINISH_MILESTONE | Complete TBM Excavation Down Track (SZ) | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 08:00:00 IST 2013
53 | TT_TASK | S624 Excavate 100m (SZ) (s.rock) | Mon Nov 05 08:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012
54 | TT_TASK | S624 Conduct General Maintenance | Mon Dec 10 08:00:00 IST 2012 | Thu Dec 13 08:00:00 IST 2012
55 | TT_TASK | S624 Excavate 142m (SZ) (s.rock/total 242m) | Thu Dec 13 08:00:00 IST 2012 | Sun Jan 06 08:00:00 IST 2013
56 | TT_TASK | S624 Conduct General Maintenance | Sat Jan 05 08:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013
57 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 484m) | Tue Jan 08 08:00:00 IST 2013 | Sun Feb 17 08:00:00 IST 2013
58 | TT_TASK | S624 Conduct General Maintenance | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 08:00:00 IST 2013
59 | TT_TASK | S624 Excavate 220m (SZ) (s.rock/total 704m) | Tue Feb 19 08:00:00 IST 2013 | Thu Mar 28 08:00:00 IST 2013
60 | TT_TASK | S624 Conduct General Maintenance | Fri Jun 28 08:58:00 IDT 2013 | Mon Jul 01 08:58:00 IDT 2013
61 | TT_TASK | S624 Excavate 150m (SZ) (m.rock/total 854m) | Tue Jul 02 08:58:00 IDT 2013 | Mon Jul 22 08:58:00 IDT 2013
62 | TT_TASK | S624 Conduct General Maintenance | Wed Jul 24 08:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013
63 | TT_TASK | S624 Excavate 50m (SZ) (s.rock/total 904m) | Wed Jul 24 08:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013
64 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 08:00:00 IDT 2013
65 | TT_TASK | S624 Excavate 100m (SZ) (s/m.rock/total 1004m) | Tue Aug 06 08:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013
66 | TT_TASK | S624 Conduct General Maintenance | Mon Aug 26 08:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013
67 | TT_TASK | S624 Excavate 470m (SZ) (s/m.rock/total 1474m) | Fri Sep 13 08:00:00 IDT 2013 | Sun Dec 01 08:00:00 IST 2013
68 | TT_TASK | S624 Conduct General Maintenance | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
69 | TT_TASK | S624 Excavate 242m (SZ) (m.rock/total 1716m) | Thu Jan 30 08:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014
70 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
71 | TT_TASK | S624 Excavate 56m (SZ) (c.rock/total 1772m) | Thu Jan 30 08:00:00 IST 2014 | Sun Feb 09 08:00:00 IST 2014
72 | TT_TASK | S624 Conduct General Maintenance | Thu Jan 30 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
73 | TT_TASK | S624 Excavate 92m (SZ) (c.rock/total 1864m) | Thu Jan 30 08:00:00 IST 2014 | Tue Feb 11 08:00:00 IST 2014
74 | FINISH_MILESTONE | Complete TBM Excavation Up Track (SZ) | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
75 | None | Interface Contractor Programme - 825 | Tue Sep 21 08:00:00 IST 2010 | Thu Dec 01 07:00:00 IST 2016
76 | FINISH_MILESTONE | TBM shaft for Contract 826 within Works Area 1.5 | Tue Jun 09 11:00:00 IDT 2015 | Tue Jun 09 11:00:00 IDT 2015
77 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - first time | Tue Sep 21 08:00:00 IST 2010 | Tue Sep 21 08:00:00 IST 2010
78 | FINISH_MILESTONE | Handover of Works Area 1.4B to 826 - second time | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
79 | TT_TASK | Cut & cover tunnel Bay 1 tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 20 08:00:00 IST 2014
80 | TT_TASK | Cut & cover tunnel Bay 2 tunnel construction | Sat Nov 30 08:00:00 IST 2013 | Mon Feb 17 08:00:00 IST 2014
81 | FINISH_MILESTONE | 826 to complete all works at interface and allow 825 access | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
82 | TT_TASK | 825 complete stitch joint to 826 tunnel | Sun May 01 07:00:00 IDT 2016 | Sat Jun 25 17:00:00 IDT 2016
83 | FINISH_MILESTONE | Return of Works Area 1.5 to 825 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
84 | None | Interface Contractor Programme - 830 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
85 | TT_TASK | Allow concrete pumping access for Contract 830 within Works Area 1.5 | Thu Dec 01 07:00:00 IST 2016 | Wed Mar 01 17:00:00 IST 2017
86 | None | Works Areas | Mon Sep 20 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
87 | None | Access Dates | Mon Sep 20 08:00:00 IST 2010 | Thu Nov 05 07:00:00 IST 2015
88 | START_MILESTONE | Works Area 1.3 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
89 | START_MILESTONE | Works Area 1.4A (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
90 | START_MILESTONE | Works Area 1.4B first time (36/2010, 13 Sep 10) | Mon Sep 20 08:00:00 IST 2010 | Mon Sep 20 08:00:00 IST 2010
91 | START_MILESTONE | Works Area 1.4B second time (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
92 | START_MILESTONE | Works Area 1.5 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
93 | START_MILESTONE | Works Area 1.6 (14/2013, 8 Apr 13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
94 | START_MILESTONE | Works Area 1.16 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
95 | START_MILESTONE | Works Area 1.17 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
96 | START_MILESTONE | Works Area 1.19 (47/2010, 29 Nov 10) | Mon Nov 29 08:00:00 IST 2010 | Mon Nov 29 08:00:00 IST 2010
97 | START_MILESTONE | Works Area 1.21 (825 Proposed to 01Feb13) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
98 | None | Return Dates | Fri Dec 17 08:00:00 IST 2010 | Tue Feb 28 17:00:00 IST 2017
99 | FINISH_MILESTONE | Works Area 1.3 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
100 | FINISH_MILESTONE | Works Area 1.4A (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
101 | FINISH_MILESTONE | Works Area 1.4B first time (01/2011, 9 Jan 11) | Fri Dec 17 08:00:00 IST 2010 | Fri Dec 17 08:00:00 IST 2010
102 | FINISH_MILESTONE | Works Area 1.4B second time (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
103 | FINISH_MILESTONE | Works Area 1.5 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
104 | FINISH_MILESTONE | Works Area 1.6 (19/2014, 11 May 14) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
105 | FINISH_MILESTONE | Works Area 1.16 (36/2013, 8 Sep 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
106 | FINISH_MILESTONE | Works Area 1.17 (50/2013, 15 Dec 13) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
107 | FINISH_MILESTONE | Works Area 1.19 (10 May 16) | Tue Feb 28 17:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017
108 | FINISH_MILESTONE | Works Area 1.21 (19/2015, 10 May 15) | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
109 | None | Specified Milestone Dates | Sun Apr 25 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
110 | None | Cost Centre A | Sun Jun 27 08:00:00 IDT 2010 | Fri Feb 24 17:00:00 IST 2017
111 | FINISH_MILESTONE | A1 (25/2010, 27 Jun 10) - Contractor's Submissions | Sun Jun 27 08:00:00 IDT 2010 | Sun Jun 27 08:00:00 IDT 2010
112 | FINISH_MILESTONE | A2 (51/2010, 26 Dec 10) - Approval of TBM Tunnelling method Statement | Wed Jan 05 08:00:00 IST 2011 | Wed Jan 05 08:00:00 IST 2011
113 | FINISH_MILESTONE | A3 (08/2011, 27 Feb 11) - Implementation of Specified Plans and Programming | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
114 | FINISH_MILESTONE | A4 (38/2011, 25 Sep 11) - Delivery of 2 nos. TBM to HGP Launching Shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
115 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of the MS of Construction of Cross Passages | Thu Feb 23 08:00:00 IST 2012 | Thu Feb 23 08:00:00 IST 2012
116 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Approval of Detailed Interface Require Specific with Designated Contractor | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
117 | FINISH_MILESTONE | A5 (34/2011, 28 Aug 11) - Implementation of Specified Plans | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
118 | FINISH_MILESTONE | A6 (08/2012, 26 Feb 12) - Implementation of Specified Plans and Programme | Fri Feb 24 08:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012
119 | FINISH_MILESTONE | A7 (25/2012, 24 Jun 12) - Approval of Detailed Interface Require Specific with Designated Contractor | Tue Jul 31 08:00:00 IDT 2012 | Tue Jul 31 08:00:00 IDT 2012
120 | FINISH_MILESTONE | A8 (34/2012, 26 Aug 12) - Implementation of Specified Plans | Wed Aug 22 08:00:00 IDT 2012 | Wed Aug 22 08:00:00 IDT 2012
121 | FINISH_MILESTONE | *A9 (48/2014, 30 Nov 14) - Complete 28% of the 1st tunnel drive | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 01 07:00:00 IST 2014
122 | FINISH_MILESTONE | A9a (08/2013, 24 Feb 13) - Implementation of Specific Plans and Program | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013
123 | FINISH_MILESTONE | *A9b (08/2014, 1 May 14) - Complete 15% of the 1st tunnel drive | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
124 | FINISH_MILESTONE | A10 (34/2013, 25 Aug 13) - Implementation of Specific Plans | Tue Jul 15 17:00:00 IDT 2014 | Tue Jul 15 17:00:00 IDT 2014
125 | FINISH_MILESTONE | *A11 (51/2015, 27 Dec 15) - Achieve Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
126 | FINISH_MILESTONE | A12 (32/2014, 10 Aug 14) - Approval of Draft O & M Manuals and Draft As-built drawings | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
127 | FINISH_MILESTONE | A13 (06/2015, 8 Feb 15) - Approval of Operating & Maintenance Mauls | Fri Feb 24 17:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017
128 | None | Cost Centre B | Sun Apr 25 08:00:00 IDT 2010 | Fri Apr 01 07:00:00 IDT 2016
129 | FINISH_MILESTONE | B1.1 (16/2010, 25 Apr 10) - Provide Evidence that TBM | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
130 | FINISH_MILESTONE | B1a (25/2010, 27 Jun 10) - On-demand bond or bank guarantee | Sat Jun 26 08:00:00 IDT 2010 | Sat Jun 26 08:00:00 IDT 2010
131 | FINISH_MILESTONE | B1.2 (28/2010, 18 Jul 10) - Provide Evidence that the STP | Thu Jul 29 08:00:00 IDT 2010 | Thu Jul 29 08:00:00 IDT 2010
132 | FINISH_MILESTONE | B2 (21/2011, 29 May 11) - Delivery of the 1st TBM | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
133 | FINISH_MILESTONE | B2a (38/2011, 25 Sep 11) - Delivery of the 2nd TBM | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
134 | FINISH_MILESTONE | B3 (49/2013, 8 Dec 13) - Complete Final Disassembly of TBM | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
135 | None | Cost Centre C (UT/S624) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
136 | FINISH_MILESTONE | C1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
137 | FINISH_MILESTONE | *C2 (17/2014, 27 Apr 14) - Complete 10% Tunnel Drive & 70% Segments | Fri Aug 01 07:00:00 IDT 2014 | Fri Aug 01 07:00:00 IDT 2014
138 | FINISH_MILESTONE | *C3 (52/2014, 28 Dec 14) - Complete 40% Tunnel Drive & 95% Segments | Mon Feb 23 07:00:00 IST 2015 | Mon Feb 23 07:00:00 IST 2015
139 | FINISH_MILESTONE | *C4 (26/2015, 28 Jun 15) - Complete 100% Tunnel Drive | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
140 | FINISH_MILESTONE | *C5 (35/2015, 30 Aug 15) -Complete 50% Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
141 | FINISH_MILESTONE | *C6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
142 | FINISH_MILESTONE | C7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
143 | None | Cost Centre D (DT/S623) | Sat Jun 29 17:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
144 | FINISH_MILESTONE | D1 (36/2012, 09SEP12) - Complete 5% Segment Manual | Sat Jun 29 17:00:00 IDT 2013 | Sat Jun 29 17:00:00 IDT 2013
145 | FINISH_MILESTONE | D2 (10/2013, 10MAR13) - Complete 5% Tunnel Drive & 40% Segments | Sat Mar 01 07:00:00 IST 2014 | Sat Mar 01 07:00:00 IST 2014
146 | FINISH_MILESTONE | *D3 (48/2014, 30 Nov 14) -Complete 28% Tunnel Drive & 85% Segments | Tue Jun 30 07:00:00 IDT 2015 | Tue Jun 30 07:00:00 IDT 2015
147 | FINISH_MILESTONE | *D4 (35/2015, 30 Aug 15) -Complete 100% Tunnel Drive | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
148 | FINISH_MILESTONE | *D5 (43/2015, 25 Oct 15) - Complete 50% of Tunnel invert & walkway | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
149 | FINISH_MILESTONE | *D6 (51/2015, 20 Dec 15) - Achieve Degree 1 Completion | Thu Apr 07 17:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
150 | FINISH_MILESTONE | D7 (25/2016) - Complete All Works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
151 | None | Cost Centre E (CP) | Thu Dec 16 08:00:00 IST 2010 | Sat Dec 31 17:00:00 IST 2016
152 | FINISH_MILESTONE | E1 (01/2011, 9 Jan 11) - Complete Ground Treatment | Thu Dec 16 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
153 | FINISH_MILESTONE | E2 (08/2011, 27 Feb 11) - Submit instrumentation | Mon Feb 28 08:00:00 IST 2011 | Mon Feb 28 08:00:00 IST 2011
154 | FINISH_MILESTONE | E3 (34/2011, 28 Aug 11) - Submit instrumentation | Mon Aug 29 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
155 | FINISH_MILESTONE | E4 (08/2012, 26 Feb 12) - Submit instrumentation | Sat Feb 25 08:00:00 IST 2012 | Sat Feb 25 08:00:00 IST 2012
156 | FINISH_MILESTONE | E5 (34/2012, 26 Aug 12) - Submit instrumentation | Sat Aug 25 08:00:00 IDT 2012 | Sat Aug 25 08:00:00 IDT 2012
157 | FINISH_MILESTONE | E6 (08/2013, 24 Feb 13) - Submit instrumentation | Mon Sep 30 08:00:00 IDT 2013 | Mon Sep 30 08:00:00 IDT 2013
158 | FINISH_MILESTONE | E7 (48/2013, 30 Nov 13) - Major ground treatment plant for CPs | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 01 07:00:00 IST 2015
159 | FINISH_MILESTONE | E8 (13/2015, 29 Mar 15) - Complete 4 Cross Passage Ground Treatment | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
160 | FINISH_MILESTONE | *E9 (51/2015, 20 Dec 15) - Deg 1 Completion in Cross Passage | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 07:00:00 IDT 2016
161 | FINISH_MILESTONE | E10 (25/2016) - All Works Complete | Sat Dec 31 17:00:00 IST 2016 | Sat Dec 31 17:00:00 IST 2016
162 | None | Construction and Site Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
163 | None | Surface Operations in Works Areas | Fri Aug 06 08:00:00 IDT 2010 | Tue Oct 31 08:00:00 IST 2017
164 | None | Huanggang Park | Tue Nov 02 08:00:00 IST 2010 | Tue Oct 31 08:00:00 IST 2017
165 | TT_TASK | Establish MTRC Project Office in Shenzhen | Tue Nov 02 08:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010
166 | TT_TASK | Establish 826 HGP Site Office | Tue Nov 30 08:00:00 IST 2010 | Mon Jan 17 08:00:00 IST 2011
167 | TT_TASK | University Games Period | Mon Aug 01 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
168 | TT_TASK | Operation and maintenance of ground support facilities during tunnel construction | Tue Dec 31 08:00:00 IST 2013 | Tue Oct 31 08:00:00 IST 2017
169 | None | Mai Po Retrieval Shaft | Fri Aug 06 08:00:00 IDT 2010 | Tue Apr 21 08:00:00 IDT 2015
170 | None | Ground Treatment Works | Fri Aug 06 08:00:00 IDT 2010 | Tue Feb 01 08:00:00 IST 2011
171 | FINISH_MILESTONE | Submit Inspection and Testing Plan for ground treatment works | Fri Aug 06 08:00:00 IDT 2010 | Fri Aug 06 08:00:00 IDT 2010
172 | TT_TASK | Engineer's review on Inspection and Testing Plan | Fri Aug 06 08:00:00 IDT 2010 | Fri Sep 03 08:00:00 IDT 2010
173 | TT_TASK | Establish Works Area 1.4B with 825 Contractor | Mon Sep 20 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
174 | TT_TASK | Set up grouting plant | Tue Oct 05 08:00:00 IST 2010 | Fri Oct 15 08:00:00 IST 2010
175 | TT_TASK | Drilling - Down Track tunnel | Thu Oct 07 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
176 | TT_TASK | Drilling - Up Track tunnel | Mon Oct 18 08:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010
177 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 04 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
178 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 11 08:00:00 IST 2010 | Sat Nov 27 08:00:00 IST 2010
179 | TT_TASK | TAM Grouting works - Down Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
180 | TT_TASK | TAM Grouting works - Up Track tunnel | Thu Nov 18 08:00:00 IST 2010 | Sat Dec 04 08:00:00 IST 2010
181 | TT_TASK | Permeability testing - Down Track tunnel | Tue Dec 07 08:00:00 IST 2010 | Mon Dec 13 08:00:00 IST 2010
182 | TT_TASK | Permeability testing - Up Track tunnel | Wed Dec 08 08:00:00 IST 2010 | Tue Dec 14 08:00:00 IST 2010
183 | TT_TASK | Demobilise grout plant | Mon Dec 13 08:00:00 IST 2010 | Sat Dec 18 08:00:00 IST 2010
184 | TT_TASK | Clear Works Area 1.4B for 825 Contractor's D.Wall | Mon Dec 13 08:00:00 IST 2010 | Wed Dec 22 08:00:00 IST 2010
185 | TT_TASK | Install instrumentation and monitoring equipment | Thu Oct 28 08:00:00 IST 2010 | Tue Feb 01 08:00:00 IST 2011
186 | None | Jet Grouting Works for TBM Break-out | Tue Dec 31 08:00:00 IST 2013 | Tue Nov 18 08:00:00 IST 2014
187 | TT_TASK | Submit Method Statement for Jet Grouting Works | Tue Dec 31 08:00:00 IST 2013 | Thu Mar 27 08:00:00 IST 2014
188 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
189 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 22 08:00:00 IST 2014
190 | TT_TASK | Trial of Jet grouting | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 27 08:00:00 IST 2014
191 | TT_TASK | Jet Grouting Works | Fri Jul 18 08:00:00 IDT 2014 | Tue Nov 18 08:00:00 IST 2014
192 | None | Ground Freezing Plant | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
193 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Ground freezing | Tue Mar 24 08:00:00 IST 2015 | Tue Mar 24 08:00:00 IST 2015
194 | TT_TASK | Engineer's review on Inspection and Testing Plan | Tue Mar 24 08:00:00 IST 2015 | Tue Apr 21 08:00:00 IDT 2015
195 | None | TBM Drives from Boundary to Mai Po Shaft | Fri May 10 08:00:00 IDT 2013 | Thu Dec 01 07:00:00 IST 2016
196 | None | Down Track - Ch.115+929 to Ch.117+400 | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 16 17:00:00 IST 2015
197 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 01 08:00:00 IST 2014
198 | TT_TASK | Continue S623 drive, ch. 115+929 to ch. 115+950 in soil | Sun Dec 01 08:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013
199 | TT_TASK | Continue S623 drive, ch. 115+950 to ch. 115+983 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Sat Jan 04 08:00:00 IST 2014
200 | TT_TASK | Continue S623 drive, ch. 115+983 to ch. 116+050 in soil | Tue Dec 31 08:00:00 IST 2013 | Wed Jan 08 08:00:00 IST 2014
201 | TT_TASK | Continue S623 drive, ch. 116+050 to ch. 116+213 in mixed ground | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
202 | TT_TASK | Continue S623 drive, ch. 116+213 to ch. 116+230 in soil | Tue Apr 01 08:00:00 IDT 2014 | Thu Apr 03 08:00:00 IDT 2014
203 | TT_TASK | Continue S623 drive, ch. 116+230 to ch. 116+260 in marble | Tue Apr 01 08:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014
204 | TT_TASK | Continue S623 drive, ch. 116+260 to ch. 116+284 in marble | Tue Jul 01 08:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014
205 | TT_TASK | TBM Cutter Head Repair & S624 Overtaking Stoppage | Fri Aug 01 08:00:00 IDT 2014 | Fri Oct 24 08:00:00 IDT 2014
206 | TT_TASK | Continue S623 drive, ch. 116+284 to ch. 116+319 in marble | Fri Nov 21 07:00:00 IST 2014 | Mon Dec 01 17:00:00 IST 2014
207 | TT_TASK | Continue S623 drive, ch. 116+319 to ch. 116+349 in marble | Wed Feb 04 07:00:00 IST 2015 | Fri Feb 13 17:00:00 IST 2015
208 | TT_TASK | Continue S623 drive, ch. 116+349 to ch. 116+379 in marble | Sun Feb 01 07:00:00 IST 2015 | Tue Feb 10 17:00:00 IST 2015
209 | TT_TASK | Continue S623 drive, ch. 116+379 to ch. 116+408 in marble | Sun Mar 01 07:00:00 IST 2015 | Thu Mar 05 01:00:00 IST 2015
210 | TT_TASK | Continue S623 drive, ch. 116+408 to ch. 116+430 in marble | Sun Mar 01 07:00:00 IST 2015 | Sat Mar 07 17:00:00 IST 2015
211 | TT_TASK | Continue S623 drive, ch. 116+430 to ch. 116+600 in soil | Sun Mar 01 07:00:00 IST 2015 | Mon Mar 30 17:00:00 IDT 2015
212 | TT_TASK | Continue S623 drive, ch. 116+600 to ch. 116+694 in soil | Fri Jul 17 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
213 | TT_TASK | Continue S623 drive, ch. 116+694 to ch. 116+927 in Alluvial zone | Tue Jun 30 07:00:00 IDT 2015 | Thu Sep 17 17:00:00 IDT 2015
214 | TT_TASK | Continue S623 drive, ch. 116+927 to ch. 116+945 in soil | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
215 | TT_TASK | Continue S623 drive, ch. 116+945 to ch. 117+400 in soil | Tue Sep 29 07:00:00 IDT 2015 | Wed Dec 16 17:00:00 IST 2015
216 | TT_TASK | Pre-coring at diaphragm wall after TBM S623 arrival | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
217 | TT_TASK | TBM Breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
218 | None | S623 TBM Removal | Thu Oct 22 07:00:00 IDT 2015 | Thu Dec 01 07:00:00 IST 2016
219 | TT_TASK | Move TBM S623 front portion to cradle | Thu Oct 22 07:00:00 IDT 2015 | Tue Oct 27 17:00:00 IST 2015
220 | TT_TASK | Weld additional bracing brackets corbels | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
221 | TT_TASK | Install cradle on lateral shifting system | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
222 | TT_TASK | Move and shift TBM to dismantle location | Thu Apr 07 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
223 | TT_TASK | Dismantle Cutter Head & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
224 | TT_TASK | Dismantle TBM rear & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
225 | TT_TASK | Dismantle segment installation machine & Remove | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
226 | TT_TASK | Dismantle TBM middle sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
227 | TT_TASK | Dismantle TBM front sheild & Remove | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
228 | TT_TASK | Dismantle S623 Link Bridge & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
229 | TT_TASK | Dismantle S623 Wagon #1 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
230 | TT_TASK | Dismantle S623 Wagon #2 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
231 | TT_TASK | Dismantle S623 Wagon #3 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
232 | TT_TASK | Dismantle S623 Wagon #4 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
233 | TT_TASK | Dismantle S623 Wagon #5 & Remove | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
234 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N1 | Thu Jun 23 07:00:00 IDT 2016 | Thu Jun 23 07:00:00 IDT 2016
235 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 623N2 | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
236 | TT_TASK | Site clearance | Fri Apr 01 07:00:00 IDT 2016 | Tue Sep 27 17:00:00 IDT 2016
237 | None | Up Track - Ch.115+940 to Ch.117+413 | Fri May 10 08:00:00 IDT 2013 | Fri Oct 09 17:00:00 IDT 2015
238 | TT_TASK | Anticipated handover at Boundary from GSG Contractor | Fri May 10 08:00:00 IDT 2013 | Sat May 11 08:00:00 IDT 2013
239 | TT_TASK | Continue S624 drive, ch. 115+939 to ch. 115+950 in soil | Fri May 09 08:00:00 IDT 2014 | Sat May 10 08:00:00 IDT 2014
240 | TT_TASK | Continue S624 drive, ch. 115+950 to ch. 115+987 in mixed ground | Fri May 09 08:00:00 IDT 2014 | Tue May 13 08:00:00 IDT 2014
241 | TT_TASK | Continue S624 drive, ch. 115+987 to ch. 116+050 in soil | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 08:00:00 IDT 2014
242 | TT_TASK | Continue S624 drive, ch. 116+050 to ch. 116+226 in mixed ground | Sun Jun 01 08:00:00 IDT 2014 | Wed Jul 02 08:00:00 IDT 2014
243 | TT_TASK | Continue S624 drive, ch. 116+226 to ch. 116+240 in soil/marble | Fri Aug 01 08:00:00 IDT 2014 | Sun Aug 03 08:00:00 IDT 2014
244 | TT_TASK | Continue S624 drive, ch. 116+240 to ch. 116+270 in marble | Fri Aug 01 08:00:00 IDT 2014 | Wed Aug 13 08:00:00 IDT 2014
245 | TT_TASK | Continue S624 drive, ch. 116+270 to ch. 116+300 in marble | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014
246 | TT_TASK | Continue S624 drive, ch. 116+300 to ch. 116+329 in marble | Wed Oct 01 08:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014
247 | TT_TASK | Continue S624 drive, ch. 116+329 to ch. 116+358 in marble | Sat Nov 01 07:00:00 IST 2014 | Mon Nov 17 17:00:00 IST 2014
248 | TT_TASK | Continue S624 drive, ch. 116+358 to ch. 116+388 in marble | Sun Nov 23 07:00:00 IST 2014 | Tue Dec 02 17:00:00 IST 2014
249 | TT_TASK | Continue S624 drive, ch. 116+388 to ch. 116+415 in marble | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 02 17:00:00 IST 2015
250 | TT_TASK | Continue S624 drive, ch. 116+415 to ch. 116+430 in soil/marble | Sun Jan 11 07:00:00 IST 2015 | Tue Jan 13 17:00:00 IST 2015
251 | TT_TASK | Continue S624 drive, ch. 116+430 to ch. 116+600 in soil | Tue Jan 13 07:00:00 IST 2015 | Wed Feb 11 17:00:00 IST 2015
252 | TT_TASK | Continue S624 drive, ch. 116+600 to ch. 116+850 in soil/Alluv. zone | Wed Jan 21 07:00:00 IST 2015 | Thu Mar 05 17:00:00 IST 2015
253 | TT_TASK | Continue S624 drive, ch. 116+850 to ch. 116+930 in Alluv. zone | Tue Mar 31 07:00:00 IDT 2015 | Mon Apr 13 17:00:00 IDT 2015
254 | TT_TASK | Continue S624 drive, ch. 116+930 to ch. 117+413 in soil at Mai Po | Thu Jul 16 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
255 | TT_TASK | Pre-coring at diaphragm wall after TBM S624 arrival | Sat Aug 15 07:00:00 IDT 2015 | Mon Aug 17 17:00:00 IDT 2015
256 | TT_TASK | TBM S624 breakthrough at Mai Po Shaft | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
257 | None | TBM Removal Preparation | Mon Dec 01 07:00:00 IST 2014 | Wed Nov 11 17:00:00 IST 2015
258 | TT_TASK | Prepare TTMS report for removal of TBM S624 & S623 | Mon Dec 01 07:00:00 IST 2014 | Mon Dec 15 17:00:00 IST 2014
259 | TT_TASK | Working Group Meeting & SLG Meeting | Fri Jan 16 07:00:00 IST 2015 | Wed Apr 15 17:00:00 IDT 2015
260 | TT_TASK | Drawings' approval and endosement from RDO | Mon Feb 23 07:00:00 IST 2015 | Mon Mar 09 17:00:00 IST 2015
261 | TT_TASK | Submit advance notice to the HK Police | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
262 | TT_TASK | On stie preparation works | Mon Jul 13 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
263 | TT_TASK | Proof drilling for water tightness test of jet grout block | Wed Jul 01 07:00:00 IDT 2015 | Tue Jul 07 17:00:00 IDT 2015
264 | TT_TASK | Shaft bottom slab levelling | Fri Jul 24 07:00:00 IDT 2015 | Sat Jul 25 17:00:00 IDT 2015
265 | TT_TASK | Moving device and cradle installation | Thu Jul 23 07:00:00 IDT 2015 | Wed Aug 19 17:00:00 IDT 2015
266 | None | S624 TBM Removal | Tue Sep 29 07:00:00 IDT 2015 | Sun Nov 08 17:00:00 IST 2015
267 | TT_TASK | Move TBM S624 front portion to cradle | Tue Oct 13 07:00:00 IDT 2015 | Sun Oct 18 17:00:00 IDT 2015
268 | TT_TASK | Weld additional bracing brackets corbels | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
269 | TT_TASK | Install cradle on lateral shifting system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
270 | TT_TASK | Move and shift TBM to dismantle location | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
271 | TT_TASK | Dismantle Cutter Head & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
272 | TT_TASK | Dismantle TBM front sheild & Remove | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
273 | TT_TASK | Dismantle segment installation machine & Remove | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
274 | TT_TASK | Dismantle TBM middle sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
275 | TT_TASK | Dismantle TBM rear sheild & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
276 | TT_TASK | Dismantle S624 Link Bridge & Remove | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
277 | TT_TASK | Dismantle S624 Wagon #1 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
278 | TT_TASK | Dismantle S624 Wagon #2 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
279 | TT_TASK | Dismantle S624 Wagon #3 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
280 | TT_TASK | Dismantle S624 Wagon #4 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
281 | TT_TASK | Dismantle S624 Wagon #5 & Remove | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
282 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N1 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
283 | START_MILESTONE | Transport TBM components from site to the ferry pier at night - 624N2 | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 07:00:00 IST 2015
284 | None | Cross Passages (HK) | Wed Oct 01 07:00:00 IDT 2014 | Thu Aug 04 17:00:00 IDT 2016
285 | None | Freezing Station A | Sat Oct 11 07:00:00 IDT 2014 | Mon Nov 09 17:00:00 IST 2015
286 | TT_TASK | Erect Freezing Station Platform | Sat Oct 11 07:00:00 IDT 2014 | Tue Oct 21 17:00:00 IDT 2014
287 | TT_TASK | Freezing Station Installation & Testing | Thu Jan 01 07:00:00 IST 2015 | Sat Jan 31 17:00:00 IST 2015
288 | TT_TASK | Remove Freezing Station A | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
289 | None | Cross Passage #1. Ch.116+030 | Wed Oct 01 07:00:00 IDT 2014 | Tue May 10 17:00:00 IDT 2016
290 | TT_TASK | Erect Temporary Drilling Platform | Wed Oct 01 07:00:00 IDT 2014 | Fri Oct 10 17:00:00 IDT 2014
291 | TT_TASK | Drill & Install Freezing Pipe | Mon Dec 01 07:00:00 IST 2014 | Wed Jan 14 17:00:00 IST 2015
292 | TT_TASK | Install temporary support including ring support (Up-track) | Sun Feb 01 07:00:00 IST 2015 | Sun Feb 15 17:00:00 IST 2015
293 | TT_TASK | Install temporary support including ring support (Down-track) | Mon Feb 23 07:00:00 IST 2015 | Fri Mar 06 17:00:00 IST 2015
294 | TT_TASK | Intall safe door | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 25 17:00:00 IDT 2015
295 | TT_TASK | Install freezing & monitoring system | Mon Feb 23 07:00:00 IST 2015 | Sat Feb 28 17:00:00 IST 2015
296 | TT_TASK | Conduct Ground Freezing | Sun Mar 01 07:00:00 IST 2015 | Tue Apr 14 17:00:00 IDT 2015
297 | TT_TASK | Maintain ground freezing during construction of CP | Tue Apr 21 07:00:00 IDT 2015 | Sun Jun 14 17:00:00 IDT 2015
298 | TT_TASK | Tunnel segment cutting & removal | Tue Apr 21 07:00:00 IDT 2015 | Wed Apr 22 17:00:00 IDT 2015
299 | TT_TASK | Excavate and temporary support | Tue Apr 21 07:00:00 IDT 2015 | Sat May 23 17:00:00 IDT 2015
300 | TT_TASK | Tunnel segment removal | Tue Aug 04 07:00:00 IDT 2015 | Mon Aug 10 17:00:00 IDT 2015
301 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Jul 03 07:00:00 IDT 2015 | Thu Jul 09 17:00:00 IDT 2015
302 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 08 17:00:00 IDT 2015
303 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
304 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
305 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
306 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
307 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
308 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
309 | TT_TASK | Remove formwork | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
310 | TT_TASK | Concrete achieved the design strength | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
311 | TT_TASK | Remove temporary works | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
312 | TT_TASK | Remove Freezing Plant | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
313 | TT_TASK | Thawing & Proof Grouting | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
314 | TT_TASK | Make Good Freezing Pipe Hole | Sun May 01 07:00:00 IDT 2016 | Tue May 10 17:00:00 IDT 2016
315 | None | Cross Passage #2. Ch.116+195 | Mon Feb 23 07:00:00 IST 2015 | Sun Apr 10 17:00:00 IDT 2016
316 | TT_TASK | Erect Temporary Drilling Platform | Mon Feb 23 07:00:00 IST 2015 | Wed Feb 25 17:00:00 IST 2015
317 | TT_TASK | Drill & Install Freezing Pipe | Mon Feb 23 07:00:00 IST 2015 | Fri Apr 10 17:00:00 IDT 2015
318 | TT_TASK | Install temporary support (including ring support) | Tue Apr 21 07:00:00 IDT 2015 | Tue May 05 17:00:00 IDT 2015
319 | TT_TASK | Install safe door | Mon Jun 01 07:00:00 IDT 2015 | Thu Jun 04 17:00:00 IDT 2015
320 | TT_TASK | Install freezing & monitoring system | Tue Apr 21 07:00:00 IDT 2015 | Thu Apr 23 17:00:00 IDT 2015
321 | TT_TASK | Conduct Ground Freezing | Tue Apr 21 07:00:00 IDT 2015 | Tue Jun 16 17:00:00 IDT 2015
322 | TT_TASK | Maintain ground freezing during construction of CP | Fri Jul 24 07:00:00 IDT 2015 | Mon Sep 21 17:00:00 IDT 2015
323 | TT_TASK | Tunnel segment cutting & removal | Fri Jul 24 07:00:00 IDT 2015 | Thu Jul 30 17:00:00 IDT 2015
324 | TT_TASK | Excavate and temporary support | Sun Jul 26 07:00:00 IDT 2015 | Thu Aug 27 17:00:00 IDT 2015
325 | TT_TASK | Tunnel segment removal | Mon Aug 03 07:00:00 IDT 2015 | Tue Aug 04 17:00:00 IDT 2015
326 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
327 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
328 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
329 | TT_TASK | Lining concreting (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
330 | TT_TASK | Lining concrete curing (floor) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 17:00:00 IDT 2015
331 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
332 | TT_TASK | Lining concreting (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Wed Sep 30 17:00:00 IDT 2015
333 | TT_TASK | Lining concrete curing (side walls and roof) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
334 | TT_TASK | Remove formwork | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
335 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
336 | TT_TASK | Remove temporary works | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
337 | TT_TASK | Remove Freezing Pipes | Sat Nov 14 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
338 | TT_TASK | Thawing & Proof Grouting | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
339 | TT_TASK | Make Good Freezing Pipe Holes | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
340 | None | Freezing Station B | Mon Jun 01 07:00:00 IDT 2015 | Thu Aug 04 17:00:00 IDT 2016
341 | TT_TASK | Erect Freezing Station Platform | Mon Jun 01 07:00:00 IDT 2015 | Sat Jun 20 17:00:00 IDT 2015
342 | TT_TASK | Freezing Station Installation & Testing | Sun Jun 21 07:00:00 IDT 2015 | Fri Jul 10 17:00:00 IDT 2015
343 | TT_TASK | Remove Station B | Fri Jul 22 07:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016
344 | None | Cross Passage #3. Ch. 116+445 | Tue Apr 21 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
345 | TT_TASK | Erect Temporary Drilling Platform | Tue Apr 21 07:00:00 IDT 2015 | Sun Apr 26 17:00:00 IDT 2015
346 | TT_TASK | Drill & Install Freezing Pipe | Tue Apr 21 07:00:00 IDT 2015 | Fri Jun 05 17:00:00 IDT 2015
347 | TT_TASK | Install temporary support (including ring support) | Sun Jul 19 07:00:00 IDT 2015 | Sun Aug 02 17:00:00 IDT 2015
348 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
349 | TT_TASK | Install freezing & monitoring system | Wed Jul 01 07:00:00 IDT 2015 | Fri Jul 03 17:00:00 IDT 2015
350 | TT_TASK | Conduct Ground Freezing | Sat Jul 04 07:00:00 IDT 2015 | Fri Aug 28 17:00:00 IDT 2015
351 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Sep 29 07:00:00 IDT 2015 | Fri Dec 18 17:00:00 IST 2015
352 | TT_TASK | Tunnel segment cutting & removal at U/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
353 | TT_TASK | Excavate and temporary support | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 31 17:00:00 IST 2015
354 | TT_TASK | Tunnel segment removal at D/T | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
355 | TT_TASK | Earthing, Waterproof works and waterproof test | Tue Sep 29 07:00:00 IDT 2015 | Mon Oct 05 17:00:00 IDT 2015
356 | TT_TASK | Portal works | Tue Sep 29 07:00:00 IDT 2015 | Wed Oct 28 17:00:00 IST 2015
357 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Tue Sep 29 07:00:00 IDT 2015 | Sun Oct 04 17:00:00 IDT 2015
358 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
359 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 12 17:00:00 IST 2015
360 | TT_TASK | Lining concreting (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
361 | TT_TASK | Lining concrete curing (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
362 | TT_TASK | Make Good Freezing Pipe Hole | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
363 | TT_TASK | Concrete achieved the design strength | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
364 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
365 | TT_TASK | Remove temp. works, ring support and temp. platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
366 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
367 | None | Cross Passage #4. Ch. 116+671 | Mon Jul 06 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
368 | TT_TASK | Erect Temporary Drilling Platform | Sun Jul 19 07:00:00 IDT 2015 | Thu Jul 23 17:00:00 IDT 2015
369 | TT_TASK | Drill & Install Freezing Pipe | Mon Jul 06 07:00:00 IDT 2015 | Thu Aug 20 17:00:00 IDT 2015
370 | TT_TASK | Install temporary support (including ring support) | Tue Sep 29 07:00:00 IDT 2015 | Tue Oct 13 17:00:00 IDT 2015
371 | TT_TASK | Install safe door | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 02 17:00:00 IDT 2015
372 | TT_TASK | Install freezing & monitoring system | Tue Sep 29 07:00:00 IDT 2015 | Thu Oct 01 17:00:00 IDT 2015
373 | TT_TASK | Conduct Ground Freezing | Tue Sep 29 07:00:00 IDT 2015 | Mon Nov 23 17:00:00 IST 2015
374 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Thu Nov 05 07:00:00 IST 2015 | Fri Feb 19 17:00:00 IST 2016
375 | TT_TASK | Tunnel segment cutting & removal at U/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
376 | TT_TASK | Excavate and temporary support | Mon Nov 09 07:00:00 IST 2015 | Wed Nov 25 17:00:00 IST 2015
377 | TT_TASK | Earthing, Waterproof works and waterproof test | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
378 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
379 | TT_TASK | Lining concreting (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
380 | TT_TASK | Lining concrete curing (floor) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
381 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
382 | TT_TASK | Lining concreting (side walls and roof) | Tue Nov 10 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
383 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
384 | TT_TASK | Remove formwork | Fri Apr 08 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
385 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
386 | TT_TASK | Remove temp. works and ring support | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
387 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
388 | TT_TASK | Construct Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
389 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
390 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Sat Nov 07 17:00:00 IST 2015
391 | TT_TASK | Erect temp. working platform | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
392 | TT_TASK | Drilling remaining holes at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
393 | TT_TASK | Install ring support at D/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
394 | TT_TASK | Tunnel segment removal at D/T | Thu Nov 05 07:00:00 IST 2015 | Sat Nov 07 17:00:00 IST 2015
395 | None | Cross Passage #5. Ch. 116+966 | Wed Jul 01 07:00:00 IDT 2015 | Sat Apr 30 17:00:00 IDT 2016
396 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+066); last gantry passed CP5 | Wed Jul 01 07:00:00 IDT 2015 | Wed Jul 01 07:00:00 IDT 2015
397 | TT_TASK | Erect Temporary Drilling Platform at U/T | Tue Sep 29 07:00:00 IDT 2015 | Sat Oct 03 17:00:00 IDT 2015
398 | START_MILESTONE | TBM S623 C/W exited Alluvial zone at S1425/Ch. 116+927 (* Note1) | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
399 | TT_TASK | TBM S623 C/W boring from Ch. 116+927 to Ch. 116+986 (CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 09 17:00:00 IDT 2015
400 | TT_TASK | Drill & Install Freezing Pipe at U/T | Sat Oct 10 07:00:00 IDT 2015 | Tue Nov 24 17:00:00 IST 2015
401 | TT_TASK | Raise track rail, slurry pipes diversion, install temp. support at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
402 | TT_TASK | Install Ring Support | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
403 | TT_TASK | Install freezing & monitoring system | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 05 17:00:00 IST 2015
404 | TT_TASK | Freezing system Test & Commissioning | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
405 | TT_TASK | Conduct Ground Freezing (Active phase) | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 24 17:00:00 IST 2015
406 | LEVEL_OF_EFFORT | Maintain ground freezing during construction of CP | Tue Dec 01 07:00:00 IST 2015 | Sun Mar 20 17:00:00 IST 2016
407 | TT_TASK | Install safe door (both sides) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
408 | TT_TASK | Tunnel segment cutting & removal at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
409 | TT_TASK | Excavate and temporary support (excavation from D/T) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
410 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
411 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
412 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
413 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
414 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
415 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
416 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
417 | TT_TASK | Remove formwork | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
418 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
419 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
420 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
421 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
422 | TT_TASK | Make Good Freezing Pipe Hole | Fri Apr 01 07:00:00 IDT 2016 | Mon Apr 04 17:00:00 IDT 2016
423 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Fri Nov 27 17:00:00 IST 2015
424 | TT_TASK | TBM S623 C/W boring from Ch.. 116+986 to Ch117+086 (last gantry passed CP5+20m) (* Note 2) | Tue Sep 29 07:00:00 IDT 2015 | Fri Oct 16 17:00:00 IDT 2015
425 | TT_TASK | Erect Temporary Drilling Platorm at D/T | Thu Nov 05 07:00:00 IST 2015 | Mon Nov 09 17:00:00 IST 2015
426 | TT_TASK | Drilling remaining holes at D/T after S623 gantries passed | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 27 17:00:00 IST 2015
427 | TT_TASK | Install ring support at D/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
428 | None | Cross Passage #6. Ch. 117+216 | Sat Aug 01 07:00:00 IDT 2015 | Wed Jun 15 17:00:00 IDT 2016
429 | START_MILESTONE | S624 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Sat Aug 01 07:00:00 IDT 2015 | Sat Aug 01 07:00:00 IDT 2015
430 | TT_TASK | Erect Drilling Platform at U/T | Thu Nov 05 07:00:00 IST 2015 | Wed Nov 11 17:00:00 IST 2015
431 | TT_TASK | Drill ground freezing holes at U/T | Thu Nov 05 07:00:00 IST 2015 | Fri Dec 04 17:00:00 IST 2015
432 | TT_TASK | Install Ring Support at U/T | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
433 | TT_TASK | Install freezing & monitoring system at U/T | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
434 | TT_TASK | Freezing system Test & Commissioning at U/T, Station B | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
435 | TT_TASK | Conduct Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Thu May 19 17:00:00 IDT 2016
436 | LEVEL_OF_EFFORT | Maintain Ground Freezing | Fri Apr 01 07:00:00 IDT 2016 | Wed Jun 15 17:00:00 IDT 2016
437 | TT_TASK | Install safe door (both sides) | Sun Apr 10 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
438 | TT_TASK | Tunnel segment removal | Sat Apr 16 07:00:00 IDT 2016 | Wed Apr 20 17:00:00 IDT 2016
439 | TT_TASK | Excavate and temporary support (excavation from U/T side only) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 21 17:00:00 IDT 2016
440 | TT_TASK | Earthing, Waterproof works and waterproof test | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
441 | TT_TASK | Lining reinforcement fixing and formwork (floor) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
442 | TT_TASK | Lining concreting (floor) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
443 | TT_TASK | Lining concrete curing (floor) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
444 | TT_TASK | Lining reinforcement fixing and formwork (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
445 | TT_TASK | Lining concreting (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
446 | TT_TASK | Lining concrete curing (side walls and roof) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
447 | TT_TASK | Concrete achieved the design strength | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
448 | TT_TASK | Remove formwork & Remove safe doors | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 01 17:00:00 IDT 2016
449 | TT_TASK | Remove Ring Support | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
450 | TT_TASK | Remove working platform | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
451 | TT_TASK | Thawing & Proof Grouting | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
452 | TT_TASK | Make Good Freezing Pipe Hole | Mon Apr 11 07:00:00 IDT 2016 | Thu Apr 14 17:00:00 IDT 2016
453 | None | Works at Down-Track | Tue Sep 29 07:00:00 IDT 2015 | Mon Apr 11 17:00:00 IDT 2016
454 | START_MILESTONE | S623 TBM C/W passed (Ch. 117+316); last gantry passed CP6 | Tue Sep 29 07:00:00 IDT 2015 | Tue Sep 29 07:00:00 IDT 2015
455 | TT_TASK | Erect Working Platform at D/T | Thu Nov 05 07:00:00 IST 2015 | Sun Nov 08 17:00:00 IST 2015
456 | TT_TASK | Drill ground freezing holes at D/T | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
457 | TT_TASK | Install freezing & monitoring system at D/T | Fri Apr 01 07:00:00 IDT 2016 | Tue Apr 05 17:00:00 IDT 2016
458 | TT_TASK | Ring support installation at D/T | Wed Apr 06 07:00:00 IDT 2016 | Mon Apr 11 17:00:00 IDT 2016
459 | None | Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
460 | None | Down Track Tunnel Finishes | Thu Nov 05 07:00:00 IST 2015 | Sat Dec 24 17:00:00 IST 2016
461 | None | Tunnel Invert Slab (DT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 30 17:00:00 IDT 2016
462 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m-64=25m) | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
463 | TT_TASK | Invert Slab at CP1 (30m) | Sun May 29 07:00:00 IDT 2016 | Mon May 30 17:00:00 IDT 2016
464 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) | Sat May 21 07:00:00 IDT 2016 | Sat May 28 17:00:00 IDT 2016
465 | TT_TASK | Invert Slab at CP2 (30m) | Sat May 21 07:00:00 IDT 2016 | Sun May 22 17:00:00 IDT 2016
466 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Sun May 08 07:00:00 IDT 2016 | Fri May 20 17:00:00 IDT 2016
467 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
468 | TT_TASK | Invert Slab between CP3 and CP4 (226-45=181m) | Fri Apr 29 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
469 | TT_TASK | Invert Slab at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
470 | TT_TASK | Invert Slab between CP4 and CP5 (296-59=237m) | Thu Apr 14 07:00:00 IDT 2016 | Thu Apr 28 17:00:00 IDT 2016
471 | TT_TASK | Invert Slab at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
472 | TT_TASK | Invert Slab between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
473 | TT_TASK | Invert Slab at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
474 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (14m) | Thu Apr 07 07:00:00 IDT 2016 | Fri Apr 08 17:00:00 IDT 2016
475 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Thu Apr 07 07:00:00 IDT 2016 | Sat Apr 16 17:00:00 IDT 2016
476 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
477 | None | Lower Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
478 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
479 | TT_TASK | Lower Wkys at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
480 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
481 | TT_TASK | Lower Wks at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
482 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
483 | TT_TASK | Lower Wkys at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
484 | TT_TASK | Lower Wkys between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
485 | TT_TASK | Lower Wkys at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
486 | TT_TASK | Lower Wkys between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
487 | TT_TASK | Lower Wkys at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
488 | TT_TASK | Lower Wkys between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
489 | TT_TASK | Lower Wkys at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
490 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
491 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
492 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
493 | None | Upper Walkway (DT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
494 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m-64=25m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
495 | TT_TASK | Upper Wky at CP1 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
496 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
497 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
498 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
499 | TT_TASK | Upper Wky at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
500 | TT_TASK | Upper Wky between CP3 and CP4 (226-45=181m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
501 | TT_TASK | Upper Wky at CP4 (60m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
502 | TT_TASK | Upper Wky between CP4 and CP5 (296-59=237m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
503 | TT_TASK | Upper Wky at CP5 (58m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
504 | TT_TASK | Upper Wky between CP5 and CP6 (250-39=211m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
505 | TT_TASK | Upper Wky at CP6 (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
506 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (14m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
507 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (190-10-14-20=146m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
508 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (12m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
509 | None | DT Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Sat Dec 24 17:00:00 IST 2016
510 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish works | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
511 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
512 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
513 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
514 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
515 | None | Double Gates (DT) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
516 | TT_TASK | Install double gates at 20m south of CP6 | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
517 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
518 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
519 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
520 | None | Up Track Tunnel Finishes to Deg. 1 | Thu Nov 05 07:00:00 IST 2015 | Thu Dec 22 17:00:00 IST 2016
521 | None | Tunnel Invert Slab (UT) | Thu Nov 05 07:00:00 IST 2015 | Mon May 02 17:00:00 IDT 2016
522 | TT_TASK | Invert Slab between HK Boundary and CP1 (104-15=89m) | Tue Apr 26 07:00:00 IDT 2016 | Sun May 01 17:00:00 IDT 2016
523 | TT_TASK | Invert Slab at CP1 (30m) | Tue Apr 26 07:00:00 IDT 2016 | Wed Apr 27 17:00:00 IDT 2016
524 | TT_TASK | Invert Slab between CP1 and CP2 (164-30=134m) incl. Station A area | Mon Apr 18 07:00:00 IDT 2016 | Mon Apr 25 17:00:00 IDT 2016
525 | TT_TASK | Invert Slab at CP2 (30m) | Mon Apr 18 07:00:00 IDT 2016 | Tue Apr 19 17:00:00 IDT 2016
526 | TT_TASK | Invert Slab between CP2 and CP3 (250-30=220m) | Tue Apr 05 07:00:00 IDT 2016 | Sun Apr 17 17:00:00 IDT 2016
527 | TT_TASK | Invert Slab at CP3 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
528 | TT_TASK | Invert Slab between CP3 and CP4 (226-47-34=145m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 13 17:00:00 IST 2015
529 | TT_TASK | Invert Slab at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
530 | TT_TASK | Invert Slab at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
531 | TT_TASK | Invert Slab between CP4 and CP5 (296-51=245m) | Thu Nov 05 07:00:00 IST 2015 | Thu Nov 19 17:00:00 IST 2015
532 | TT_TASK | Invert Slab at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
533 | TT_TASK | Invert Slab between CP5 and CP6 (250-32=218m) | Sat Dec 19 07:00:00 IST 2015 | Thu Dec 31 17:00:00 IST 2015
534 | TT_TASK | Invert Slab at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
535 | TT_TASK | Invert Slab between CP6 and 2B Gates(next to CP6) (20m) | Thu Nov 05 07:00:00 IST 2015 | Fri Nov 06 17:00:00 IST 2015
536 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
537 | TT_TASK | Invert Slab between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
538 | None | Lower Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
539 | TT_TASK | Lower Wkys between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
540 | TT_TASK | Lower Wkys at CP1 (30m) | Mon May 16 07:00:00 IDT 2016 | Tue May 17 17:00:00 IDT 2016
541 | TT_TASK | Lower Wkys between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
542 | TT_TASK | Lower Wkys at CP2 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
543 | TT_TASK | Lower Wkys between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
544 | TT_TASK | Lower Wkys at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
545 | TT_TASK | Lower Wkys between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
546 | TT_TASK | Lower Wkys at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
547 | TT_TASK | Lower Wkys at CP4 (64m) | Sat Apr 16 07:00:00 IDT 2016 | Mon Apr 18 17:00:00 IDT 2016
548 | TT_TASK | Lower Wkys between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
549 | TT_TASK | Lower Wkys at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
550 | TT_TASK | Lower Wkys between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
551 | TT_TASK | Lower Wkys at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
552 | TT_TASK | Lower Wkys between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
553 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
554 | TT_TASK | Lower Wkys between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
555 | None | Upper Walkway (UT) | Fri Apr 01 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
556 | TT_TASK | Upper Wky between HK Boundary and CP1 (104-15=89m) | Mon May 16 07:00:00 IDT 2016 | Sat May 21 17:00:00 IDT 2016
557 | TT_TASK | Upper Wky at CP1 (30m) | Sun May 08 07:00:00 IDT 2016 | Mon May 09 17:00:00 IDT 2016
558 | TT_TASK | Upper Wky between CP1 and CP2 (164-30=134m) incl. Station A area | Sun May 08 07:00:00 IDT 2016 | Sun May 15 17:00:00 IDT 2016
559 | TT_TASK | Upper Wky at CP2 (30m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
560 | TT_TASK | Upper Wky between CP2 and CP3 (250-30=220m) | Mon Apr 25 07:00:00 IDT 2016 | Sat May 07 17:00:00 IDT 2016
561 | TT_TASK | Upper Wky at CP3 (30m) | Mon Apr 25 07:00:00 IDT 2016 | Tue Apr 26 17:00:00 IDT 2016
562 | TT_TASK | Upper Wky between CP3 and CP4 (226-47-34=145m) | Sat Apr 16 07:00:00 IDT 2016 | Sun Apr 24 17:00:00 IDT 2016
563 | TT_TASK | Upper Wky at Station B (34m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
564 | TT_TASK | Upper Wky at CP4 (64m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 03 17:00:00 IDT 2016
565 | TT_TASK | Upper Wky between CP4 and CP5 (296-51=245m) | Fri Apr 01 07:00:00 IDT 2016 | Fri Apr 15 17:00:00 IDT 2016
566 | TT_TASK | Upper Wky at CP5 (38m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
567 | TT_TASK | Upper Wky between CP5 and CP6 (250-32=218m) | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 13 17:00:00 IDT 2016
568 | TT_TASK | Upper Wky at CP6 (26m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
569 | TT_TASK | Upper Wky between CP6 and 2B Gates(next to CP6) (20m) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 02 17:00:00 IDT 2016
570 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to CP6 (192-13-20-20=139m) | Fri Apr 01 07:00:00 IDT 2016 | Sun Apr 10 17:00:00 IDT 2016
571 | TT_TASK | Upper Wky between 2B Gates(next to MPS) to MPS (10m) | Sun May 01 07:00:00 IDT 2016 | Mon May 02 17:00:00 IDT 2016
572 | None | Up Track Tunnel Finishes | Fri Apr 01 07:00:00 IDT 2016 | Thu Dec 22 17:00:00 IST 2016
573 | FINISH_MILESTONE | Submit Inspection and Testing Plan for Tunnel Finish | Thu Dec 01 07:00:00 IST 2016 | Thu Dec 01 07:00:00 IST 2016
574 | TT_TASK | Engineer's review on Inspection and Testing Plan | Thu Dec 01 07:00:00 IST 2016 | Sat Dec 17 17:00:00 IST 2016
575 | TT_TASK | Wriggle survey and survey report submission | Sun Dec 18 07:00:00 IST 2016 | Thu Dec 22 17:00:00 IST 2016
576 | TT_TASK | Install trackside brackets (No.1 & 4) | Fri Apr 01 07:00:00 IDT 2016 | Thu Jun 30 17:00:00 IDT 2016
577 | TT_TASK | Install trackside brackets (No.2 & 3) | Fri Apr 01 07:00:00 IDT 2016 | Sat Apr 30 17:00:00 IDT 2016
578 | None | UT Double Gates | Thu Nov 05 07:00:00 IST 2015 | Wed Apr 06 17:00:00 IDT 2016
579 | TT_TASK | Install double gates at 20m south of CP6 | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
580 | TT_TASK | Lock up manlock when cutter head breakthrough cont' wall | Wed Nov 11 07:00:00 IST 2015 | Mon Nov 16 17:00:00 IST 2015
581 | TT_TASK | Shift double gates to Mai Po Shaft after TBM removal | Thu Nov 05 07:00:00 IST 2015 | Tue Nov 10 17:00:00 IST 2015
582 | TT_TASK | Shift double gates back to Hong Kong Boundary | Fri Apr 01 07:00:00 IDT 2016 | Wed Apr 06 17:00:00 IDT 2016
583 | None | Tunnel Finishes to Completion | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
584 | None | Down Track | Fri Apr 08 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
585 | TT_TASK | Operation and maintenance of temporary services | Fri Apr 08 07:00:00 IDT 2016 | Sun Mar 05 17:00:00 IST 2017
586 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
587 | None | Up Track | Wed Jun 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
588 | TT_TASK | Operation and maintenance of temporary services | Wed Jun 01 07:00:00 IDT 2016 | Thu Oct 06 17:00:00 IDT 2016
589 | TT_TASK | Remove temporary services and utilities | Sat Mar 04 07:00:00 IST 2017 | Fri Mar 31 17:00:00 IDT 2017
590 | None | Commissioning, Inspections and Completion | Fri Apr 01 07:00:00 IDT 2016 | Fri Mar 31 17:00:00 IDT 2017
591 | RESOURCE_DEPENDENT | Site Cleaning, Inspection for Degree 1 Completion | Fri Apr 01 07:00:00 IDT 2016 | Thu Apr 07 17:00:00 IDT 2016
592 | FINISH_MILESTONE | Submit draft as-built drawings (Z8.2) and draft O&M Manuals | Sat Dec 24 17:00:00 IST 2016 | Sat Dec 24 17:00:00 IST 2016
593 | FINISH_MILESTONE | Submit approved Design Data (Z8.4) | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
594 | FINISH_MILESTONE | Submit final as-built drawings and O&M Manuals | Tue Jan 24 17:00:00 IST 2017 | Tue Jan 24 17:00:00 IST 2017
595 | TT_TASK | Inspect & Certify completion of whole works | Sat Mar 25 07:00:00 IDT 2017 | Fri Mar 31 17:00:00 IDT 2017
596 | None | Contract Preliminaries | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
597 | None | Designs and Submissions | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
598 | None | Principle Method Statements, Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Wed Jun 17 17:00:00 IDT 2015
599 | None | Management Plans and Programme | Mon Mar 15 08:00:00 IST 2010 | Sun Oct 30 08:00:00 IST 2011
600 | TT_TASK | Submit System Assurance Plan (App P, P3.1) | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
601 | TT_TASK | Engineer's review on System Assurance Plan | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
602 | TT_TASK | Submit Health and Safety Plan (G3.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
603 | TT_TASK | Engineer's review on Health and Safety Plan | Wed May 05 08:00:00 IDT 2010 | Wed Jun 02 08:00:00 IDT 2010
604 | TT_TASK | Submit Quality Assurance Plan (G9.2.1) | Thu Apr 15 08:00:00 IDT 2010 | Thu May 13 08:00:00 IDT 2010
605 | TT_TASK | Engineer's review on Quality Assurance Plan | Wed May 12 08:00:00 IDT 2010 | Wed Jun 09 08:00:00 IDT 2010
606 | TT_TASK | Submit Prelimiary Master Programme (G4.6.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
607 | TT_TASK | Engineer's review on Prelimiary Master Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
608 | TT_TASK | Submit first Three-Month Rolling Programme (G4.8 | Mon Mar 15 08:00:00 IST 2010 | Mon Mar 29 08:00:00 IDT 2010
609 | TT_TASK | Engineer's review on first Three-Month Rolling P | Fri Apr 02 08:00:00 IDT 2010 | Fri Apr 30 08:00:00 IDT 2010
610 | TT_TASK | Submit Time-chainage Programme (G4.11.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
611 | TT_TASK | Engineer's review on Time-chainage Programme | Sat May 15 08:00:00 IDT 2010 | Sat Jun 12 08:00:00 IDT 2010
612 | TT_TASK | Submit Design Schedule (App Z) | Mon May 03 08:00:00 IDT 2010 | Mon May 17 08:00:00 IDT 2010
613 | TT_TASK | Engineer's review on Design Schedule | Fri May 28 08:00:00 IDT 2010 | Fri Jun 25 08:00:00 IDT 2010
614 | TT_TASK | Submit Subcontractor Management Plan (App S) | Sat May 15 08:00:00 IDT 2010 | Mon Jun 14 08:00:00 IDT 2010
615 | TT_TASK | Engineer's review on Subcontractor Management Pl | Tue Jun 15 08:00:00 IDT 2010 | Tue Jul 13 08:00:00 IDT 2010
616 | TT_TASK | Submit Groundwater Monitoring and Emergency Resp | Thu Apr 22 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
617 | TT_TASK | Engineer's review on Groundwater Monitoring and | Fri Jun 04 08:00:00 IDT 2010 | Fri Jul 02 08:00:00 IDT 2010
618 | TT_TASK | Submit Water Pollution Control Measures and Moni | Thu Apr 15 08:00:00 IDT 2010 | Sun May 30 08:00:00 IDT 2010
619 | TT_TASK | Engineer's review on Water Pollution Control Mea | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
620 | TT_TASK | Submit Waste Management Plan (P22.8.1) | Mon Mar 15 08:00:00 IST 2010 | Fri May 14 08:00:00 IDT 2010
621 | TT_TASK | Engineer's review on Waste Management Plan | Tue May 18 08:00:00 IDT 2010 | Tue Jun 15 08:00:00 IDT 2010
622 | TT_TASK | Submit the Plan for the Design for Safety and Co | Mon May 24 08:00:00 IDT 2010 | Mon Jun 21 08:00:00 IDT 2010
623 | TT_TASK | Engineer's review on Plan for the Design for Saf | Tue Jun 29 08:00:00 IDT 2010 | Tue Jul 27 08:00:00 IDT 2010
624 | TT_TASK | Submit Air Quality Management Plan (P22.4.4) | Fri Apr 09 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
625 | TT_TASK | Engineer's review on Air Quality Management Plan | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
626 | TT_TASK | Submit TBM manufacturiing and delivery programme | Sat May 22 08:00:00 IDT 2010 | Sat Jun 19 08:00:00 IDT 2010
627 | TT_TASK | Engineer's review on TBM manufacturiing and deli | Wed Jun 02 08:00:00 IDT 2010 | Wed Jun 30 08:00:00 IDT 2010
628 | TT_TASK | Submit Environmental Management Plan (G5.1.10) | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
629 | TT_TASK | Engineer's review on Environmental Management Pl | Tue May 11 08:00:00 IDT 2010 | Tue Jun 08 08:00:00 IDT 2010
630 | TT_TASK | Submit interfacing documentation for System-wide | Mon Aug 01 08:00:00 IDT 2011 | Sun Oct 30 08:00:00 IST 2011
631 | TT_TASK | Engineer's review on interfacing documentation f | Thu Sep 01 08:00:00 IDT 2011 | Thu Sep 29 08:00:00 IDT 2011
632 | None | Method Statements | Fri Apr 09 08:00:00 IDT 2010 | Wed Jun 17 17:00:00 IDT 2015
633 | TT_TASK | Submit Geotechnical Instruments installation | Fri Jun 18 08:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010
634 | TT_TASK | Engineer's review on Geotechnical Instruments installation | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
635 | TT_TASK | Submit Survey control network | Fri Apr 09 08:00:00 IDT 2010 | Mon May 24 08:00:00 IDT 2010
636 | TT_TASK | Engineer's review on Survey control network | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
637 | TT_TASK | Submit MS for surveying and survey control for tunnelling works | Mon Jun 14 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
638 | TT_TASK | Engineer's review on MS for surveying and survey control for tunnelling works | Sat Aug 07 08:00:00 IDT 2010 | Sat Sep 04 08:00:00 IDT 2010
639 | TT_TASK | Submit a Ground Treatment Works spoil disposal plan | Tue Jun 08 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
640 | TT_TASK | Engineer's review on Ground Treatment Works spoil disposal plan | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
641 | TT_TASK | Submit MS for ground treatment | Sun May 09 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
642 | TT_TASK | Engineer's review on MS for ground treatment | Fri Jun 25 08:00:00 IDT 2010 | Fri Jul 23 08:00:00 IDT 2010
643 | TT_TASK | Submit TBM MS for transportation and erection of the TBMs (X.17.1.1) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
644 | TT_TASK | Engineer's review on TBM MS for transportation and erection of the TBMs | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
645 | TT_TASK | Submit TBM MS for operation of the TBM (X17.1.3) | Mon Oct 04 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
646 | TT_TASK | Engineer's review on TBM MS for operation of the TBM | Thu Dec 16 08:00:00 IST 2010 | Thu Jan 13 08:00:00 IST 2011
647 | TT_TASK | Submit MS for instrumentation and monitoring works in Ramsar & WPC areas | Mon Feb 28 08:00:00 IST 2011 | Fri Apr 29 08:00:00 IDT 2011
648 | TT_TASK | Engineer's review on MS for instrumentation and monitoring works in Ramsar & WPC | Tue Mar 08 08:00:00 IST 2011 | Tue Apr 05 08:00:00 IDT 2011
649 | TT_TASK | Submit TBM MS for determining ground conditions ahead of the face (X17.1.5) (CS569) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
650 | TT_TASK | Engineer's review on TBM MS for determining ground conditions ahead of the face | Fri Apr 17 07:00:00 IDT 2015 | Thu May 14 17:00:00 IDT 2015
651 | TT_TASK | Submit MS for cross passage construction | Mon Jul 04 08:00:00 IDT 2011 | Mon Aug 01 08:00:00 IDT 2011
652 | TT_TASK | Engineer's review on MS for cross passage construction | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 26 08:00:00 IDT 2011
653 | TT_TASK | Submit TBM MS for commencing the initial drives (X17.1.2) (CS80) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
654 | TT_TASK | Engineer's review on TBM MS for commencing the initial drives | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
655 | TT_TASK | Submit TBM MS for setting out and controlling the tunnel alignment (Survey MS CS21) | Tue May 11 07:00:00 IDT 2010 | Fri Jul 09 17:00:00 IDT 2010
656 | TT_TASK | Engineer's review on TBM MS for setting out & contolling the tunnel alignment | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
657 | TT_TASK | Submit TBM MS for monitoring ground loss and settlement monitoring (X17.1.6) (CS36) | Tue Nov 30 07:00:00 IST 2010 | Tue Nov 30 07:00:00 IST 2010
658 | TT_TASK | Engineer's review on TBM MS for monitoring ground loss & settlement monitoring | Wed Aug 11 07:00:00 IDT 2010 | Wed Aug 11 07:00:00 IDT 2010
659 | TT_TASK | Submit TBM MS for hyperbaric interventions (X17.1.7) (CS520) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
660 | TT_TASK | Engineer's review on TBM MS for hyperbaric interventions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
661 | TT_TASK | Submit MS for the identification and removal of obstructions (P11.11) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Mon Dec 29 17:00:00 IST 2014
662 | TT_TASK | Engineer's review on MS for the identification & removal of obstructions | Tue Dec 30 07:00:00 IST 2014 | Mon Jan 26 17:00:00 IST 2015
663 | TT_TASK | Submit TBM MS for tunnelling under sensitive structures (X17.1.10) (CS145) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
664 | TT_TASK | Engineer's review on TBM MS for tunnelling under sensitive structures | Sun Nov 30 07:00:00 IST 2014 | Sat Dec 27 17:00:00 IST 2014
665 | TT_TASK | Submit TBM MS for TBM dismantling (X17.1.9) (CS652) | Fri Feb 20 07:00:00 IST 2015 | Wed May 20 17:00:00 IDT 2015
666 | TT_TASK | Engineer's review on TBM MS for TBM dismantling | Thu May 21 07:00:00 IDT 2015 | Wed Jun 17 17:00:00 IDT 2015
667 | TT_TASK | Submit TBM MS for junctions with shafts (X17.1.8) (CS246) | Wed Oct 01 07:00:00 IDT 2014 | Sat Nov 29 17:00:00 IST 2014
668 | TT_TASK | Engineer's review on TBM MS for junctions with shafts | Thu Jun 23 07:00:00 IDT 2011 | Wed Jul 20 17:00:00 IDT 2011
669 | TT_TASK | Submit MS for ground freezing works (CS686) | Mon Dec 12 08:00:00 IST 2011 | Fri Feb 10 08:00:00 IST 2012
670 | TT_TASK | Engineer's review on MS for ground freezing work | Mon Mar 19 08:00:00 IST 2012 | Mon Apr 16 08:00:00 IDT 2012
671 | TT_TASK | Submit MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Sat Mar 01 08:00:00 IST 2014
672 | TT_TASK | Engineer's review on MS for TBM break though | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
673 | TT_TASK | Submit Methods of Construction | Thu May 27 08:00:00 IDT 2010 | Thu Jun 17 08:00:00 IDT 2010
674 | TT_TASK | Engineer's review on Methods of Construction | Fri Jun 18 08:00:00 IDT 2010 | Fri Jul 16 08:00:00 IDT 2010
675 | TT_TASK | Submit TBM Spoil Disposal Plan (HK) | Wed Jun 23 08:00:00 IDT 2010 | Wed Jul 14 08:00:00 IDT 2010
676 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Jul 22 08:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010
677 | TT_TASK | Submit TBM Spoil Disposal Plan (SZ) | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 21 08:00:00 IST 2013
678 | TT_TASK | Engineer's review on TBM Spoil Disposal Plan | Thu Dec 26 08:00:00 IST 2013 | Thu Jan 23 08:00:00 IST 2014
679 | None | Submissions to Government Departments | Sat May 29 08:00:00 IDT 2010 | Tue Jun 03 09:00:00 IDT 2014
680 | TT_TASK | Apply for the initial batch of Frontier Closed Area Permits | Sat May 29 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
681 | TT_TASK | Submit Emergency Rescue proposals and procedures | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
682 | TT_TASK | Engineer's review on Emergency Rescue proposals and procedures | Sat Nov 30 08:00:00 IST 2013 | Sat Dec 28 08:00:00 IST 2013
683 | TT_TASK | Application and obtain approval of Construction Noise Permits | Fri Apr 04 09:00:00 IDT 2014 | Tue Jun 03 09:00:00 IDT 2014
684 | None | Temporary Works Design Submissions | Thu Apr 22 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
685 | TT_TASK | Submit site logistics plans (initial layout) | Thu Apr 22 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
686 | TT_TASK | Engineer's review on site logistics plans (initial layout) | Fri Jul 23 08:00:00 IDT 2010 | Fri Aug 20 08:00:00 IDT 2010
687 | TT_TASK | Submit designs for the Engineer's Office | Mon Jul 12 08:00:00 IDT 2010 | Fri Sep 10 08:00:00 IDT 2010
688 | TT_TASK | Engineer's review on designs for the Engineer's | Mon Aug 23 08:00:00 IDT 2010 | Mon Sep 20 08:00:00 IST 2010
689 | TT_TASK | Submit temporary ventilation system design | Mon Aug 01 08:00:00 IDT 2011 | Fri Sep 30 08:00:00 IDT 2011
690 | TT_TASK | Engineer's review on temporary ventilation syste | Sat Aug 20 08:00:00 IDT 2011 | Sat Sep 17 08:00:00 IDT 2011
691 | None | Design of Permanent Works | Tue Jun 01 08:00:00 IDT 2010 | Sun Sep 07 08:00:00 IDT 2014
692 | None | Tunnel Permanent Lining | Tue Jun 01 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
693 | TT_TASK | Submission preparation & ICE checking | Tue Jun 01 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
694 | TT_TASK | Engineer's review | Thu Jun 24 08:00:00 IDT 2010 | Thu Jul 22 08:00:00 IDT 2010
695 | TT_TASK | Re-submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Tue Aug 31 08:00:00 IDT 2010
696 | TT_TASK | Engineer's review | Wed Aug 04 08:00:00 IDT 2010 | Wed Sep 01 08:00:00 IDT 2010
697 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
698 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
699 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
700 | None | Permanent Tunnel Lining of Cross Passages | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
701 | None | AIP Submission | Mon Jun 28 08:00:00 IDT 2010 | Mon Oct 01 08:00:00 IST 2012
702 | TT_TASK | Submission preparation | Mon Jun 28 08:00:00 IDT 2010 | Sat Aug 07 08:00:00 IDT 2010
703 | TT_TASK | Engineer's review | Sat Aug 14 08:00:00 IDT 2010 | Sat Sep 11 08:00:00 IDT 2010
704 | TT_TASK | Re-submission preparation | Fri Aug 03 08:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012
705 | TT_TASK | Engineer's review | Mon Sep 03 08:00:00 IDT 2012 | Mon Oct 01 08:00:00 IST 2012
706 | None | Connection between Bored Tunnel and Retrival Shaft | Mon Aug 16 08:00:00 IDT 2010 | Tue Jul 01 08:00:00 IDT 2014
707 | TT_TASK | Submission preparation & ICE checking | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 25 08:00:00 IST 2010
708 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
709 | TT_TASK | Re-submission preparation & ICE checking | Sat Oct 23 08:00:00 IST 2010 | Sun Nov 28 08:00:00 IST 2010
710 | TT_TASK | Engineer's review | Sat Oct 06 08:00:00 IST 2012 | Sat Nov 03 08:00:00 IST 2012
711 | TT_TASK | Submission for RDO/BD consultation | Sun Feb 10 08:00:00 IST 2013 | Sun Mar 10 08:00:00 IST 2013
712 | TT_TASK | Re-submission for RDO/BD consultation | Tue Dec 17 08:00:00 IST 2013 | Tue Jan 14 08:00:00 IST 2014
713 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
714 | None | Junction between Main Tunnel and Cross Passages | Mon Oct 04 08:00:00 IST 2010 | Sun Sep 07 08:00:00 IDT 2014
715 | TT_TASK | Submission preparation & ICE checking | Mon Oct 04 08:00:00 IST 2010 | Tue Nov 23 08:00:00 IST 2010
716 | TT_TASK | Engineer's review | Thu Feb 07 08:00:00 IST 2013 | Thu Mar 07 08:00:00 IST 2013
717 | TT_TASK | Submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
718 | TT_TASK | Re-submission preparation & ICE checking | Tue Jul 01 08:00:00 IDT 2014 | Sun Aug 10 08:00:00 IDT 2014
719 | TT_TASK | Engineer's review | Sun Aug 10 08:00:00 IDT 2014 | Sun Sep 07 08:00:00 IDT 2014
720 | TT_TASK | Re-submission for RDO/BD consultation | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 29 08:00:00 IDT 2014
721 | START_MILESTONE | Construction drawings issuance | Tue Jul 01 08:00:00 IDT 2014 | Tue Jul 01 08:00:00 IDT 2014
722 | None | Design of Temporary Works | Sat May 01 08:00:00 IDT 2010 | Fri Aug 29 08:00:00 IDT 2014
723 | None | Ground Treatment Works for TBM Break-in | Sat May 01 08:00:00 IDT 2010 | Tue Nov 02 08:00:00 IST 2010
724 | TT_TASK | Submission preparation & ICE checking | Sat May 01 08:00:00 IDT 2010 | Sun Jun 06 08:00:00 IDT 2010
725 | TT_TASK | Engineer's review | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 12 08:00:00 IDT 2010
726 | TT_TASK | Re-submission preparation & ICE checking | Wed Jun 30 08:00:00 IDT 2010 | Wed Jul 07 08:00:00 IDT 2010
727 | TT_TASK | Engineer's review | Thu Aug 05 08:00:00 IDT 2010 | Thu Sep 02 08:00:00 IDT 2010
728 | TT_TASK | Submission for RDO/BD consultation | Tue Aug 31 08:00:00 IDT 2010 | Tue Sep 28 08:00:00 IST 2010
729 | TT_TASK | Re-submission for RDO/BD consultation | Tue Oct 05 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
730 | START_MILESTONE | Construction drawings issuance | Tue Nov 02 08:00:00 IST 2010 | Tue Nov 02 08:00:00 IST 2010
731 | None | Geotechnical Assessment Report | Mon Jun 14 08:00:00 IDT 2010 | Mon Dec 26 08:00:00 IST 2011
732 | TT_TASK | Submission preparation & ICE checking | Mon Jun 14 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010
733 | TT_TASK | Engineer's review | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
734 | TT_TASK | Re-submission preparation & ICE checking | Thu Oct 21 08:00:00 IST 2010 | Fri Nov 05 08:00:00 IST 2010
735 | TT_TASK | Engineer's review | Fri Nov 05 08:00:00 IST 2010 | Fri Dec 03 08:00:00 IST 2010
736 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
737 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
738 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
739 | None | Groundwater Assessment Report | Mon Jul 26 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
740 | TT_TASK | Submission preparation & ICE checking | Mon Jul 26 08:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010
741 | TT_TASK | Engineer's review | Tue Sep 07 08:00:00 IDT 2010 | Tue Oct 05 08:00:00 IST 2010
742 | TT_TASK | Re-submission preparation & ICE checking | Wed Nov 03 08:00:00 IST 2010 | Sun Nov 21 08:00:00 IST 2010
743 | TT_TASK | Engineer's review | Tue Nov 23 08:00:00 IST 2010 | Tue Dec 21 08:00:00 IST 2010
744 | TT_TASK | Submission for RDO/BD consultation | Wed Oct 06 08:00:00 IST 2010 | Wed Nov 03 08:00:00 IST 2010
745 | TT_TASK | Re-submission for RDO/BD consultation | Sat Oct 23 08:00:00 IST 2010 | Sat Nov 20 08:00:00 IST 2010
746 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
747 | None | Ground Freezing and Temporary Support of Cross Passages | Sat Jan 01 08:00:00 IST 2011 | Fri Aug 29 08:00:00 IDT 2014
748 | TT_TASK | Submission preparation & ICE checking | Sat Jan 01 08:00:00 IST 2011 | Sat Mar 12 08:00:00 IST 2011
749 | TT_TASK | Engineer's review | Fri Nov 25 08:00:00 IST 2011 | Fri Dec 23 08:00:00 IST 2011
750 | TT_TASK | Re-submission preparation & ICE checking | Fri Feb 15 08:00:00 IST 2013 | Mon Apr 01 08:00:00 IDT 2013
751 | TT_TASK | Engineer's review | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
752 | TT_TASK | Submission for RDO/BD consultation | Tue Dec 31 08:00:00 IST 2013 | Tue Jan 28 08:00:00 IST 2014
753 | TT_TASK | Re-submission for RDO/BD consultation | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014
754 | START_MILESTONE | Construction drawings issuance | Fri Aug 01 08:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014
755 | None | Bulk Head for TBM Removal | Mon May 31 08:00:00 IDT 2010 | Mon Oct 31 08:00:00 IST 2011
756 | TT_TASK | Submission preparation & ICE checking | Mon May 31 08:00:00 IDT 2010 | Mon Aug 09 08:00:00 IDT 2010
757 | TT_TASK | Engineer's review | Fri Jul 30 08:00:00 IDT 2010 | Fri Aug 27 08:00:00 IDT 2010
758 | TT_TASK | Re-submission preparation & ICE checking | Thu Aug 12 08:00:00 IDT 2010 | Sun Sep 26 08:00:00 IST 2010
759 | TT_TASK | Engineer's review | Thu Sep 16 08:00:00 IST 2010 | Thu Oct 14 08:00:00 IST 2010
760 | START_MILESTONE | Construction drawings issuance | Mon Oct 31 08:00:00 IST 2011 | Mon Oct 31 08:00:00 IST 2011
761 | None | Prediction of Ground Movement | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
762 | None | Report on the Prediction of Ground Movement and and Assessment on effect of EBS | Mon Jul 12 08:00:00 IDT 2010 | Tue Dec 27 08:00:00 IST 2011
763 | TT_TASK | Submission preparation & ICE checking | Mon Jul 12 08:00:00 IDT 2010 | Tue Aug 17 08:00:00 IDT 2010
764 | TT_TASK | Engineer's review | Sun Aug 22 08:00:00 IDT 2010 | Sun Sep 19 08:00:00 IST 2010
765 | TT_TASK | Re-submission preparation & ICE checking | Wed Sep 29 08:00:00 IST 2010 | Sun Oct 17 08:00:00 IST 2010
766 | TT_TASK | Engineer's review | Wed Oct 13 08:00:00 IST 2010 | Wed Nov 10 08:00:00 IST 2010
767 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
768 | TT_TASK | Re-submission for RDO/BD consultation | Mon Nov 28 08:00:00 IST 2011 | Mon Dec 26 08:00:00 IST 2011
769 | START_MILESTONE | Construction drawings issuance | Tue Dec 27 08:00:00 IST 2011 | Tue Dec 27 08:00:00 IST 2011
770 | None | Instrumentation and Montoring Plans | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
771 | None | Instrumentation Plan | Mon May 03 08:00:00 IDT 2010 | Mon Nov 28 08:00:00 IST 2011
772 | TT_TASK | Submission preparation & ICE checking | Mon May 03 08:00:00 IDT 2010 | Fri May 28 08:00:00 IDT 2010
773 | TT_TASK | Engineer's review | Tue Jun 08 08:00:00 IDT 2010 | Tue Jul 06 08:00:00 IDT 2010
774 | TT_TASK | Re-submission preparation & ICE checking | Wed Jul 28 08:00:00 IDT 2010 | Sun Aug 15 08:00:00 IDT 2010
775 | TT_TASK | Engineer's review | Tue Aug 10 08:00:00 IDT 2010 | Tue Sep 07 08:00:00 IDT 2010
776 | TT_TASK | Submission for RDO/BD consultation | Mon Oct 04 08:00:00 IST 2010 | Mon Nov 01 08:00:00 IST 2010
777 | TT_TASK | Re-submission for RDO/BD consultation | Mon Oct 31 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
778 | START_MILESTONE | Construction drawings issuance | Mon Nov 28 08:00:00 IST 2011 | Mon Nov 28 08:00:00 IST 2011
779 | None | Additional Ground Investigation Plans and Laboratory | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
780 | None | Further GI Plan and Lab Test Schedule | Tue May 31 08:00:00 IDT 2011 | Fri Jan 31 08:00:00 IST 2014
781 | TT_TASK | Submission preparation & ICE checking | Tue May 31 08:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011
782 | TT_TASK | Engineer's review | Thu Jul 14 08:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011
783 | TT_TASK | Re-submission preparation & ICE checking | Mon Oct 31 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
784 | TT_TASK | Engineer's review | Sat Nov 19 08:00:00 IST 2011 | Sat Dec 17 08:00:00 IST 2011
785 | TT_TASK | Submission for RDO/BD consultation | Sat Dec 17 08:00:00 IST 2011 | Sat Jan 14 08:00:00 IST 2012
786 | TT_TASK | Re-submission for RDO/BD consultation | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 31 08:00:00 IST 2014
787 | START_MILESTONE | Construction drawings issuance | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 08:00:00 IST 2013
788 | None | Procurement | Mon Mar 15 08:00:00 IST 2010 | Mon Sep 07 17:00:00 IDT 2015
789 | None | TBM Manufacture and Delivery | Mon Mar 15 08:00:00 IST 2010 | Thu Nov 01 08:00:00 IST 2012
790 | TT_TASK | Confirmation of purchase order on TBM manufacture | Mon Mar 15 08:00:00 IST 2010 | Wed Apr 14 08:00:00 IDT 2010
791 | FINISH_MILESTONE | Submit PO to the Engineer | Sun Apr 25 08:00:00 IDT 2010 | Sun Apr 25 08:00:00 IDT 2010
792 | TT_TASK | Shop drawing preparation and submission | Thu Jul 15 08:00:00 IDT 2010 | Wed Aug 04 08:00:00 IDT 2010
793 | TT_TASK | Shop drawing review by the Engineer | Tue Aug 24 08:00:00 IDT 2010 | Tue Sep 21 08:00:00 IST 2010
794 | TT_TASK | Resubmission of shop drawings | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 25 08:00:00 IST 2010
795 | TT_TASK | Engineer's approval of shop drawings | Thu Nov 18 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
796 | TT_TASK | Shop drawings issued for manufacture | Thu Dec 16 08:00:00 IST 2010 | Fri Dec 31 08:00:00 IST 2010
797 | TT_TASK | Manufacturing & purchase parts for TBM #1 | Mon Aug 23 08:00:00 IDT 2010 | Mon Nov 01 08:00:00 IST 2010
798 | TT_TASK | TBM #1 factory preassembly and packing | Thu Oct 07 08:00:00 IST 2010 | Thu Dec 16 08:00:00 IST 2010
799 | TT_TASK | TBM #1 delivery to workshop | Fri Nov 19 08:00:00 IST 2010 | Sun Dec 19 08:00:00 IST 2010
800 | TT_TASK | TBM #1 workshop assembly | Fri Jan 07 08:00:00 IST 2011 | Fri Mar 18 08:00:00 IST 2011
801 | TT_TASK | TBM #1 test runs, acceptance, dis-assembly and p | Mon May 16 08:00:00 IDT 2011 | Wed Jun 15 08:00:00 IDT 2011
802 | TT_TASK | TBM #1 delivery to Shenzhen | Wed May 25 08:00:00 IDT 2011 | Sat Jun 04 08:00:00 IDT 2011
803 | FINISH_MILESTONE | TBM #1 delivery to HGP shaft | Mon May 30 08:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011
804 | TT_TASK | TBM #1 on-site assembly, T&C @ HGP Shaft | Mon Oct 31 08:00:00 IST 2011 | Sun Jan 29 08:00:00 IST 2012
805 | TT_TASK | TBM #1 free walk-thru to commencement position | Fri Apr 27 08:00:00 IDT 2012 | Thu May 17 08:00:00 IDT 2012
806 | FINISH_MILESTONE | TBM #1 ready to commence drive at HGP by GSG Contractor | Wed Jul 04 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
807 | TT_TASK | Manufacturing & purchase parts for TBM #2 | Thu Dec 16 08:00:00 IST 2010 | Thu Feb 24 08:00:00 IST 2011
808 | TT_TASK | TBM #2 factory preassembly and packing | Mon Feb 14 08:00:00 IST 2011 | Mon Apr 25 08:00:00 IDT 2011
809 | TT_TASK | TBM #2 delivery to workshop | Sat Mar 05 08:00:00 IST 2011 | Mon Apr 04 08:00:00 IDT 2011
810 | TT_TASK | TBM #2 workshop assembly | Mon May 30 08:00:00 IDT 2011 | Mon Aug 08 08:00:00 IDT 2011
811 | TT_TASK | TBM #2 test runs, acceptance, dis-assembly and p | Mon Aug 22 08:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011
812 | TT_TASK | TBM #2 delivery to temporary storage at Nansha | Mon Sep 19 08:00:00 IDT 2011 | Thu Sep 22 08:00:00 IDT 2011
813 | TT_TASK | TBM #2 delivery to Shenzhen | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 09 08:00:00 IDT 2012
814 | FINISH_MILESTONE | TBM #2 delivery to HGP shaft | Tue May 01 08:00:00 IDT 2012 | Tue May 01 08:00:00 IDT 2012
815 | TT_TASK | TBM #2 on-site assembly, T&C @ HGP Shaft | Thu Apr 05 08:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012
816 | TT_TASK | TBM #2 free walk-thru to commencement position | Mon Oct 01 08:00:00 IST 2012 | Sun Oct 21 08:00:00 IST 2012
817 | FINISH_MILESTONE | TBM #2 ready to commence drive at HGP by GSG Con | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012
818 | None | TBM Ground Support Equipment | Thu Jul 08 08:00:00 IDT 2010 | Mon Nov 05 08:00:00 IST 2012
819 | TT_TASK | Confirm order for slurry treatment plant (STP) | Thu Jul 08 08:00:00 IDT 2010 | Thu Jul 15 08:00:00 IDT 2010
820 | TT_TASK | STP shop drawing preparation and submission | Mon Oct 04 08:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010
821 | TT_TASK | STP shop drawing review by the Engineer | Wed Dec 01 08:00:00 IST 2010 | Wed Dec 29 08:00:00 IST 2010
822 | TT_TASK | STP procurement of components and materials | Thu Dec 09 08:00:00 IST 2010 | Sun Jan 23 08:00:00 IST 2011
823 | TT_TASK | STP resubmission of shop drawings | Mon Jan 10 08:00:00 IST 2011 | Mon Jan 24 08:00:00 IST 2011
824 | TT_TASK | STP Engineer's approval of shop drawings | Tue Apr 05 08:00:00 IDT 2011 | Tue May 03 08:00:00 IDT 2011
825 | TT_TASK | STP shop drawings issued for manufacture | Mon Mar 14 08:00:00 IST 2011 | Mon Mar 21 08:00:00 IST 2011
826 | TT_TASK | STP sub-unit assembly | Wed Mar 16 08:00:00 IST 2011 | Wed Apr 06 08:00:00 IDT 2011
827 | TT_TASK | STP final assembly at factory | Wed Mar 23 08:00:00 IST 2011 | Sat Apr 02 08:00:00 IDT 2011
828 | TT_TASK | STP factory testing | Wed Mar 30 08:00:00 IST 2011 | Sat Apr 09 08:00:00 IDT 2011
829 | TT_TASK | STP packaging and transportation to docks | Fri Apr 01 08:00:00 IDT 2011 | Fri Apr 15 08:00:00 IDT 2011
830 | TT_TASK | STP shipping to Shenzhen, customs clearance and forwarding | Mon Apr 04 08:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011
831 | FINISH_MILESTONE | STP delivery to HGP works area | Tue Apr 12 08:00:00 IDT 2011 | Tue Apr 12 08:00:00 IDT 2011
832 | TT_TASK | STP on-site assembly | Wed Sep 28 08:00:00 IDT 2011 | Sat Oct 22 08:00:00 IST 2011
833 | TT_TASK | STP on-site self testing and commissioning | Mon Jan 16 08:00:00 IST 2012 | Fri Jan 27 08:00:00 IST 2012
834 | TT_TASK | STP on-site testing and commissioning with TBM#1 | Mon Jun 18 08:00:00 IDT 2012 | Fri Jun 29 08:00:00 IDT 2012
835 | TT_TASK | STP on-site testing and commissioning with TBM#2 | Wed Oct 03 08:00:00 IST 2012 | Sun Oct 14 08:00:00 IST 2012
836 | FINISH_MILESTONE | STP ready to commence operations for TBM #1 | Mon Jun 18 08:00:00 IDT 2012 | Mon Jun 18 08:00:00 IDT 2012
837 | FINISH_MILESTONE | STP ready to commence operations for TBM #2 | Mon Nov 05 08:00:00 IST 2012 | Mon Nov 05 08:00:00 IST 2012
838 | None | Tunnel Lining Segments | Mon Aug 29 08:00:00 IDT 2011 | Mon Sep 07 17:00:00 IDT 2015
839 | START_MILESTONE | Confirmation of purchase order on segment manufacturer | Wed Aug 31 08:00:00 IDT 2011 | Wed Aug 31 08:00:00 IDT 2011
840 | TT_TASK | Shop drawings issued for manufacture | Mon Aug 29 08:00:00 IDT 2011 | Sat Sep 10 08:00:00 IDT 2011
841 | TT_TASK | Pre-casting trials | Thu Nov 03 08:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011
842 | TT_TASK | Engineer's approval of trial segments | Thu Dec 15 08:00:00 IST 2011 | Thu Jan 12 08:00:00 IST 2012
843 | TT_TASK | Manufacture 926 Tunnel Rings (SZ) | Wed Feb 01 08:00:00 IST 2012 | Fri Jul 20 08:00:00 IDT 2012
844 | TT_TASK | Manufacture 163 Tunnel Rings (SZ) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 25 08:00:00 IST 2012
845 | TT_TASK | Manufacture 105 Tunnel Rings (SZ) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012
846 | TT_TASK | Manufacture 98 Tunnel Rings (SZ) | Wed Oct 31 08:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012
847 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sat Dec 01 08:00:00 IST 2012 | Wed Dec 26 08:00:00 IST 2012
848 | TT_TASK | Manufacture 250 Tunnel Rings (SZ) | Sun Jan 13 08:00:00 IST 2013 | Thu Feb 07 08:00:00 IST 2013
849 | TT_TASK | Manufacture 60 Tunnel Rings (SZ) | Sun Feb 24 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013
850 | TT_TASK | Manufacture 81 Tunnel Rings (HK) | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 08:00:00 IDT 2013
851 | TT_TASK | Manufacture 76 Tunnel Rings (HK) | Sun Jun 30 08:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013
852 | TT_TASK | Manufacture 75 Tunnel Rings (HK) | Mon Jul 01 08:00:00 IDT 2013 | Fri Jul 26 08:00:00 IDT 2013
853 | TT_TASK | Manufacture 88 Tunnel Rings (HK) | Thu Aug 01 08:00:00 IDT 2013 | Sun Aug 25 08:00:00 IDT 2013
854 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Sun Sep 01 08:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013
855 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Fri Jan 24 08:00:00 IST 2014
856 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Dec 31 08:00:00 IST 2013 | Mon Jan 20 08:00:00 IST 2014
857 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 17:00:00 IDT 2014
858 | TT_TASK | Manufacture 120 Tunnel Rings (HK) | Tue Jul 01 08:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014
859 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014
860 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Fri Jan 02 07:00:00 IST 2015 | Fri Jan 16 17:00:00 IST 2015
861 | TT_TASK | Manufacture 50 Tunnel Rings (HK) | Mon Feb 16 07:00:00 IST 2015 | Mon Mar 02 17:00:00 IST 2015
862 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Mar 03 07:00:00 IST 2015 | Fri Mar 27 17:00:00 IDT 2015
863 | TT_TASK | Manufacture 60 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Sat May 02 17:00:00 IDT 2015
864 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Tue Apr 21 07:00:00 IDT 2015 | Fri May 15 17:00:00 IDT 2015
865 | TT_TASK | Manufacture 100 Tunnel Rings (HK) | Sun Aug 09 07:00:00 IDT 2015 | Wed Sep 02 17:00:00 IDT 2015
866 | TT_TASK | Manufacture 10 Tunnel Rings (HK) | Thu Sep 03 07:00:00 IDT 2015 | Mon Sep 07 17:00:00 IDT 2015
867 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (SZ rings) | Wed Aug 01 08:00:00 IDT 2012 | Wed Dec 26 08:00:00 IST 2012
868 | TT_TASK | Ship & Deliver Tunnel Rings to HGP (HK rings) | Sat Nov 30 08:00:00 IST 2013 | Sun Oct 12 08:00:00 IDT 2014
869 | None | Segment Mould Design, Fabrication and Delivery | Mon May 16 08:00:00 IDT 2011 | Wed Feb 15 08:00:00 IST 2012
870 | START_MILESTONE | Confirm order for moulds | Mon May 16 08:00:00 IDT 2011 | Mon May 16 08:00:00 IDT 2011
871 | TT_TASK | Design and planning | Mon May 16 08:00:00 IDT 2011 | Thu Jun 09 08:00:00 IDT 2011
872 | TT_TASK | Design mould drawings for manufacture | Fri Jul 08 08:00:00 IDT 2011 | Sun Aug 07 08:00:00 IDT 2011
873 | TT_TASK | Materials procurement | Fri Jul 08 08:00:00 IDT 2011 | Thu Jul 28 08:00:00 IDT 2011
874 | TT_TASK | Factory assembly | Mon Jul 18 08:00:00 IDT 2011 | Fri Sep 16 08:00:00 IDT 2011
875 | TT_TASK | Shipping and delivery to Shenzhen - 1st batch (3 sets) | Sat Nov 05 08:00:00 IST 2011 | Thu Nov 10 08:00:00 IST 2011
876 | TT_TASK | Shipping and delivery to Shenzhen - 2nd batch (3 sets) | Fri Feb 10 08:00:00 IST 2012 | Wed Feb 15 08:00:00 IST 2012
877 | TT_TASK | Mould erection and commissioning ready for production in precast yard | Thu Nov 10 08:00:00 IST 2011 | Thu Nov 17 08:00:00 IST 2011
878 | None | Other Procurement Items | Tue Nov 02 08:00:00 IST 2010 | Sun Apr 06 08:00:00 IDT 2014
879 | TT_TASK | Transformer and substation procurement | Tue May 31 08:00:00 IDT 2011 | Mon Aug 29 08:00:00 IDT 2011
880 | TT_TASK | Procure temporary electrics subcontractor | Wed Jun 01 08:00:00 IDT 2011 | Fri Jul 01 08:00:00 IDT 2011
881 | TT_TASK | Place order for ready mixed concrete | Fri Mar 01 08:00:00 IST 2013 | Sat Apr 06 08:00:00 IDT 2013
882 | TT_TASK | Procure other major construction plant and equip | Tue Mar 01 08:00:00 IST 2011 | Mon May 30 08:00:00 IDT 2011
883 | TT_TASK | Place order for rebar supply | Mon Oct 31 08:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011
884 | TT_TASK | Rental agreement for off site office accommodation | Tue Nov 02 08:00:00 IST 2010 | Thu Dec 02 08:00:00 IST 2010
885 | TT_TASK | Procure tunnel personnel electronic tagging system | Sat Nov 30 08:00:00 IST 2013 | Sat Jan 11 08:00:00 IST 2014
886 | TT_TASK | Procure tunnel ventilation system | Thu Mar 01 08:00:00 IST 2012 | Tue Apr 10 08:00:00 IDT 2012
887 | TT_TASK | Procure ground freezing specialist subcontractor | Sat Mar 01 08:00:00 IST 2014 | Sun Apr 06 08:00:00 IDT 2014
888 | None | Site Mobilisation | Mon Mar 15 08:00:00 IST 2010 | Sat Apr 01 07:00:00 IDT 2017
889 | TT_TASK | Initial project staff assignments | Mon Mar 15 08:00:00 IST 2010 | Sun Jun 13 08:00:00 IDT 2010
890 | TT_TASK | Establish Works Areas at HGP | Wed Dec 01 08:00:00 IST 2010 | Tue Jan 18 08:00:00 IST 2011
891 | TT_TASK | Establish Works Areas at MPV | Fri Feb 01 08:00:00 IST 2013 | Sat Mar 09 08:00:00 IST 2013
892 | TT_TASK | Establish and operate Project Office in Hong Kong | Thu Apr 22 08:00:00 IDT 2010 | Fri Feb 18 08:00:00 IST 2011
893 | TT_TASK | Establish and operate Project Office in Shenzhen | Mon Jan 10 08:00:00 IST 2011 | Sat Oct 01 08:00:00 IDT 2016
894 | TT_TASK | Establish and operate Project Office in Mai Po | Tue Mar 15 08:00:00 IST 2011 | Fri Jul 25 08:00:00 IDT 2014
895 | START_MILESTONE | Commencement to operate compound at Mai Po, Area 1.19, for DLP | Sat Apr 01 07:00:00 IDT 2017 | Sat Apr 01 07:00:00 IDT 2017