## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status
1 |  | 823A As-built Programme | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 02 18:00:00 IDT 2017 | Mon Jul 19 08:00:00 IDT 2010
2 |  | Key Date | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 11 18:00:00 IDT 2017 | Mon Jul 19 08:00:00 IDT 2010
3 |  | Contractual Dates | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2016 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2016
4 | START_MILESTONE | Commencement of works | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 |  | COMPLETED
5 | FINISH_MILESTONE | Completion of the Whole of the Works | Sat Dec 31 18:00:00 IST 2016 | Sat Dec 31 18:00:00 IST 2016 | Sat Dec 31 18:00:00 IST 2016 | Sat Dec 31 18:00:00 IST 2016 |  | COMPLETED
6 |  | Completion of Specified Parts of the Works | Sun Dec 18 18:00:00 IST 2011 | Fri Jul 01 08:00:00 IDT 2016 | Sun Dec 18 18:00:00 IST 2011 | Tue May 17 18:00:00 IDT 2016
7 | FINISH_MILESTONE | Complete TUT Shaft within Works Area 5.1 & all requirements stated in App. Y3 of PS for ground treatment works by 822 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sun Dec 02 18:00:00 IST 2012 | Sun Dec 02 18:00:00 IST 2012 |  | COMPLETED
8 | FINISH_MILESTONE | Complete the down track tunnel structure at tai Kong Po Shaft for the final tunnel connections by Contract 824 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Mon Aug 04 18:00:00 IDT 2014 | Mon Aug 04 18:00:00 IDT 2014 |  | COMPLETED
9 | FINISH_MILESTONE | Complete the up track tunnel structure at tai Kong Po Shaft for the final tunnel connections by Contract 824 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 |  | COMPLETED
10 | FINISH_MILESTONE | Complete the backfilling works within Works Area 4.10 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Mon Dec 21 00:00:00 IST 2015 | Mon Dec 21 00:00:00 IST 2015 |  | COMPLETED
11 | FINISH_MILESTONE | Complete the temporary diversion of Wang Toi Shan Shan Tsuen Road | Sun Dec 18 18:00:00 IST 2011 | Sun Dec 18 18:00:00 IST 2011 | Sun Dec 18 18:00:00 IST 2011 | Sun Dec 18 18:00:00 IST 2011 |  | COMPLETED
12 | FINISH_MILESTONE | Complete commissioning of the East Culvert | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sun Mar 31 00:00:00 IDT 2013 | Sun Mar 31 00:00:00 IDT 2013 |  | COMPLETED
13 |  | Specified Degrees of Completion of The Works | Sun May 01 08:00:00 IDT 2016 | Sun Jan 01 08:00:00 IST 2017 | Sun Dec 29 00:00:00 IST 2013 | Mon Sep 19 00:00:00 IDT 2016
14 | FINISH_MILESTONE | Complete downtrack TBM tunnel of N.Tunnels include Box 7A except the roof, and C&C tunnel at 7B&6B both up & down tracks | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue Jan 20 18:00:00 IST 2015 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
15 | FINISH_MILESTONE | Complete the up track TBM tunnel of the North Tunnels | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Tue May 31 00:00:00 IDT 2016 | Tue May 31 00:00:00 IDT 2016 |  | COMPLETED
16 | FINISH_MILESTONE | Complete up track C&C tunnel of North Tunnels at Box 7A except the roof | Fri Jun 17 18:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Tue May 31 00:00:00 IDT 2016 | Tue May 31 00:00:00 IDT 2016 |  | COMPLETED
17 | FINISH_MILESTONE | Remaining cut and cover tunnel (Box 6) of the North Tunnels | Sun May 01 08:00:00 IDT 2016 | Sun May 01 08:00:00 IDT 2016 | Sun Dec 29 00:00:00 IST 2013 | Sun Dec 29 00:00:00 IST 2013 |  | COMPLETED
18 | FINISH_MILESTONE | Complete the down track tunnel of the South Tunnels, excluding cross passages and backfilling | Sun May 01 08:00:00 IDT 2016 | Sun May 01 08:00:00 IDT 2016 | Fri Nov 07 00:00:00 IST 2014 | Fri Nov 07 00:00:00 IST 2014 |  | COMPLETED
19 | FINISH_MILESTONE | Complete the up track tunnel of the South Tunnels and the Shunt Neck Tunnel w/ Emergency Exit Point,excl. backfilling | Sun May 01 08:00:00 IDT 2016 | Sun May 01 08:00:00 IDT 2016 | Mon Nov 30 00:00:00 IST 2015 | Mon Nov 30 00:00:00 IST 2015 |  | COMPLETED
20 | FINISH_MILESTONE | Complete Closing of the access opening for up track and C&C Tunnel at TUT within Works Area 5.1 & backfilling | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 | Mon Sep 19 00:00:00 IDT 2016 | Mon Sep 19 00:00:00 IDT 2016 |  | COMPLETED
21 |  | Schedule of Power on Dates | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017
22 | START_MILESTONE | Overhead Lines Power On - South Tunnels (by Designated C830) | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
23 | START_MILESTONE | Overhead Lines Power On - North Tunnels (by Designated C830) | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
24 |  | Temporary Access Opening for Designated Contractors | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016
25 | TASK_DEPENDENT | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
26 |  | Close Out Temporary Access at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016
27 | TASK_DEPENDENT | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
28 |  | Tai Kong Po Shaft | Mon Apr 02 08:00:00 IDT 2012 | Thu Sep 01 08:00:00 IDT 2016 | Mon Apr 02 08:00:00 IDT 2012 | Thu Mar 31 00:00:00 IDT 2016
29 | START_MILESTONE | Tai Kong Po Shaft (ready not later than) | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 |  | COMPLETED
30 | FINISH_MILESTONE | Remove all equipment, plant, materials and temporary works, and reinstate the area after final TBM removal | Thu Sep 01 08:00:00 IDT 2016 | Thu Sep 01 08:00:00 IDT 2016 | Thu Mar 31 00:00:00 IDT 2016 | Thu Mar 31 00:00:00 IDT 2016 |  | COMPLETED
31 |  | Interface with Contract 823B | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Sun Mar 24 18:00:00 IST 2013 | Sun Mar 24 18:00:00 IST 2013
32 | FINISH_MILESTONE | 823B to complete East Culvert for 823A connection | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Sun Mar 24 18:00:00 IST 2013 | Sun Mar 24 18:00:00 IST 2013 |  | COMPLETED
33 |  | Cost Centre A - Preliminaries | Mon Oct 04 18:00:00 IST 2010 | Mon Jun 12 18:00:00 IDT 2017 | Mon Oct 04 18:00:00 IST 2010
34 |  | Milestone A1 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010
35 | FINISH_MILESTONE | Approval of Contractor's Submission - Preliminary Master Programme (G4.6.1) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
36 | FINISH_MILESTONE | Approval of Contractor's Submission - Time Chainage Programme (G4.11.1) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
37 | FINISH_MILESTONE | Approval of Contractor's Submission - Environmental Management Plan (G5.1.10) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
38 | FINISH_MILESTONE | Approval of Contractor's Submission - Quality Plan (G9.2.1) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
39 | FINISH_MILESTONE | Approval of Contractor's Submission - Method of Construction (G12.1.1) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
40 | FINISH_MILESTONE | Approval of Contractor's Submission - Submission Schedule (G12.11.1) | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
41 |  | Milestone A2 | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011
42 | FINISH_MILESTONE | Engineer's confirmation of satisfactory implementation of Specified Plans | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
43 |  | Milestone A3 | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011
44 | FINISH_MILESTONE | Prepare and submit Contamination Assessment Report (CAR) & Remediation Action Plan (RAP) for WAs 3.1, 3.2, 3.3 & 3.3A | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
45 |  | Milestone A4 | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011
46 | FINISH_MILESTONE | Engineer's confirmation of satisfactory implementation of Specified Plans and Programming Management System | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
47 |  | Milestone A5 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012
48 | FINISH_MILESTONE | Approval of detailed Interface Requirements Specifications with the Designated Contractors (Appendix W of the PS) | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
49 | FINISH_MILESTONE | Engineer's confirmation of satisfactory of implementation of Specified Plans | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
50 |  | Milestone A6 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 28 18:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 28 18:00:00 IDT 2012
51 | FINISH_MILESTONE | Approval of detailed Interface Requirements Specifications with the Designated Contractors (Appendix W of the PS) | Sat Jul 28 18:00:00 IDT 2012 | Sat Jul 28 18:00:00 IDT 2012 | Sat Jul 28 18:00:00 IDT 2012 | Sat Jul 28 18:00:00 IDT 2012 |  | COMPLETED
52 | FINISH_MILESTONE | Engineer's confirmation of Satisfactory implementation of Specified Plans and Programming Management System | Fri Jul 27 18:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
53 |  | Milestone A7 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Thu Jan 31 18:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013
54 | FINISH_MILESTONE | Engineer's confirmation of satisfactory implementation of Specified Plans | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Thu Jan 31 18:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
55 |  | Milestone A8 | Fri Jul 26 18:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013
56 | FINISH_MILESTONE | Engineer's confirmation of satisfactory implementation of Specified Plans and Programming Management System | Fri Jul 26 18:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
57 |  | Milestone A9 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Fri Oct 17 18:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014
58 | FINISH_MILESTONE | Complete removal of TBM, all equipment, plant, materials and temp. works, and reinstate the areas at Tai Kong Po Shaft | Wed May 06 18:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Fri Oct 17 18:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
59 |  | Milestone A10 | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016
60 | FINISH_MILESTONE | Complete cross passage construction for ERS to Tse Uk Tsuen | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
61 |  | Milestone A11 | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014
62 | FINISH_MILESTONE | Engineer's confirmation of satisfactory implementation of Specified Plans | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 | Fri Jan 31 18:00:00 IST 2014 |  | COMPLETED
63 |  | Milestone A12 | Thu Sep 01 08:00:00 IDT 2016 | Thu Sep 01 08:00:00 IDT 2016 | Thu Jun 30 08:00:00 IDT 2016 | Thu Jun 30 08:00:00 IDT 2016
64 | FINISH_MILESTONE | Complete installation of all cable brackets supplied by Contract 846 inside all the tunnels | Thu Sep 01 08:00:00 IDT 2016 | Thu Sep 01 08:00:00 IDT 2016 | Thu Jun 30 08:00:00 IDT 2016 | Thu Jun 30 08:00:00 IDT 2016 |  | COMPLETED
65 |  | Milestone A13 | Wed Jan 18 18:00:00 IST 2017 | Wed Jan 18 18:00:00 IST 2017
66 | FINISH_MILESTONE | Approval of draft Operating and Maintenance Manuals and draft as-built drawings for Whole of the Works | Wed Jan 18 18:00:00 IST 2017 | Wed Jan 18 18:00:00 IST 2017 |  |  | 1160.0 | NOT_STARTED
67 |  | Milestone A14 | Mon Jun 12 18:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017
68 | FINISH_MILESTONE | Approval of Operating and Maintenance Manuals and as-built drawings for the Whole of the Works | Mon Jun 12 18:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
69 |  | Cost Centre B1 - Tunnel Boring Machine (North Tunnels) | Wed Sep 15 18:00:00 IST 2010 | Thu Mar 03 18:00:00 IST 2016 | Wed Sep 15 18:00:00 IST 2010 | Thu Mar 03 18:00:00 IST 2016
70 |  | Milestone B1.1 | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010
71 | FINISH_MILESTONE | Confirmation of the order of 1st tunnel boring machine | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
72 |  | Milestone B1.2 | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010
73 | FINISH_MILESTONE | Engineer's confirmation of the acceptance of on-demand bond or bank guarantee in respect of the procurement of TBM | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
74 |  | Milestone B1.3 | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011
75 | FINISH_MILESTONE | Commencement of final assembly for tunnel boring machine at the factory | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
76 |  | Milestone B1.4 | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011
77 | FINISH_MILESTONE | Complete fabrication and factory tests of the tunnel boring machine and ready for shipment to Hong Kong | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011 | Mon Sep 05 18:00:00 IDT 2011 |  | COMPLETED
78 |  | Milestone B1.5 | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012
79 | FINISH_MILESTONE | Comp assembly, T&C of TBM & asso eqpmt (incl. surface eqpmt) & start down track tunnel drive from ERS to Tai Kong Po | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Nov 02 18:00:00 IST 2012 |  | COMPLETED
80 |  | Milestone B1.6 | Fri Dec 05 18:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Nov 28 18:00:00 IST 2014 | Fri Nov 28 18:00:00 IST 2014
81 | FINISH_MILESTONE | Comp assembly, T&C of TBM & asso eqpmt (incl. surface eqpmt) & start up track tunnel drive from ERS to Tai Kong Po | Fri Dec 05 18:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Nov 28 18:00:00 IST 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
82 |  | Milestone B1.7 | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016
83 | FINISH_MILESTONE | Complete dismantling of the North tunnel boring machine | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016 | Thu Mar 03 18:00:00 IST 2016 |  | COMPLETED
84 |  | Cost Centre B2 - Tunnel Boring Machine (South Tunnels) | Sat Dec 10 18:00:00 IST 2011 | Fri Sep 25 18:00:00 IDT 2015 | Sat Dec 10 18:00:00 IST 2011 | Thu Sep 24 18:00:00 IDT 2015
85 |  | Milestone B2.1 | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011
86 | FINISH_MILESTONE | Confirmation of the order of 2nd tunnel boring machine | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
87 |  | Milestone B2.2 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012
88 | FINISH_MILESTONE | Complete fabrication and factory tests of the 2nd tunnel boring machine and delivery to Hong Kong | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
89 |  | Milestone B2.3 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013
90 | FINISH_MILESTONE | Comp assembly, T&C of TBM & asso eqpt (incl surface eqpt) & start down track tunnel drive from ERS to Tse Uk Tsuen Shaft | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
91 |  | Milestone B2.4 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014
92 | FINISH_MILESTONE | Comp assembly, T&C of TBM & asso eqpmt (incl surface eqpmt) & start up track tunnel drive from ERS to Tse Uk Tsuen Shaft | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
93 |  | Milestone B2.5 | Fri Sep 25 18:00:00 IDT 2015 | Fri Sep 25 18:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015
94 | FINISH_MILESTONE | Complete dismantling of the South tunnel boring machine | Fri Sep 25 18:00:00 IDT 2015 | Fri Sep 25 18:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
95 |  | Cost Centre C - Tai Kong Po to ERS Tunnel (Up Track) | Fri May 31 18:00:00 IDT 2013 | Wed Jun 01 08:00:00 IDT 2016 | Wed Oct 17 18:00:00 IST 2012 | Wed Jun 01 18:00:00 IDT 2016
96 |  | Milestone C1 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012
97 | FINISH_MILESTONE | Complete 30% of approved pre-cast segments manufacturing | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
98 |  | Milestone C2 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Mon Dec 03 18:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012
99 | FINISH_MILESTONE | Complete 60% of approved pre-cast segments manufacturing | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Mon Dec 03 18:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
100 |  | Milestone C3 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015
101 | FINISH_MILESTONE | Complete 20% of tunnel drive | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015 |  | COMPLETED
102 |  | Milestone C4 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015
103 | FINISH_MILESTONE | Complete 80% of tunnel drive | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
104 |  | Milestone C5 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016
105 | FINISH_MILESTONE | Complete tunnel invert, walkway and installation of cable brackets supplied by Contract 846 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
106 |  | Cost Centre D - Tai Kong Po to ERS Tunnel (Down Track) | Thu Nov 25 18:00:00 IST 2010 | Mon Jul 27 18:00:00 IDT 2015 | Thu Nov 25 18:00:00 IST 2010 | Fri Jul 17 18:00:00 IDT 2015
107 |  | Milestone D1 | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010
108 | FINISH_MILESTONE | Approval of tunnel lining design | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
109 |  | Milestone D2 | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011
110 | FINISH_MILESTONE | Approval of tunnel segment mould design | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
111 |  | Milestone D3 | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011
112 | FINISH_MILESTONE | Complete fabrication of tunnel segment mould | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
113 |  | Milestone D4 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012
114 | FINISH_MILESTONE | Complete 50% of approved pre-cast segments manufacturing | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
115 |  | Milestone D5 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012
116 | FINISH_MILESTONE | Complete 100% of approved pre-cast segments manufacturing | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
117 |  | Milestone D6 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sun Mar 31 18:00:00 IDT 2013 | Sun Mar 31 18:00:00 IDT 2013
118 | FINISH_MILESTONE | Complete 30% of tunnel drive | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sun Mar 31 18:00:00 IDT 2013 | Sun Mar 31 18:00:00 IDT 2013 |  | COMPLETED
119 |  | Milestone D7 | Tue Aug 19 18:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014
120 | FINISH_MILESTONE | Complete 100% of tunnel drive | Tue Aug 19 18:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
121 |  | Milestone D8 | Mon Jul 27 18:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015
122 | FINISH_MILESTONE | Complete 100% tunnel invert & walkway and complete installation of cable brackets supplied by Contract 846 | Mon Jul 27 18:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
123 |  | Cost Centre E - Tai Kong Po to ERS Tunnel (C&C Tunnel) | Thu Dec 15 18:00:00 IST 2011 | Fri Mar 31 18:00:00 IDT 2017 | Thu Dec 15 18:00:00 IST 2011
124 |  | Milestone E1 | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011
125 | FINISH_MILESTONE | Complete temporary diversion of Wang Toi Shan Shan Tsuen Road | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
126 |  | Milestone E2 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012
127 | FINISH_MILESTONE | Complete the temporary base slab of the northern TBM launching shaft | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
128 |  | Milestone E3 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sun Dec 09 18:00:00 IST 2012 | Sun Dec 09 18:00:00 IST 2012
129 | FINISH_MILESTONE | Complete excavation of the cut and cover tunnels Box 6B | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sun Dec 09 18:00:00 IST 2012 | Sun Dec 09 18:00:00 IST 2012 |  | COMPLETED
130 |  | Milestone E4 | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012
131 | FINISH_MILESTONE | Complete the Box 7B northern cut and cover tunnels to facilitate construction of temporary Kam Tin Nullah above | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
132 |  | Milestone E5 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sat Jan 19 18:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013
133 | FINISH_MILESTONE | Complete temporary diversion of Kam Tin Nullah near Wang Toi Shan Shan Tsuen Road | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Sat Jan 19 18:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
134 |  | Milestone E6 | Fri May 09 18:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 | Tue Dec 31 18:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013
135 | FINISH_MILESTONE | Complete the Box 6B northern cut and cover tunnels to Degree 1 | Fri May 09 18:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 | Tue Dec 31 18:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
136 |  | Milestone E7 | Mon Sep 30 18:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013
137 | FINISH_MILESTONE | Complete excavation of the cut and cover tunnels Box 6A | Mon Sep 30 18:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
138 |  | Milestone E8 | Sat Feb 08 18:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013
139 | FINISH_MILESTONE | Complete the Box 6A northern cut and cover tunnels to Degree 1 | Sat Feb 08 18:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
140 |  | Milestone E9 | Mon Oct 24 18:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016
141 | FINISH_MILESTONE | Complete backfilling of the cut & cover tunnel except Box 6A & 7A | Mon Oct 24 18:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
142 |  | Milestone E10 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Sun Jul 31 08:00:00 IDT 2016 | Sun Jul 31 08:00:00 IDT 2016
143 | FINISH_MILESTONE | Reinstate the Kam Tin Nullah near Wang Toi Shan Shan Tsuen Road and complete gauging stations | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Sun Jul 31 08:00:00 IDT 2016 | Sun Jul 31 08:00:00 IDT 2016 |  | COMPLETED
144 |  | Milestone E11 | Fri Mar 31 18:00:00 IDT 2017 | Fri Mar 31 18:00:00 IDT 2017
145 | FINISH_MILESTONE | Complete all reinstatement works of the Works Areas | Fri Mar 31 18:00:00 IDT 2017 | Fri Mar 31 18:00:00 IDT 2017 |  |  | 584.0 | NOT_STARTED
146 |  | Cost Centre F - ERS to Tse Uk Tsuen Tunnel (Up Track) | Fri May 31 18:00:00 IDT 2013 | Mon Aug 03 18:00:00 IDT 2015 | Thu Feb 28 18:00:00 IST 2013 | Sat Jan 30 18:00:00 IST 2016
147 |  | Milestone F1 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013
148 | FINISH_MILESTONE | Complete 50% of approved pre-cast segments manufacturing | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
149 |  | Milestone F2 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013
150 | FINISH_MILESTONE | Complete 100% of approved pre-cast segments manufacturing | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
151 |  | Milestone F3 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015
152 | FINISH_MILESTONE | Complete 100% of tunnel drive | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 |  | COMPLETED
153 |  | Milestone F4 | Fri Oct 10 18:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Jan 30 18:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016
154 | FINISH_MILESTONE | Complete installation of cable brackets supplied by Contract 846 | Fri Oct 10 18:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Jan 30 18:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
155 |  | Cost Centre G - ERS to Tse Uk Tsuen Tunnel (Down Track) | Thu Aug 30 18:00:00 IDT 2012 | Fri Oct 31 18:00:00 IST 2014 | Thu Aug 30 18:00:00 IDT 2012 | Fri Oct 31 18:00:00 IST 2014
156 |  | Milestone G1 | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012
157 | FINISH_MILESTONE | Complete 50% of approved pre-cast segments manufacturing | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
158 |  | Milestone G2 | Sat Sep 29 18:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Sun Sep 30 18:00:00 IST 2012 | Sun Sep 30 18:00:00 IST 2012
159 | FINISH_MILESTONE | Complete 100% of approved pre-cast segments manufacturing | Sat Sep 29 18:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Sun Sep 30 18:00:00 IST 2012 | Sun Sep 30 18:00:00 IST 2012 |  | COMPLETED
160 |  | Milestone G3 | Thu May 22 18:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014
161 | FINISH_MILESTONE | Complete 100% of tunnel drive | Thu May 22 18:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
162 |  | Milestone G4 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014
163 | FINISH_MILESTONE | Complete tunnel invert, walkway and installation of cable brackets supplied by Contract 846 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
164 |  | Cost Centre H - ERS to Tse Uk Tsuen Tunnel (C&C Tunnel Incl. Shunt Neck) | Sat Apr 16 18:00:00 IDT 2011 | Tue Feb 28 18:00:00 IST 2017 | Sat Apr 16 18:00:00 IDT 2011
165 |  | Milestone H1 | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011
166 | FINISH_MILESTONE | Removal of contamination | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
167 |  | Milestone H2 | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012
168 | FINISH_MILESTONE | Complete diaphragm wall construction for the launching shaft | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
169 |  | Milestone H3 | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012
170 | FINISH_MILESTONE | Complete diaphragm wall construction for the shunt neck | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
171 |  | Milestone H4 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012
172 | FINISH_MILESTONE | Complete excavation for the launching shaft | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
173 |  | Milestone H5 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Mon Jan 21 18:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013
174 | FINISH_MILESTONE | Complete 30% of the cut and cover tunnels | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Mon Jan 21 18:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
175 |  | Milestone H6 | Fri Aug 09 18:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013
176 | FINISH_MILESTONE | Complete 60% of the cut and cover tunnels | Fri Aug 09 18:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
177 |  | Milestone H7 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Dec 31 18:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013
178 | FINISH_MILESTONE | Complete the shunt neck tunnel above south Tunnel | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Dec 31 18:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
179 |  | Milestone H8 | Sat Jan 31 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015 | Sat Feb 28 18:00:00 IST 2015 | Sat Feb 28 18:00:00 IST 2015
180 | FINISH_MILESTONE | Complete the remaining down track cut and cover tunnel to Degree 1 | Sat Jan 31 18:00:00 IST 2015 | Sat Jan 31 18:00:00 IST 2015 | Sat Feb 28 18:00:00 IST 2015 | Sat Feb 28 18:00:00 IST 2015 |  | COMPLETED
181 |  | Milestone H9 | Wed Jan 13 18:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Tue Dec 22 18:00:00 IST 2015 | Tue Dec 22 18:00:00 IST 2015
182 | FINISH_MILESTONE | Complete the remaining up track cut and cover tunnel and the shunt neck to Degree 1 | Wed Jan 13 18:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Tue Dec 22 18:00:00 IST 2015 | Tue Dec 22 18:00:00 IST 2015 |  | COMPLETED
183 |  | Milestone H10 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017
184 | FINISH_MILESTONE | Complete all reinstatement works within the Works Areas except Works Area 4.9 and 4.12C | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
185 |  | Milestone H11 | Tue Feb 28 18:00:00 IST 2017 | Tue Feb 28 18:00:00 IST 2017
186 | FINISH_MILESTONE | Complete all tree planting and reinstate Works Area 4.12C | Tue Feb 28 18:00:00 IST 2017 | Tue Feb 28 18:00:00 IST 2017 |  |  | 832.0 | NOT_STARTED
187 |  | Cost Centre I - Tse Uk Tsuen Work Area | Fri Nov 11 18:00:00 IST 2011 | Mon Oct 03 18:00:00 IDT 2016 | Fri Nov 11 18:00:00 IST 2011 | Sun Sep 18 18:00:00 IDT 2016
188 |  | Milestone I1 | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011
189 | FINISH_MILESTONE | Complete 100% of diaphragm wall | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
190 |  | Milestone I2 | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012
191 | FINISH_MILESTONE | Complete pumping test | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
192 |  | Milestone I3 | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012
193 | FINISH_MILESTONE | Complete 30% of excavation | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
194 |  | Milestone I4 | Sun Nov 01 08:00:00 IST 2015 | Sun Nov 01 08:00:00 IST 2015 | Sun Jul 14 18:00:00 IDT 2013 | Sun Jul 14 18:00:00 IDT 2013
195 | FINISH_MILESTONE | Complete the temporary base slab for Tse Uk Tsuen Shaft | Sun Nov 01 08:00:00 IST 2015 | Sun Nov 01 08:00:00 IST 2015 | Sun Jul 14 18:00:00 IDT 2013 | Sun Jul 14 18:00:00 IDT 2013 |  | COMPLETED
196 |  | Milestone I5 | Thu Nov 20 18:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014
197 | FINISH_MILESTONE | Complete the down track cut and cover tunnel to Degree 1 | Thu Nov 20 18:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
198 |  | Milestone I6 | Wed Feb 03 18:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016
199 | FINISH_MILESTONE | Complete the up track cut and cover tunnel to Degree 1 | Wed Feb 03 18:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
200 |  | Milestone I7 | Wed Apr 20 18:00:00 IDT 2016 | Wed Apr 20 18:00:00 IDT 2016 | Tue Jan 12 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016
201 | FINISH_MILESTONE | Complete closing of the access opening | Wed Apr 20 18:00:00 IDT 2016 | Wed Apr 20 18:00:00 IDT 2016 | Tue Jan 12 18:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
202 |  | Milestone I8 | Mon Oct 03 18:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Sun Sep 18 18:00:00 IDT 2016 | Sun Sep 18 18:00:00 IDT 2016
203 | FINISH_MILESTONE | Complete backfilling of the shaft | Mon Oct 03 18:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Sun Sep 18 18:00:00 IDT 2016 | Sun Sep 18 18:00:00 IDT 2016 |  | COMPLETED
204 |  | Cost Centre J - Associated Works | Sat May 21 18:00:00 IDT 2011 | Fri Mar 31 18:00:00 IDT 2017 | Sat May 21 18:00:00 IDT 2011
205 |  | Milestone J1 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011
206 | FINISH_MILESTONE | Complete installation of ground settlement markers within Works Areas 3.1, 3.2 and 3.3 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
207 |  | Milestone J2 | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011
208 | FINISH_MILESTONE | Complete ground treatment works adjacent to cut and cover tunnels at the northern launching shaft | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
209 |  | Milestone J3 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012
210 | FINISH_MILESTONE | Submit instrumentation monitoring report | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
211 |  | Milestone J4 | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012
212 | FINISH_MILESTONE | Submit instrumentation monitoring report | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
213 |  | Milestone J5 | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012
214 | FINISH_MILESTONE | Complete ground treatment works adjacent to Tse Uk Tsuen shaft | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
215 |  | Milestone J6 | Sat Oct 19 18:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013
216 | FINISH_MILESTONE | Submit instrumentation monitoring report | Sat Oct 19 18:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Feb 28 18:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
217 |  | Milestone J7 | Thu Mar 20 18:00:00 IST 2014 | Thu Mar 20 18:00:00 IST 2014 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013
218 | FINISH_MILESTONE | Submit instrumentation monitoring report | Thu Mar 20 18:00:00 IST 2014 | Thu Mar 20 18:00:00 IST 2014 | Wed Jul 31 18:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
219 |  | Milestone J8 | Sat Jan 30 18:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Mon Jan 25 18:00:00 IST 2016 | Mon Jan 25 18:00:00 IST 2016
220 | FINISH_MILESTONE | Complete cross passages construction for Tai Kong Po to ERS Tunnels | Sat Jan 30 18:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Mon Jan 25 18:00:00 IST 2016 | Mon Jan 25 18:00:00 IST 2016 |  | COMPLETED
221 |  | Milestone J9 | Fri Feb 28 18:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 | Sun Feb 23 18:00:00 IST 2014 | Sun Feb 23 18:00:00 IST 2014
222 | FINISH_MILESTONE | Submit instrumentation monitoring report | Fri Feb 28 18:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 | Sun Feb 23 18:00:00 IST 2014 | Sun Feb 23 18:00:00 IST 2014 |  | COMPLETED
223 |  | Milestone J10 | Sun Aug 31 18:00:00 IDT 2014 | Sun Aug 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014
224 | FINISH_MILESTONE | Submit instrumentation monitoring report | Sun Aug 31 18:00:00 IDT 2014 | Sun Aug 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
225 |  | Milestone J11 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sun Jan 25 18:00:00 IST 2015 | Sun Jan 25 18:00:00 IST 2015
226 | FINISH_MILESTONE | Complete the East Culvert in Works Area 4.4 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sun Jan 25 18:00:00 IST 2015 | Sun Jan 25 18:00:00 IST 2015 |  | COMPLETED
227 |  | Milestone J12 | Fri Mar 31 18:00:00 IDT 2017 | Fri Mar 31 18:00:00 IDT 2017
228 | FINISH_MILESTONE | Complete all works | Fri Mar 31 18:00:00 IDT 2017 | Fri Mar 31 18:00:00 IDT 2017 |  |  | 584.0 | NOT_STARTED
229 |  | Cost Centre K - Tai Lam Kok Baring Facility
230 |  | Milestone K1
231 |  | Milestone K2
232 |  | Milestone K3
233 |  | Access Dates for Works Areas | Mon Jul 19 08:00:00 IDT 2010 | Sun Jan 01 08:00:00 IST 2017 | Mon Jul 19 08:00:00 IDT 2010
234 |  | First Possession Dates | Mon Jul 19 08:00:00 IDT 2010 | Sat Feb 01 08:00:00 IST 2014 | Mon Jul 19 08:00:00 IDT 2010 | Mon Apr 01 08:00:00 IDT 2013
235 | START_MILESTONE | Works Area 1.15A | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 |  | COMPLETED
236 | START_MILESTONE | Works Area 1.15B (Option No. 1) | Sat Feb 01 08:00:00 IST 2014 | Sat Feb 01 08:00:00 IST 2014 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 |  | COMPLETED
237 | START_MILESTONE | Works Area 3.1 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
238 | START_MILESTONE | Works Area 3.2 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
239 | START_MILESTONE | Works Area 3.3 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
240 | START_MILESTONE | Works Area 3.3A | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
241 | START_MILESTONE | Works Area 3.3B | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
242 | START_MILESTONE | Works Area 3.4 (subject to SLG approval) | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 |  | COMPLETED
243 | START_MILESTONE | Works Area 3.11 | Mon Aug 16 08:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 |  | COMPLETED
244 | START_MILESTONE | Works Area 4.1 (subject to SLG approval) | Thu Apr 07 08:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 |  | COMPLETED
245 | START_MILESTONE | Works Area 4.2 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
246 | START_MILESTONE | Works Area 4.3 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
247 | START_MILESTONE | Works Area 4.4 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
248 | START_MILESTONE | Works Area 4.9 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
249 | START_MILESTONE | Works Area 4.9A | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
250 | START_MILESTONE | Works Area 4.10 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
251 | START_MILESTONE | Works Area 4.10A | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
252 | START_MILESTONE | Works Area 4.11 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
253 | START_MILESTONE | Works Area 4.12A | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
254 | START_MILESTONE | Works Area 4.12B | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
255 | START_MILESTONE | Works Area 4.12C | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
256 | START_MILESTONE | Works Area 4.13 (subject to SLG approval) | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 |  | COMPLETED
257 | START_MILESTONE | Works Area 4.15 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
258 | START_MILESTONE | Works Area 4.15A | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
259 | START_MILESTONE | Works Area 4.15B | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 |  | COMPLETED
260 | START_MILESTONE | Works Area 4.16 (subject to SLG approval) | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 |  | COMPLETED
261 | START_MILESTONE | Works Area 5.1 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 |  | COMPLETED
262 | START_MILESTONE | Works Area 5.2 (subject to SLG approval) | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 | Sun Mar 20 08:00:00 IST 2011 |  | COMPLETED
263 | START_MILESTONE | Works Area 5.3 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 |  | COMPLETED
264 |  | Second Possession Dates | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017
265 | START_MILESTONE | Works Area 3.1 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
266 | START_MILESTONE | Works Area 3.2 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
267 | START_MILESTONE | Works Area 4.15B | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
268 | START_MILESTONE | Works Area 5.3 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
269 |  | Handover Dates for Works Areas | Mon Feb 01 08:00:00 IST 2016 | Fri Aug 11 18:00:00 IDT 2017 | Mon Feb 01 18:00:00 IST 2016
270 |  | First Return Dates | Mon Feb 01 08:00:00 IST 2016 | Fri Aug 11 18:00:00 IDT 2017 | Mon Feb 01 18:00:00 IST 2016
271 | FINISH_MILESTONE | Works Area 1.15A | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
272 | FINISH_MILESTONE | Works Area 1.15B | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
273 | FINISH_MILESTONE | Works Area 3.1 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Sat Jul 23 18:00:00 IDT 2016 | Sat Jul 23 18:00:00 IDT 2016 |  | COMPLETED
274 | FINISH_MILESTONE | Works Area 3.2 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Sat Jul 09 18:00:00 IDT 2016 | Sat Jul 09 18:00:00 IDT 2016 |  | COMPLETED
275 | FINISH_MILESTONE | Works Area 3.3 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
276 | FINISH_MILESTONE | Works Area 3.3A | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
277 | FINISH_MILESTONE | Works Area 3.3B | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
278 | FINISH_MILESTONE | Works Area 3.4 (subject to SLG approval) | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
279 | FINISH_MILESTONE | Works Area 3.11 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
280 | FINISH_MILESTONE | Works Area 4.1 (subject to SLG approval) | Sat Jul 09 18:00:00 IDT 2016 | Sat Jul 09 18:00:00 IDT 2016 | Sun Jul 24 18:00:00 IDT 2016 | Sun Jul 24 18:00:00 IDT 2016 |  | COMPLETED
281 | FINISH_MILESTONE | Works Area 4.2 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
282 | FINISH_MILESTONE | Works Area 4.3 | Thu Sep 01 08:00:00 IDT 2016 | Thu Sep 01 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
283 | FINISH_MILESTONE | Works Area 4.4 | Thu Sep 01 08:00:00 IDT 2016 | Thu Sep 01 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
284 | FINISH_MILESTONE | Works Area 4.9 | Fri Aug 11 18:00:00 IDT 2017 | Fri Aug 11 18:00:00 IDT 2017 | Mon Sep 19 18:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
285 | FINISH_MILESTONE | Works Area 4.9A | Fri Aug 11 18:00:00 IDT 2017 | Fri Aug 11 18:00:00 IDT 2017 | Mon Sep 19 18:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
286 | FINISH_MILESTONE | Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 |  | COMPLETED
287 | FINISH_MILESTONE | Works Area 4.10A | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 |  | COMPLETED
288 | FINISH_MILESTONE | Works Area 4.11 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Fri Feb 19 18:00:00 IST 2016 | Fri Feb 19 18:00:00 IST 2016 |  | COMPLETED
289 | FINISH_MILESTONE | Works Area 4.12A | Tue Feb 28 18:00:00 IST 2017 | Tue Feb 28 18:00:00 IST 2017 |  |  | 832.0 | NOT_STARTED
290 | FINISH_MILESTONE | Works Area 4.12B | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
291 | FINISH_MILESTONE | Works Area 4.12C | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
292 | FINISH_MILESTONE | Works Area 4.13 (subject to SLG approval) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
293 | FINISH_MILESTONE | Works Area 4.15 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
294 | FINISH_MILESTONE | Works Area 4.15A | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
295 | FINISH_MILESTONE | Works Area 4.15B | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
296 | FINISH_MILESTONE | Works Area 4.16 (subject to SLG approval) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
297 | FINISH_MILESTONE | Works Area 5.1 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  |  | NOT_STARTED
298 | FINISH_MILESTONE | Works Area 5.2 (subject to SLG approval) | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
299 | FINISH_MILESTONE | Works Area 5.3 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
300 |  | Second Return Dates | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017
301 | FINISH_MILESTONE | Works Area 3.1 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
302 | FINISH_MILESTONE | Works Area 3.2 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
303 | FINISH_MILESTONE | Works Area 4.15B | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
304 | FINISH_MILESTONE | Works Area 5.3 | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
305 |  | Interfacing Contractors | Tue Sep 25 08:00:00 IST 2012 | Fri Jan 08 18:00:00 IST 2016 | Tue Sep 25 08:00:00 IST 2012 | Fri Jan 08 18:00:00 IST 2016
306 |  | Contract 823A / Contract 824 | Wed Jul 02 08:00:00 IDT 2014 | Fri Jan 08 18:00:00 IST 2016 | Sat Jul 26 08:00:00 IDT 2014 | Fri Jan 08 18:00:00 IST 2016
307 | TASK_DEPENDENT | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TASK_DEPENDENT | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TASK_DEPENDENT | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TASK_DEPENDENT | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
311 |  | Contract 823A / Contract 823B | Fri Feb 28 18:00:00 IST 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Nov 27 18:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013
312 | FINISH_MILESTONE | Final tunnel connections by 823B at southern cut and cover tunnels | Tue May 13 18:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Nov 27 18:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 |  | COMPLETED
313 | FINISH_MILESTONE | Final tunnel connection to 823B northern cut and cover tunnels | Fri Feb 28 18:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 | Thu Nov 28 18:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
314 |  | Contract 823A / Contract 822 | Tue Sep 25 08:00:00 IST 2012 | Sun Aug 31 18:00:00 IDT 2014 | Tue Sep 25 08:00:00 IST 2012 | Sun Aug 31 18:00:00 IDT 2014
315 | START_MILESTONE | Ground treatment works by 822 | Tue Sep 25 08:00:00 IST 2012 | Tue Sep 25 08:00:00 IST 2012 | Tue Sep 25 08:00:00 IST 2012 | Tue Sep 25 08:00:00 IST 2012 |  | COMPLETED
316 | FINISH_MILESTONE | 822 to complete lining for 823A connection (Down Track) | Mon Mar 31 18:00:00 IDT 2014 | Mon Mar 31 18:00:00 IDT 2014 | Mon Mar 31 18:00:00 IDT 2014 | Mon Mar 31 18:00:00 IDT 2014 |  | COMPLETED
317 | FINISH_MILESTONE | 822 to complete lining for 823A connection (Up Track) | Sun Aug 31 18:00:00 IDT 2014 | Sun Aug 31 18:00:00 IDT 2014 | Sun Aug 31 18:00:00 IDT 2014 | Sun Aug 31 18:00:00 IDT 2014 |  | COMPLETED
318 |  | Access Dates for Designated Contractors | Sun Dec 01 08:00:00 IST 2013 | Mon Jan 02 08:00:00 IST 2017 | Mon Jul 01 08:00:00 IDT 2013
319 |  | 827 - Supply and Installation of Cross Passage Doors | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016
320 | START_MILESTONE | All cross passages within Tai Kong Po to ERS Tunnels,down track for door installation | Fri Jan 01 08:00:00 IST 2016 | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
321 | START_MILESTONE | All cross passages within Tai Kong Po to ERS Tunnels,up track for door installation | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
322 | START_MILESTONE | All cross passages within ERS to Tse Uk Tsuen Tunnels, down track, for door frame installation | Fri Jan 01 08:00:00 IST 2016 | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
323 | START_MILESTONE | All cross passages within ERS to Tse Uk Tsuen Tunnels, uptrack, for door installation | Fri Jan 01 08:00:00 IST 2016 | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
324 |  | 830 - Trackwork and Overhead Line System | Sun Mar 01 08:00:00 IST 2015 | Tue May 03 08:00:00 IDT 2016 | Sun Mar 01 08:00:00 IST 2015 | Tue May 31 08:00:00 IDT 2016
325 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track, excluding Box 6A | Sun Mar 01 08:00:00 IST 2015 | Sun Mar 01 08:00:00 IST 2015 | Sun Mar 01 08:00:00 IST 2015 | Sun Mar 01 08:00:00 IST 2015 |  | COMPLETED
326 | START_MILESTONE | Tai Kong Po to ERS Tunnels, (Box 7B & 6B) up track | Sun May 01 08:00:00 IDT 2016 | Sun May 01 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 |  | COMPLETED
327 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track excluding Box 7A, 7B & 6B | Sun May 01 08:00:00 IDT 2016 | Sun May 01 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 |  | COMPLETED
328 | START_MILESTONE | Tai Kong Po to ERS Tunnels, (Box 6A) both up & down tracks | Tue May 03 08:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 |  | COMPLETED
329 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Mon Mar 02 08:00:00 IST 2015 | Mon Mar 02 08:00:00 IST 2015 | Sun Mar 01 08:00:00 IST 2015 | Sun Mar 01 08:00:00 IST 2015 |  | COMPLETED
330 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track including shunt neck | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 |  | COMPLETED
331 |  | 841A - Signalling System - Trackside Equipment | Fri Jan 01 08:00:00 IST 2016 | Mon Jan 02 08:00:00 IST 2017 | Sat Jan 02 08:00:00 IST 2016
332 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Fri Jan 01 08:00:00 IST 2016 | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
333 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
334 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Fri Jan 01 08:00:00 IST 2016 | Fri Jan 01 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 | Sat Jan 02 08:00:00 IST 2016 |  | COMPLETED
335 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 | Fri Jul 01 08:00:00 IDT 2016 |  | COMPLETED
336 |  | 841B - Signalling System - Train Borne Equipment | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
337 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
338 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
339 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
340 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
341 |  | 843 - Tunnel Environmental Control System | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017
342 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
343 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
344 |  | 844 - 11kV Power Distribution | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
345 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
346 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
347 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
348 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
349 |  | 846 - Trackside Auxiliaries | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
350 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
351 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
352 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
353 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
354 |  | 849 - Radio Communication System | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
355 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
356 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
357 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
358 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
359 |  | 850 - Passenger Mobile Communications Systems | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
360 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
361 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
362 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
363 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
364 |  | 851 - Fixed Communication System | Sun Jan 01 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017
365 | START_MILESTONE | Tai Kong Po to ERS Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
366 | START_MILESTONE | Tai Kong Po to ERS Tunnels, up track | Mon Jan 02 08:00:00 IST 2017 | Mon Jan 02 08:00:00 IST 2017 |  |  | 1112.0 | NOT_STARTED
367 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, down track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
368 | START_MILESTONE | ERS to Tse Uk Tsuen Tunnels, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
369 |  | 8203 - Construction Stage Mobile Phone Network | Sun Dec 01 08:00:00 IST 2013 | Sun Jan 01 08:00:00 IST 2017 | Mon Jul 01 08:00:00 IDT 2013
370 | START_MILESTONE | Tai Kong Po to ERS Tunnels, both up and down tracks | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013 | Mon Jul 01 08:00:00 IDT 2013 | Mon Jul 01 08:00:00 IDT 2013 |  | COMPLETED
371 | START_MILESTONE | ERS to Tse Uk Tsuen, down track | Sun Dec 01 08:00:00 IST 2013 | Sun Dec 01 08:00:00 IST 2013 | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 |  | COMPLETED
372 | START_MILESTONE | ERS to Tse Uk Tsuen, up track | Sun Jan 01 08:00:00 IST 2017 | Sun Jan 01 08:00:00 IST 2017 |  |  | 1304.0 | NOT_STARTED
373 |  | Preliminaries
374 |  | Preliminaries and General Requirements | Mon Jul 19 08:00:00 IDT 2010 | Mon Jun 12 18:00:00 IDT 2017 | Mon Jul 19 08:00:00 IDT 2010
375 |  | Site Accommodation & Services to the Engineer | Mon Jul 19 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Jul 19 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015
376 | TASK_DEPENDENT | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TASK_DEPENDENT | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TASK_DEPENDENT | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TASK_DEPENDENT | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TASK_DEPENDENT | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TASK_DEPENDENT | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
382 |  | Programmme Management System | Mon Jul 19 08:00:00 IDT 2010 | Fri Jul 26 18:00:00 IDT 2013 | Mon Jul 19 08:00:00 IDT 2010 | Fri Jul 26 18:00:00 IDT 2013
383 | TASK_DEPENDENT | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TASK_DEPENDENT | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TASK_DEPENDENT | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TASK_DEPENDENT | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TASK_DEPENDENT | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TASK_DEPENDENT | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TASK_DEPENDENT | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
390 |  | Specified Plan Management | Mon Jul 19 08:00:00 IDT 2010 | Thu Jun 05 18:00:00 IDT 2014 | Mon Jul 19 08:00:00 IDT 2010 | Fri Jan 24 18:00:00 IST 2014
391 | TASK_DEPENDENT | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TASK_DEPENDENT | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TASK_DEPENDENT | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TASK_DEPENDENT | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TASK_DEPENDENT | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TASK_DEPENDENT | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TASK_DEPENDENT | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TASK_DEPENDENT | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TASK_DEPENDENT | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TASK_DEPENDENT | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
407 |  | General Submission | Mon Jul 19 08:00:00 IDT 2010 | Mon Mar 14 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Mon Mar 14 18:00:00 IST 2011
408 | TASK_DEPENDENT | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TASK_DEPENDENT | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TASK_DEPENDENT | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TASK_DEPENDENT | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TASK_DEPENDENT | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TASK_DEPENDENT | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TASK_DEPENDENT | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TASK_DEPENDENT | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TASK_DEPENDENT | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TASK_DEPENDENT | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TASK_DEPENDENT | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TASK_DEPENDENT | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TASK_DEPENDENT | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TASK_DEPENDENT | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TASK_DEPENDENT | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TASK_DEPENDENT | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TASK_DEPENDENT | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TASK_DEPENDENT | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TASK_DEPENDENT | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TASK_DEPENDENT | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TASK_DEPENDENT | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TASK_DEPENDENT | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TASK_DEPENDENT | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TASK_DEPENDENT | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TASK_DEPENDENT | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TASK_DEPENDENT | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TASK_DEPENDENT | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TASK_DEPENDENT | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TASK_DEPENDENT | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TASK_DEPENDENT | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
438 |  | Preliminary Works | Mon Aug 16 08:00:00 IDT 2010 | Fri Jul 25 18:00:00 IDT 2014 | Mon Aug 16 08:00:00 IDT 2010 | Fri Jul 25 18:00:00 IDT 2014
439 |  | General Works | Mon Aug 16 08:00:00 IDT 2010 | Wed Nov 30 18:00:00 IST 2011 | Mon Aug 16 08:00:00 IDT 2010 | Wed Nov 30 18:00:00 IST 2011
440 | TASK_DEPENDENT | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TASK_DEPENDENT | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TASK_DEPENDENT | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TASK_DEPENDENT | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TASK_DEPENDENT | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TASK_DEPENDENT | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TASK_DEPENDENT | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TASK_DEPENDENT | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TASK_DEPENDENT | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TASK_DEPENDENT | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TASK_DEPENDENT | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TASK_DEPENDENT | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TASK_DEPENDENT | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TASK_DEPENDENT | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TASK_DEPENDENT | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TASK_DEPENDENT | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TASK_DEPENDENT | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TASK_DEPENDENT | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TASK_DEPENDENT | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TASK_DEPENDENT | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TASK_DEPENDENT | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TASK_DEPENDENT | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TASK_DEPENDENT | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TASK_DEPENDENT | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TASK_DEPENDENT | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TASK_DEPENDENT | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TASK_DEPENDENT | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TASK_DEPENDENT | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TASK_DEPENDENT | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TASK_DEPENDENT | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TASK_DEPENDENT | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TASK_DEPENDENT | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TASK_DEPENDENT | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TASK_DEPENDENT | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TASK_DEPENDENT | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TASK_DEPENDENT | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TASK_DEPENDENT | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TASK_DEPENDENT | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TASK_DEPENDENT | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
479 |  | Instrumentation Monitoring | Thu Jan 20 08:00:00 IST 2011 | Fri Jul 25 18:00:00 IDT 2014 | Thu Jan 20 08:00:00 IST 2011 | Fri Jul 25 18:00:00 IDT 2014
480 | TASK_DEPENDENT | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TASK_DEPENDENT | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TASK_DEPENDENT | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TASK_DEPENDENT | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TASK_DEPENDENT | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TASK_DEPENDENT | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TASK_DEPENDENT | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
487 |  | Archaeology Survey and Rescue Operation (South Tunnels Area) | Mon Jan 03 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Mon Jan 03 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011
488 | TASK_DEPENDENT | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TASK_DEPENDENT | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TASK_DEPENDENT | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TASK_DEPENDENT | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TASK_DEPENDENT | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
493 |  | Temporary Works | Mon Jul 19 08:00:00 IDT 2010 | Sat Jan 22 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jan 22 18:00:00 IST 2011
494 | TASK_DEPENDENT | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TASK_DEPENDENT | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TASK_DEPENDENT | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TASK_DEPENDENT | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TASK_DEPENDENT | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TASK_DEPENDENT | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TASK_DEPENDENT | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TASK_DEPENDENT | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
502 |  | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015
503 | TASK_DEPENDENT | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
504 |  | Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Oct 08 08:00:00 IST 2011 | Fri Jul 27 18:00:00 IDT 2012
505 | TASK_DEPENDENT | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TASK_DEPENDENT | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TASK_DEPENDENT | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TASK_DEPENDENT | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
509 |  | O&M Manuals and As-Built Drawings | Mon Aug 24 08:00:00 IDT 2015 | Mon Jun 12 18:00:00 IDT 2017 | Mon Jul 28 08:00:00 IDT 2014
510 | TASK_DEPENDENT | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TASK_DEPENDENT | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TASK_DEPENDENT | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TASK_DEPENDENT | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TASK_DEPENDENT | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
515 |  | Design Submissions | Mon Jul 19 08:00:00 IDT 2010 | Sat Apr 30 18:00:00 IDT 2016 | Mon Jul 19 08:00:00 IDT 2010 | Sat Oct 24 18:00:00 IDT 2015
516 |  | General | Mon Jul 19 08:00:00 IDT 2010 | Thu Nov 10 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Thu Nov 10 18:00:00 IST 2011
517 | TASK_DEPENDENT | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TASK_DEPENDENT | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TASK_DEPENDENT | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TASK_DEPENDENT | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TASK_DEPENDENT | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
522 |  | Design for TBM Tunnel | Mon Jul 19 08:00:00 IDT 2010 | Mon Mar 05 18:00:00 IST 2012 | Mon Jul 19 08:00:00 IDT 2010 | Mon Mar 05 18:00:00 IST 2012
523 |  | TBM Design | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010
524 | TASK_DEPENDENT | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TASK_DEPENDENT | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TASK_DEPENDENT | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
527 |  | Design for Permanent Lining for Main Tunnels | Mon Jul 19 08:00:00 IDT 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Fri Jan 07 18:00:00 IST 2011
528 | TASK_DEPENDENT | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TASK_DEPENDENT | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TASK_DEPENDENT | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
535 |  | Design for Permanent Lining for Cross Passages and Main Tunnel Connections | Sat Jan 08 08:00:00 IST 2011 | Mon Jul 18 18:00:00 IDT 2011 | Sat Jan 08 08:00:00 IST 2011 | Mon Jul 18 18:00:00 IDT 2011
536 | TASK_DEPENDENT | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TASK_DEPENDENT | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TASK_DEPENDENT | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TASK_DEPENDENT | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TASK_DEPENDENT | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
545 |  | Design for Temporary Support for Cross-Passage | Tue Jul 19 08:00:00 IDT 2011 | Thu Nov 10 18:00:00 IST 2011 | Tue Jul 19 08:00:00 IDT 2011 | Thu Nov 10 18:00:00 IST 2011
546 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TASK_DEPENDENT | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
551 |  | Design for Connection between Bored Tunnels and Cut & Cover Tunnels | Tue Aug 30 08:00:00 IDT 2011 | Mon Mar 05 18:00:00 IST 2012 | Tue Aug 30 08:00:00 IDT 2011 | Mon Mar 05 18:00:00 IST 2012
552 | TASK_DEPENDENT | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TASK_DEPENDENT | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TASK_DEPENDENT | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TASK_DEPENDENT | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TASK_DEPENDENT | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
561 |  | Tunnel Segment Mould | Fri Nov 26 08:00:00 IST 2010 | Mon Feb 14 18:00:00 IST 2011 | Fri Nov 26 08:00:00 IST 2010 | Mon Feb 14 18:00:00 IST 2011
562 | TASK_DEPENDENT | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TASK_DEPENDENT | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TASK_DEPENDENT | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TASK_DEPENDENT | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
566 |  | Design for Launching Shaft | Mon Jul 19 08:00:00 IDT 2010 | Tue Feb 28 18:00:00 IST 2012 | Mon Jul 19 08:00:00 IDT 2010 | Tue Feb 28 18:00:00 IST 2012
567 |  | Design forTemporary Cofferdam for Northern Launching Shaft | Mon Jul 19 08:00:00 IDT 2010 | Wed Nov 10 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Nov 10 18:00:00 IST 2010
568 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TASK_DEPENDENT | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
573 |  | Design for Temporary Cofferdam for Southern Launching Shaft & Shunt Neck | Thu Nov 11 08:00:00 IST 2010 | Wed Mar 09 18:00:00 IST 2011 | Thu Nov 11 08:00:00 IST 2010 | Wed Mar 09 18:00:00 IST 2011
574 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TASK_DEPENDENT | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
579 |  | Design for Temporary Cofferdam for Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2011 | Fri Jul 08 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Fri Jul 08 18:00:00 IDT 2011
580 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TASK_DEPENDENT | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
585 |  | Design for Temporary Works for TBM Launching and Retrieval | Sat Jul 09 08:00:00 IDT 2011 | Tue Nov 01 18:00:00 IST 2011 | Sat Jul 09 08:00:00 IDT 2011 | Tue Nov 01 18:00:00 IST 2011
586 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TASK_DEPENDENT | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
591 |  | Design for Temporary Noise Enclousure for Launching Shafts | Wed Nov 02 08:00:00 IST 2011 | Tue Feb 28 18:00:00 IST 2012 | Wed Nov 02 08:00:00 IST 2011 | Tue Feb 28 18:00:00 IST 2012
592 | TASK_DEPENDENT | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TASK_DEPENDENT | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TASK_DEPENDENT | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TASK_DEPENDENT | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TASK_DEPENDENT | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
597 |  | Design for Cut & Cover Tunnel | Wed Dec 14 08:00:00 IST 2011 | Sat Apr 14 18:00:00 IDT 2012 | Wed Dec 14 08:00:00 IST 2011 | Sat Apr 14 18:00:00 IDT 2012
598 |  | Design for Formworks and Falseworks for Box Tunnel | Wed Dec 14 08:00:00 IST 2011 | Sat Apr 14 18:00:00 IDT 2012 | Wed Dec 14 08:00:00 IST 2011 | Sat Apr 14 18:00:00 IDT 2012
599 | TASK_DEPENDENT | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TASK_DEPENDENT | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TASK_DEPENDENT | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TASK_DEPENDENT | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
603 |  | Design for Miscellaneous | Mon Jul 19 08:00:00 IDT 2010 | Sat Apr 30 18:00:00 IDT 2016 | Mon Jul 19 08:00:00 IDT 2010 | Sat Oct 24 18:00:00 IDT 2015
604 |  | Design for the Layout of Site Hoarding | Mon Jul 19 08:00:00 IDT 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Oct 12 18:00:00 IST 2010
605 | TASK_DEPENDENT | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TASK_DEPENDENT | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TASK_DEPENDENT | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TASK_DEPENDENT | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
609 |  | Design for the Layout of Engineer's Site Accommodation | Wed Oct 13 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Wed Oct 13 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011
610 | TASK_DEPENDENT | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TASK_DEPENDENT | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TASK_DEPENDENT | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TASK_DEPENDENT | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
614 |  | Temporary Diversion Scheme - Wong Toi Shan Shan Tsuen Road | Mon Jan 10 08:00:00 IST 2011 | Thu May 26 18:00:00 IDT 2011 | Mon Jan 10 08:00:00 IST 2011 | Thu May 26 18:00:00 IDT 2011
615 | TASK_DEPENDENT | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TASK_DEPENDENT | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TASK_DEPENDENT | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TASK_DEPENDENT | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TASK_DEPENDENT | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
620 |  | Temporary Diversion Scheme - Kam Tin River | Thu Feb 24 08:00:00 IST 2011 | Thu Jun 23 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Jun 23 18:00:00 IDT 2011
621 | TASK_DEPENDENT | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TASK_DEPENDENT | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TASK_DEPENDENT | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TASK_DEPENDENT | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TASK_DEPENDENT | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
626 |  | Retaining Wall Reprovisioning Works | Wed Sep 23 08:00:00 IDT 2015 | Sat Apr 30 18:00:00 IDT 2016 | Mon Jun 01 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015
627 | TASK_DEPENDENT | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TASK_DEPENDENT | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TASK_DEPENDENT | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TASK_DEPENDENT | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TASK_DEPENDENT | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TASK_DEPENDENT | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TASK_DEPENDENT | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TASK_DEPENDENT | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TASK_DEPENDENT | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
636 |  | Design for Barging Point Structures and Associated Facilities | Wed Nov 30 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Nov 30 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012
637 | TASK_DEPENDENT | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TASK_DEPENDENT | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TASK_DEPENDENT | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TASK_DEPENDENT | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TASK_DEPENDENT | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TASK_DEPENDENT | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TASK_DEPENDENT | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TASK_DEPENDENT | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TASK_DEPENDENT | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TASK_DEPENDENT | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TASK_DEPENDENT | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TASK_DEPENDENT | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
649 |  | North Tunnel | Mon Jul 19 08:00:00 IDT 2010 | Wed Mar 29 18:00:00 IDT 2017 | Mon Jul 19 08:00:00 IDT 2010
650 |  | North Lanuching Shaft (Box 7A) | Mon Dec 06 08:00:00 IST 2010 | Fri Nov 18 18:00:00 IST 2016 | Mon Dec 06 08:00:00 IST 2010 | Fri Nov 11 18:00:00 IST 2016
651 |  | D-Wall | Mon Dec 06 08:00:00 IST 2010 | Thu Dec 15 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Thu Dec 15 18:00:00 IST 2011
652 | TASK_DEPENDENT | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TASK_DEPENDENT | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TASK_DEPENDENT | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TASK_DEPENDENT | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TASK_DEPENDENT | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
657 |  | Excavation and Lateral Support | Thu Dec 01 08:00:00 IST 2011 | Thu May 31 18:00:00 IDT 2012 | Thu Dec 01 08:00:00 IST 2011 | Thu May 31 18:00:00 IDT 2012
658 | TASK_DEPENDENT | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TASK_DEPENDENT | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TASK_DEPENDENT | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TASK_DEPENDENT | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TASK_DEPENDENT | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TASK_DEPENDENT | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TASK_DEPENDENT | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TASK_DEPENDENT | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TASK_DEPENDENT | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TASK_DEPENDENT | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TASK_DEPENDENT | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
669 | FINISH_MILESTONE | Handover to TBM Team | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
670 |  | Structure | Sat Dec 06 08:00:00 IST 2014 | Wed Aug 17 18:00:00 IDT 2016 | Fri Dec 05 08:00:00 IST 2014 | Sat Jun 18 18:00:00 IDT 2016
671 |  | Southbound (Down Track) | Sat Dec 06 08:00:00 IST 2014 | Fri Mar 04 18:00:00 IST 2016 | Fri Dec 05 08:00:00 IST 2014 | Mon Nov 30 18:00:00 IST 2015
672 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TASK_DEPENDENT | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TASK_DEPENDENT | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TASK_DEPENDENT | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TASK_DEPENDENT | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TASK_DEPENDENT | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TASK_DEPENDENT | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TASK_DEPENDENT | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TASK_DEPENDENT | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TASK_DEPENDENT | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TASK_DEPENDENT | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TASK_DEPENDENT | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
689 |  | Northbound (Up Track) | Fri May 20 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016
690 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TASK_DEPENDENT | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TASK_DEPENDENT | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TASK_DEPENDENT | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TASK_DEPENDENT | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TASK_DEPENDENT | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TASK_DEPENDENT | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TASK_DEPENDENT | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TASK_DEPENDENT | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TASK_DEPENDENT | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TASK_DEPENDENT | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TASK_DEPENDENT | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TASK_DEPENDENT | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
708 |  | Backfilling | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Nov 11 18:00:00 IST 2016
709 | TASK_DEPENDENT | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TASK_DEPENDENT | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TASK_DEPENDENT | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TASK_DEPENDENT | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TASK_DEPENDENT | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TASK_DEPENDENT | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TASK_DEPENDENT | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
716 |  | Cut and Cover Tunnel | Mon Dec 06 08:00:00 IST 2010 | Wed Mar 29 18:00:00 IDT 2017 | Mon Dec 06 08:00:00 IST 2010
717 |  | Box 7B | Mon Dec 06 08:00:00 IST 2010 | Wed Jun 01 18:00:00 IDT 2016 | Mon Dec 06 08:00:00 IST 2010 | Thu May 05 18:00:00 IDT 2016
718 |  | D- Wall Construction | Mon Dec 06 08:00:00 IST 2010 | Mon Nov 21 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Nov 21 18:00:00 IST 2011
719 | TASK_DEPENDENT | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TASK_DEPENDENT | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TASK_DEPENDENT | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TASK_DEPENDENT | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
723 |  | Excavation and Lateral Support | Tue Nov 29 08:00:00 IST 2011 | Thu Jul 12 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Thu Jul 12 18:00:00 IDT 2012
724 | TASK_DEPENDENT | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TASK_DEPENDENT | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TASK_DEPENDENT | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TASK_DEPENDENT | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
728 |  | Structure | Mon Jun 04 08:00:00 IDT 2012 | Wed Jun 01 18:00:00 IDT 2016 | Mon Jun 04 18:00:00 IDT 2012 | Thu May 05 18:00:00 IDT 2016
729 | TASK_DEPENDENT | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TASK_DEPENDENT | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TASK_DEPENDENT | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
732 |  | Backfilling | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012
733 | TASK_DEPENDENT | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
734 |  | Box 6A | Sat Sep 01 08:00:00 IDT 2012 | Wed Jul 13 18:00:00 IDT 2016 | Sat Sep 01 08:00:00 IDT 2012
735 |  | Excavation and Lateral Support | Sat Sep 01 08:00:00 IDT 2012 | Sat Sep 28 18:00:00 IDT 2013 | Sat Sep 01 08:00:00 IDT 2012 | Sat Sep 21 18:00:00 IDT 2013
736 | TASK_DEPENDENT | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TASK_DEPENDENT | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TASK_DEPENDENT | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TASK_DEPENDENT | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TASK_DEPENDENT | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TASK_DEPENDENT | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TASK_DEPENDENT | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TASK_DEPENDENT | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TASK_DEPENDENT | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TASK_DEPENDENT | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
746 |  | Structure | Fri Oct 11 08:00:00 IDT 2013 | Wed Mar 18 18:00:00 IST 2015 | Mon Sep 23 08:00:00 IDT 2013
747 |  | Bay 6 | Fri Nov 01 08:00:00 IST 2013 | Wed Mar 18 18:00:00 IST 2015 | Sat Sep 28 08:00:00 IDT 2013
748 |  | Southbound (Down Track)
749 |  | Northbound (Up Track) | Fri Nov 01 08:00:00 IST 2013 | Wed Mar 18 18:00:00 IST 2015 | Sat Sep 28 08:00:00 IDT 2013 | Fri Oct 02 18:00:00 IDT 2015
750 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TASK_DEPENDENT | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TASK_DEPENDENT | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TASK_DEPENDENT | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TASK_DEPENDENT | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TASK_DEPENDENT | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TASK_DEPENDENT | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TASK_DEPENDENT | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TASK_DEPENDENT | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TASK_DEPENDENT | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TASK_DEPENDENT | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TASK_DEPENDENT | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
767 |  | Central Base Slab
768 |  | Bay 7B | Fri Nov 01 08:00:00 IST 2013 | Wed Mar 18 18:00:00 IST 2015 | Sat Sep 28 08:00:00 IDT 2013 | Fri Oct 02 18:00:00 IDT 2015
769 |  | Southbound (Down Track) | Fri Nov 01 08:00:00 IST 2013 | Sat May 31 18:00:00 IDT 2014 | Sat Sep 28 08:00:00 IDT 2013 | Sat May 31 18:00:00 IDT 2014
770 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TASK_DEPENDENT | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TASK_DEPENDENT | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TASK_DEPENDENT | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TASK_DEPENDENT | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TASK_DEPENDENT | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TASK_DEPENDENT | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TASK_DEPENDENT | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TASK_DEPENDENT | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TASK_DEPENDENT | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TASK_DEPENDENT | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TASK_DEPENDENT | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
787 |  | Northbound (Up Track) | Fri Nov 01 08:00:00 IST 2013 | Wed Mar 18 18:00:00 IST 2015 | Sat Sep 28 08:00:00 IDT 2013 | Fri Oct 02 18:00:00 IDT 2015
788 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TASK_DEPENDENT | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TASK_DEPENDENT | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TASK_DEPENDENT | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TASK_DEPENDENT | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TASK_DEPENDENT | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TASK_DEPENDENT | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TASK_DEPENDENT | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TASK_DEPENDENT | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TASK_DEPENDENT | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TASK_DEPENDENT | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TASK_DEPENDENT | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
805 |  | Central Base Slab | Fri Nov 01 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013
806 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TASK_DEPENDENT | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TASK_DEPENDENT | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TASK_DEPENDENT | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TASK_DEPENDENT | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TASK_DEPENDENT | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
813 |  | Bay 8 | Fri Nov 01 08:00:00 IST 2013 | Thu Mar 12 18:00:00 IST 2015 | Mon Oct 07 08:00:00 IDT 2013 | Thu Mar 26 18:00:00 IST 2015
814 |  | Southbound (Down Track) | Fri Nov 01 08:00:00 IST 2013 | Mon May 26 18:00:00 IDT 2014 | Mon Oct 07 08:00:00 IDT 2013 | Mon May 26 18:00:00 IDT 2014
815 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TASK_DEPENDENT | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TASK_DEPENDENT | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TASK_DEPENDENT | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TASK_DEPENDENT | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TASK_DEPENDENT | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TASK_DEPENDENT | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TASK_DEPENDENT | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TASK_DEPENDENT | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TASK_DEPENDENT | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
832 |  | Northbound (Up Track) | Fri Nov 01 08:00:00 IST 2013 | Thu Mar 12 18:00:00 IST 2015 | Mon Oct 07 08:00:00 IDT 2013 | Thu Mar 26 18:00:00 IST 2015
833 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TASK_DEPENDENT | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TASK_DEPENDENT | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TASK_DEPENDENT | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TASK_DEPENDENT | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TASK_DEPENDENT | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TASK_DEPENDENT | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TASK_DEPENDENT | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TASK_DEPENDENT | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TASK_DEPENDENT | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TASK_DEPENDENT | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
850 |  | Central Base Slab | Tue Nov 12 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013
851 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TASK_DEPENDENT | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TASK_DEPENDENT | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TASK_DEPENDENT | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TASK_DEPENDENT | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TASK_DEPENDENT | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TASK_DEPENDENT | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
858 |  | Bay 9 | Fri Nov 01 08:00:00 IST 2013 | Thu Mar 12 18:00:00 IST 2015 | Sat Oct 19 08:00:00 IDT 2013 | Thu Mar 26 18:00:00 IST 2015
859 |  | Southbound (Down Track) | Fri Nov 15 08:00:00 IST 2013 | Tue May 20 18:00:00 IDT 2014 | Sat Oct 19 08:00:00 IDT 2013 | Tue May 20 18:00:00 IDT 2014
860 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TASK_DEPENDENT | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TASK_DEPENDENT | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TASK_DEPENDENT | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TASK_DEPENDENT | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TASK_DEPENDENT | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TASK_DEPENDENT | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TASK_DEPENDENT | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TASK_DEPENDENT | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TASK_DEPENDENT | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
877 |  | Northbound (Up Track) | Fri Nov 01 08:00:00 IST 2013 | Thu Mar 12 18:00:00 IST 2015 | Sat Oct 19 08:00:00 IDT 2013 | Thu Mar 26 18:00:00 IST 2015
878 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TASK_DEPENDENT | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TASK_DEPENDENT | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TASK_DEPENDENT | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TASK_DEPENDENT | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TASK_DEPENDENT | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TASK_DEPENDENT | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TASK_DEPENDENT | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TASK_DEPENDENT | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TASK_DEPENDENT | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TASK_DEPENDENT | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
895 |  | Central Base Slab | Mon Nov 18 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 29 18:00:00 IST 2013
896 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TASK_DEPENDENT | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TASK_DEPENDENT | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TASK_DEPENDENT | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TASK_DEPENDENT | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TASK_DEPENDENT | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TASK_DEPENDENT | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
903 |  | Bay 10 | Fri Nov 15 08:00:00 IST 2013 | Fri Mar 06 18:00:00 IST 2015 | Thu Oct 03 08:00:00 IDT 2013 | Fri Mar 20 18:00:00 IST 2015
904 |  | Southbound (Down Track) | Fri Nov 15 08:00:00 IST 2013 | Wed May 14 18:00:00 IDT 2014 | Thu Oct 03 08:00:00 IDT 2013 | Wed May 14 18:00:00 IDT 2014
905 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TASK_DEPENDENT | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TASK_DEPENDENT | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TASK_DEPENDENT | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TASK_DEPENDENT | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TASK_DEPENDENT | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TASK_DEPENDENT | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TASK_DEPENDENT | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TASK_DEPENDENT | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TASK_DEPENDENT | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TASK_DEPENDENT | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TASK_DEPENDENT | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
922 |  | Northbound (Up Track) | Fri Nov 29 08:00:00 IST 2013 | Fri Mar 06 18:00:00 IST 2015 | Thu Oct 03 08:00:00 IDT 2013 | Fri Mar 20 18:00:00 IST 2015
923 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TASK_DEPENDENT | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TASK_DEPENDENT | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TASK_DEPENDENT | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TASK_DEPENDENT | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TASK_DEPENDENT | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TASK_DEPENDENT | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TASK_DEPENDENT | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TASK_DEPENDENT | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TASK_DEPENDENT | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TASK_DEPENDENT | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
940 |  | Central Base Slab | Fri Dec 06 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013
941 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TASK_DEPENDENT | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TASK_DEPENDENT | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TASK_DEPENDENT | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TASK_DEPENDENT | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TASK_DEPENDENT | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
948 |  | Bay 11 | Fri Oct 11 08:00:00 IDT 2013 | Fri Mar 06 18:00:00 IST 2015 | Mon Sep 23 08:00:00 IDT 2013 | Fri Mar 20 18:00:00 IST 2015
949 |  | Southbound (Down Track) | Fri Nov 29 08:00:00 IST 2013 | Thu May 08 18:00:00 IDT 2014 | Mon Sep 23 08:00:00 IDT 2013 | Thu May 08 18:00:00 IDT 2014
950 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TASK_DEPENDENT | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TASK_DEPENDENT | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TASK_DEPENDENT | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TASK_DEPENDENT | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TASK_DEPENDENT | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TASK_DEPENDENT | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TASK_DEPENDENT | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TASK_DEPENDENT | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TASK_DEPENDENT | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TASK_DEPENDENT | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TASK_DEPENDENT | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
967 |  | Northbound (Up Track) | Thu Oct 31 08:00:00 IST 2013 | Fri Mar 06 18:00:00 IST 2015 | Mon Sep 23 08:00:00 IDT 2013 | Fri Mar 20 18:00:00 IST 2015
968 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TASK_DEPENDENT | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TASK_DEPENDENT | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TASK_DEPENDENT | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TASK_DEPENDENT | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TASK_DEPENDENT | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TASK_DEPENDENT | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TASK_DEPENDENT | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TASK_DEPENDENT | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TASK_DEPENDENT | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TASK_DEPENDENT | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TASK_DEPENDENT | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TASK_DEPENDENT | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
985 |  | Central Base Slab | Fri Oct 11 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013
986 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TASK_DEPENDENT | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TASK_DEPENDENT | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TASK_DEPENDENT | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TASK_DEPENDENT | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TASK_DEPENDENT | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
993 |  | Backfilling | Tue Dec 31 08:00:00 IST 2013 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 31 08:00:00 IST 2013 | Mon Jul 18 18:00:00 IDT 2016
994 | TASK_DEPENDENT | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TASK_DEPENDENT | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TASK_DEPENDENT | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TASK_DEPENDENT | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TASK_DEPENDENT | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TASK_DEPENDENT | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TASK_DEPENDENT | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1001 |  | Box 6B | Tue Mar 01 08:00:00 IST 2011 | Wed May 21 18:00:00 IDT 2014 | Tue Mar 01 08:00:00 IST 2011 | Mon Dec 30 18:00:00 IST 2013
1002 |  | D- Wall Construction | Tue Mar 01 08:00:00 IST 2011 | Fri Aug 31 18:00:00 IDT 2012 | Tue Mar 01 08:00:00 IST 2011 | Fri Aug 31 18:00:00 IDT 2012
1003 | TASK_DEPENDENT | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TASK_DEPENDENT | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TASK_DEPENDENT | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TASK_DEPENDENT | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1007 |  | Excavation and Lateral Support | Sat Sep 01 08:00:00 IDT 2012 | Sat Jun 15 18:00:00 IDT 2013 | Sat Sep 01 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012
1008 | TASK_DEPENDENT | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TASK_DEPENDENT | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TASK_DEPENDENT | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TASK_DEPENDENT | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TASK_DEPENDENT | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TASK_DEPENDENT | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TASK_DEPENDENT | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TASK_DEPENDENT | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TASK_DEPENDENT | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TASK_DEPENDENT | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1018 |  | Structure | Sat Jun 01 08:00:00 IDT 2013 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 30 18:00:00 IST 2013
1019 |  | Bay 12 | Sat Jun 08 08:00:00 IDT 2013 | Thu May 15 18:00:00 IDT 2014 | Mon Dec 17 08:00:00 IST 2012 | Sat Dec 21 18:00:00 IST 2013
1020 |  | Base Slab | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013
1021 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TASK_DEPENDENT | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TASK_DEPENDENT | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TASK_DEPENDENT | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TASK_DEPENDENT | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TASK_DEPENDENT | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1031 |  | Southbound | Sat Jun 08 08:00:00 IDT 2013 | Fri Feb 14 18:00:00 IST 2014 | Tue Jan 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013
1032 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TASK_DEPENDENT | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TASK_DEPENDENT | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TASK_DEPENDENT | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1041 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Thu May 15 18:00:00 IDT 2014 | Fri Jan 18 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013
1042 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TASK_DEPENDENT | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TASK_DEPENDENT | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1051 |  | Bay 13 | Sat Jun 01 08:00:00 IDT 2013 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 30 18:00:00 IST 2013
1052 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013
1053 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TASK_DEPENDENT | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TASK_DEPENDENT | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TASK_DEPENDENT | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TASK_DEPENDENT | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1063 |  | Southbound | Sat Jun 01 08:00:00 IDT 2013 | Tue Feb 18 18:00:00 IST 2014 | Tue Jan 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013
1064 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TASK_DEPENDENT | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TASK_DEPENDENT | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TASK_DEPENDENT | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TASK_DEPENDENT | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1073 |  | Northbound | Sat Jun 01 08:00:00 IDT 2013 | Wed May 21 18:00:00 IDT 2014 | Fri Jan 18 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013
1074 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TASK_DEPENDENT | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TASK_DEPENDENT | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1083 |  | Backfilling | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013
1084 | TASK_DEPENDENT | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TASK_DEPENDENT | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TASK_DEPENDENT | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1087 |  | East Culvert | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 18 18:00:00 IDT 2014 | Fri Mar 01 08:00:00 IST 2013 | Fri Jun 27 18:00:00 IDT 2014
1088 | TASK_DEPENDENT | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TASK_DEPENDENT | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TASK_DEPENDENT | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TASK_DEPENDENT | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TASK_DEPENDENT | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TASK_DEPENDENT | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TASK_DEPENDENT | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TASK_DEPENDENT | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TASK_DEPENDENT | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1097 |  | Reinstatement and Landscaping | Thu Sep 01 08:00:00 IDT 2016 | Wed Mar 29 18:00:00 IDT 2017 | Thu Sep 01 08:00:00 IDT 2016
1098 | TASK_DEPENDENT | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TASK_DEPENDENT | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TASK_DEPENDENT | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TASK_DEPENDENT | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1102 |  | Temporary Kam Tin River Diversion | Wed Mar 16 08:00:00 IST 2011 | Fri Aug 16 18:00:00 IDT 2013 | Wed Mar 16 08:00:00 IST 2011 | Sat Jan 19 18:00:00 IST 2013
1103 |  | Stage 1 - 3 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011
1104 | TASK_DEPENDENT | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1105 |  | Stage 4 | Thu Nov 01 08:00:00 IST 2012 | Fri Jun 28 18:00:00 IDT 2013 | Thu Nov 01 08:00:00 IST 2012 | Tue Jan 08 18:00:00 IST 2013
1106 | TASK_DEPENDENT | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TASK_DEPENDENT | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TASK_DEPENDENT | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TASK_DEPENDENT | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TASK_DEPENDENT | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TASK_DEPENDENT | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TASK_DEPENDENT | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TASK_DEPENDENT | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TASK_DEPENDENT | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TASK_DEPENDENT | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TASK_DEPENDENT | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TASK_DEPENDENT | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TASK_DEPENDENT | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TASK_DEPENDENT | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1120 |  | Stage 5 | Thu Nov 01 08:00:00 IST 2012 | Fri Jul 19 18:00:00 IDT 2013 | Thu Nov 01 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013
1121 | TASK_DEPENDENT | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TASK_DEPENDENT | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TASK_DEPENDENT | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TASK_DEPENDENT | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TASK_DEPENDENT | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TASK_DEPENDENT | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TASK_DEPENDENT | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TASK_DEPENDENT | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TASK_DEPENDENT | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TASK_DEPENDENT | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TASK_DEPENDENT | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TASK_DEPENDENT | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1133 |  | Stage 6 | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013
1134 | TASK_DEPENDENT | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TASK_DEPENDENT | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TASK_DEPENDENT | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TASK_DEPENDENT | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1138 |  | Kam Tin River Reinstatement
1139 |  | TBM Bored Tunnel (ERS to Tai Kong Po) | Mon Jul 19 08:00:00 IDT 2010 | Thu May 19 18:00:00 IDT 2016 | Mon Jul 19 08:00:00 IDT 2010 | Tue May 24 18:00:00 IDT 2016
1140 |  | Preliminaries | Mon Jul 19 08:00:00 IDT 2010 | Tue Dec 03 18:00:00 IST 2013 | Mon Jul 19 08:00:00 IDT 2010 | Mon Dec 02 18:00:00 IST 2013
1141 | TASK_DEPENDENT | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TASK_DEPENDENT | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TASK_DEPENDENT | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TASK_DEPENDENT | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TASK_DEPENDENT | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TASK_DEPENDENT | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TASK_DEPENDENT | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TASK_DEPENDENT | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TASK_DEPENDENT | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TASK_DEPENDENT | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TASK_DEPENDENT | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TASK_DEPENDENT | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TASK_DEPENDENT | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TASK_DEPENDENT | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TASK_DEPENDENT | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TASK_DEPENDENT | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TASK_DEPENDENT | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TASK_DEPENDENT | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TASK_DEPENDENT | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TASK_DEPENDENT | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TASK_DEPENDENT | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1162 |  | Southbound CH122+369 to CH123+340 (Down track) 878m | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 13 18:00:00 IST 2015 | Fri Jun 01 08:00:00 IDT 2012 | Fri Jul 17 18:00:00 IDT 2015
1163 | TASK_DEPENDENT | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TASK_DEPENDENT | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TASK_DEPENDENT | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TASK_DEPENDENT | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TASK_DEPENDENT | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TASK_DEPENDENT | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TASK_DEPENDENT | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TASK_DEPENDENT | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TASK_DEPENDENT | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TASK_DEPENDENT | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TASK_DEPENDENT | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TASK_DEPENDENT | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TASK_DEPENDENT | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TASK_DEPENDENT | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TASK_DEPENDENT | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TASK_DEPENDENT | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1179 |  | Northbound CH122+506 to CH123+384 (Up track) 878m | Mon Oct 06 13:00:00 IDT 2014 | Thu May 19 18:00:00 IDT 2016 | Sat Oct 04 08:00:00 IDT 2014 | Tue May 24 18:00:00 IDT 2016
1180 | TASK_DEPENDENT | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TASK_DEPENDENT | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TASK_DEPENDENT | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TASK_DEPENDENT | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TASK_DEPENDENT | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TASK_DEPENDENT | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TASK_DEPENDENT | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TASK_DEPENDENT | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TASK_DEPENDENT | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TASK_DEPENDENT | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TASK_DEPENDENT | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TASK_DEPENDENT | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TASK_DEPENDENT | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TASK_DEPENDENT | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TASK_DEPENDENT | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TASK_DEPENDENT | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TASK_DEPENDENT | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1197 |  | Cross Passenges | Thu Jan 02 08:00:00 IST 2014 | Thu Feb 25 18:00:00 IST 2016 | Thu Jan 02 08:00:00 IST 2014 | Sat Feb 06 18:00:00 IST 2016
1198 |  | CP26 | Thu Apr 10 08:00:00 IDT 2014 | Thu Feb 25 18:00:00 IST 2016 | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 06 18:00:00 IST 2016
1199 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TASK_DEPENDENT | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TASK_DEPENDENT | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TASK_DEPENDENT | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TASK_DEPENDENT | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TASK_DEPENDENT | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TASK_DEPENDENT | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TASK_DEPENDENT | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TASK_DEPENDENT | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TASK_DEPENDENT | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TASK_DEPENDENT | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TASK_DEPENDENT | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TASK_DEPENDENT | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1217 |  | CP27 | Tue Mar 11 08:00:00 IST 2014 | Wed Dec 16 18:00:00 IST 2015 | Thu Jan 02 08:00:00 IST 2014 | Thu Nov 05 18:00:00 IST 2015
1218 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TASK_DEPENDENT | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TASK_DEPENDENT | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TASK_DEPENDENT | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TASK_DEPENDENT | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TASK_DEPENDENT | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TASK_DEPENDENT | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TASK_DEPENDENT | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TASK_DEPENDENT | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TASK_DEPENDENT | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TASK_DEPENDENT | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TASK_DEPENDENT | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TASK_DEPENDENT | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1236 |  | CP28 | Thu Jan 02 08:00:00 IST 2014 | Wed Dec 16 18:00:00 IST 2015 | Thu Jan 02 08:00:00 IST 2014 | Thu Nov 05 18:00:00 IST 2015
1237 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TASK_DEPENDENT | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TASK_DEPENDENT | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TASK_DEPENDENT | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TASK_DEPENDENT | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TASK_DEPENDENT | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TASK_DEPENDENT | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TASK_DEPENDENT | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TASK_DEPENDENT | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TASK_DEPENDENT | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TASK_DEPENDENT | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TASK_DEPENDENT | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TASK_DEPENDENT | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TASK_DEPENDENT | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1255 |  | South Tunnel | Mon Mar 21 08:00:00 IST 2011 | Sat Sep 02 18:00:00 IDT 2017 | Mon Mar 21 08:00:00 IST 2011
1256 |  | South Lanuching Shaft | Mon Apr 18 08:00:00 IDT 2011 | Tue May 17 18:00:00 IDT 2016 | Mon Apr 18 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2016
1257 |  | D-Wall | Mon Apr 18 08:00:00 IDT 2011 | Sat Feb 16 18:00:00 IST 2013 | Mon Apr 18 08:00:00 IDT 2011 | Thu Mar 21 18:00:00 IST 2013
1258 | TASK_DEPENDENT | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TASK_DEPENDENT | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TASK_DEPENDENT | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TASK_DEPENDENT | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TASK_DEPENDENT | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1263 |  | Excavation and Lateral Support | Fri May 18 08:00:00 IDT 2012 | Fri Aug 16 18:00:00 IDT 2013 | Fri May 18 08:00:00 IDT 2012 | Wed Apr 24 18:00:00 IDT 2013
1264 | TASK_DEPENDENT | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TASK_DEPENDENT | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TASK_DEPENDENT | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TASK_DEPENDENT | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TASK_DEPENDENT | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TASK_DEPENDENT | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TASK_DEPENDENT | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TASK_DEPENDENT | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TASK_DEPENDENT | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TASK_DEPENDENT | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TASK_DEPENDENT | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TASK_DEPENDENT | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TASK_DEPENDENT | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TASK_DEPENDENT | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TASK_DEPENDENT | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TASK_DEPENDENT | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TASK_DEPENDENT | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TASK_DEPENDENT | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TASK_DEPENDENT | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1283 | START_MILESTONE | Handover to TBM's Team | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 08:00:00 IST 2012 |  | COMPLETED
1284 |  | Structure (Bay 21) | Fri Aug 08 08:00:00 IDT 2014 | Fri Jan 29 18:00:00 IST 2016 | Thu Jul 17 08:00:00 IDT 2014 | Mon Feb 01 18:00:00 IST 2016
1285 |  | Southbound (Down Track) | Fri Aug 08 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Jul 17 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014
1286 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TASK_DEPENDENT | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TASK_DEPENDENT | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TASK_DEPENDENT | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TASK_DEPENDENT | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TASK_DEPENDENT | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TASK_DEPENDENT | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TASK_DEPENDENT | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TASK_DEPENDENT | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TASK_DEPENDENT | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TASK_DEPENDENT | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TASK_DEPENDENT | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TASK_DEPENDENT | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1303 |  | Northbound (Up Track) | Tue Nov 10 08:00:00 IST 2015 | Fri Jan 29 18:00:00 IST 2016 | Mon Oct 19 08:00:00 IDT 2015 | Mon Feb 01 18:00:00 IST 2016
1304 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TASK_DEPENDENT | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TASK_DEPENDENT | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TASK_DEPENDENT | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TASK_DEPENDENT | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TASK_DEPENDENT | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TASK_DEPENDENT | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TASK_DEPENDENT | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TASK_DEPENDENT | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TASK_DEPENDENT | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TASK_DEPENDENT | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TASK_DEPENDENT | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TASK_DEPENDENT | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1321 |  | Backfilling | Tue Feb 02 08:00:00 IST 2016 | Tue May 17 18:00:00 IDT 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Jun 01 18:00:00 IDT 2016
1322 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TASK_DEPENDENT | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TASK_DEPENDENT | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TASK_DEPENDENT | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TASK_DEPENDENT | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TASK_DEPENDENT | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TASK_DEPENDENT | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TASK_DEPENDENT | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TASK_DEPENDENT | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1331 |  | South Cut and Cover Tunnel | Tue Jul 12 08:00:00 IDT 2011 | Tue Nov 24 18:00:00 IST 2015 | Tue Jul 12 08:00:00 IDT 2011 | Tue Oct 13 18:00:00 IDT 2015
1332 |  | D-Wall | Tue Jul 12 08:00:00 IDT 2011 | Thu May 17 18:00:00 IDT 2012 | Tue Jul 12 08:00:00 IDT 2011 | Thu May 17 18:00:00 IDT 2012
1333 | TASK_DEPENDENT | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TASK_DEPENDENT | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TASK_DEPENDENT | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1336 |  | Excavation and Lateral Support | Fri May 18 08:00:00 IDT 2012 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 18 08:00:00 IDT 2012 | Sat Feb 16 18:00:00 IST 2013
1337 | TASK_DEPENDENT | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TASK_DEPENDENT | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TASK_DEPENDENT | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TASK_DEPENDENT | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TASK_DEPENDENT | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TASK_DEPENDENT | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TASK_DEPENDENT | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TASK_DEPENDENT | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TASK_DEPENDENT | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TASK_DEPENDENT | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TASK_DEPENDENT | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TASK_DEPENDENT | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TASK_DEPENDENT | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TASK_DEPENDENT | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TASK_DEPENDENT | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TASK_DEPENDENT | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1353 |  | Structure | Mon Nov 12 08:00:00 IST 2012 | Tue Nov 24 18:00:00 IST 2015 | Mon Nov 12 08:00:00 IST 2012 | Tue Oct 13 18:00:00 IDT 2015
1354 |  | Bay 6a | Mon Nov 12 08:00:00 IST 2012 | Tue Nov 24 18:00:00 IST 2015 | Mon Nov 12 08:00:00 IST 2012 | Tue Oct 13 18:00:00 IDT 2015
1355 |  | Southbound | Mon Nov 12 08:00:00 IST 2012 | Tue Jan 13 18:00:00 IST 2015 | Mon Nov 12 08:00:00 IST 2012 | Fri Dec 05 18:00:00 IST 2014
1356 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TASK_DEPENDENT | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TASK_DEPENDENT | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TASK_DEPENDENT | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TASK_DEPENDENT | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TASK_DEPENDENT | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TASK_DEPENDENT | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TASK_DEPENDENT | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1373 |  | Northbound | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 24 18:00:00 IST 2015 | Tue Nov 13 08:00:00 IST 2012 | Tue Oct 13 18:00:00 IDT 2015
1374 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TASK_DEPENDENT | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TASK_DEPENDENT | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TASK_DEPENDENT | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TASK_DEPENDENT | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TASK_DEPENDENT | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TASK_DEPENDENT | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TASK_DEPENDENT | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TASK_DEPENDENT | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TASK_DEPENDENT | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TASK_DEPENDENT | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TASK_DEPENDENT | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1398 |  | Bay 6b | Tue Nov 27 08:00:00 IST 2012 | Fri Nov 13 18:00:00 IST 2015 | Tue Nov 27 08:00:00 IST 2012 | Sat Oct 10 18:00:00 IDT 2015
1399 |  | Southbound | Tue Nov 27 08:00:00 IST 2012 | Wed Jan 07 18:00:00 IST 2015 | Tue Nov 27 08:00:00 IST 2012 | Fri Dec 05 18:00:00 IST 2014
1400 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TASK_DEPENDENT | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TASK_DEPENDENT | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TASK_DEPENDENT | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TASK_DEPENDENT | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1417 |  | Northbound | Tue Nov 27 08:00:00 IST 2012 | Mon Sep 21 18:00:00 IDT 2015 | Tue Nov 27 08:00:00 IST 2012 | Wed Oct 07 18:00:00 IDT 2015
1418 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TASK_DEPENDENT | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TASK_DEPENDENT | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TASK_DEPENDENT | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TASK_DEPENDENT | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TASK_DEPENDENT | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TASK_DEPENDENT | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TASK_DEPENDENT | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TASK_DEPENDENT | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TASK_DEPENDENT | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TASK_DEPENDENT | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TASK_DEPENDENT | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1442 |  | Cross Passage | Sat Jun 01 08:00:00 IDT 2013 | Fri Nov 13 18:00:00 IST 2015 | Tue Nov 27 08:00:00 IST 2012 | Sat Oct 10 18:00:00 IDT 2015
1443 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TASK_DEPENDENT | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TASK_DEPENDENT | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TASK_DEPENDENT | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TASK_DEPENDENT | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TASK_DEPENDENT | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1459 |  | Bay 5a | Sat Jun 01 08:00:00 IDT 2013 | Wed Sep 09 18:00:00 IDT 2015 | Thu Dec 13 08:00:00 IST 2012 | Mon Oct 05 18:00:00 IDT 2015
1460 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013
1461 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TASK_DEPENDENT | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TASK_DEPENDENT | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TASK_DEPENDENT | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TASK_DEPENDENT | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TASK_DEPENDENT | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TASK_DEPENDENT | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1472 |  | Southbound | Sat Jun 01 08:00:00 IDT 2013 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 29 08:00:00 IST 2012 | Wed Dec 31 18:00:00 IST 2014
1473 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TASK_DEPENDENT | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TASK_DEPENDENT | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TASK_DEPENDENT | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1482 |  | Northbound | Sat Jun 01 08:00:00 IDT 2013 | Wed Sep 09 18:00:00 IDT 2015 | Thu Dec 27 08:00:00 IST 2012 | Mon Oct 05 18:00:00 IDT 2015
1483 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TASK_DEPENDENT | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TASK_DEPENDENT | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TASK_DEPENDENT | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1492 |  | Bay 5b | Wed Nov 21 08:00:00 IST 2012 | Thu Sep 03 18:00:00 IDT 2015 | Wed Nov 21 08:00:00 IST 2012 | Sat Oct 03 18:00:00 IDT 2015
1493 |  | Base Slab | Wed Nov 21 08:00:00 IST 2012 | Tue Jun 25 18:00:00 IDT 2013 | Wed Nov 21 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012
1494 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TASK_DEPENDENT | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TASK_DEPENDENT | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TASK_DEPENDENT | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TASK_DEPENDENT | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TASK_DEPENDENT | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1505 |  | Southbound | Sat Jun 01 08:00:00 IDT 2013 | Tue Dec 23 18:00:00 IST 2014 | Mon Dec 24 08:00:00 IST 2012 | Tue Dec 23 18:00:00 IST 2014
1506 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TASK_DEPENDENT | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1515 |  | Northbound | Sat Jun 01 08:00:00 IDT 2013 | Thu Sep 03 18:00:00 IDT 2015 | Sat Jan 05 08:00:00 IST 2013 | Sat Oct 03 18:00:00 IDT 2015
1516 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TASK_DEPENDENT | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1525 |  | Bay 4a | Sat Jun 01 08:00:00 IDT 2013 | Fri Aug 28 18:00:00 IDT 2015 | Thu Dec 20 08:00:00 IST 2012 | Sat Oct 03 18:00:00 IDT 2015
1526 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013
1527 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TASK_DEPENDENT | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TASK_DEPENDENT | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TASK_DEPENDENT | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TASK_DEPENDENT | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TASK_DEPENDENT | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TASK_DEPENDENT | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1538 |  | Southbound | Sat Jun 08 08:00:00 IDT 2013 | Wed Dec 17 18:00:00 IST 2014 | Wed Mar 06 08:00:00 IST 2013 | Wed Dec 17 18:00:00 IST 2014
1539 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1548 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Fri Aug 28 18:00:00 IDT 2015 | Mon Feb 18 08:00:00 IST 2013 | Sat Oct 03 18:00:00 IDT 2015
1549 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1558 |  | Bay 4b | Sat Jun 01 08:00:00 IDT 2013 | Sat Aug 22 18:00:00 IDT 2015 | Mon Jan 14 08:00:00 IST 2013 | Fri Oct 02 18:00:00 IDT 2015
1559 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013
1560 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TASK_DEPENDENT | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TASK_DEPENDENT | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TASK_DEPENDENT | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TASK_DEPENDENT | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1571 |  | Southbound | Sat Jun 08 08:00:00 IDT 2013 | Thu Dec 11 18:00:00 IST 2014 | Wed Mar 06 08:00:00 IST 2013 | Thu Dec 11 18:00:00 IST 2014
1572 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1581 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Sat Aug 22 18:00:00 IDT 2015 | Thu Feb 21 08:00:00 IST 2013 | Fri Oct 02 18:00:00 IDT 2015
1582 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1591 |  | Bay 3a | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 17 18:00:00 IDT 2015 | Fri Jan 25 08:00:00 IST 2013 | Fri Oct 02 18:00:00 IDT 2015
1592 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013
1593 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TASK_DEPENDENT | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TASK_DEPENDENT | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TASK_DEPENDENT | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TASK_DEPENDENT | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TASK_DEPENDENT | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1604 |  | Southbound | Wed Jun 19 08:00:00 IDT 2013 | Thu Mar 13 18:00:00 IST 2014 | Sat Aug 24 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013
1605 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TASK_DEPENDENT | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TASK_DEPENDENT | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TASK_DEPENDENT | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TASK_DEPENDENT | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1614 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Mon Aug 17 18:00:00 IDT 2015 | Wed Mar 13 08:00:00 IST 2013 | Fri Oct 02 18:00:00 IDT 2015
1615 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TASK_DEPENDENT | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TASK_DEPENDENT | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1624 |  | Bay 3b | Sat Jun 01 08:00:00 IDT 2013 | Tue Aug 11 18:00:00 IDT 2015 | Mon Feb 04 08:00:00 IST 2013 | Fri Jul 31 18:00:00 IDT 2015
1625 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013
1626 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TASK_DEPENDENT | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TASK_DEPENDENT | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TASK_DEPENDENT | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TASK_DEPENDENT | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TASK_DEPENDENT | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1637 |  | Southbound | Fri Jul 12 08:00:00 IDT 2013 | Fri Mar 07 18:00:00 IST 2014 | Sat Jun 22 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013
1638 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TASK_DEPENDENT | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TASK_DEPENDENT | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1647 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Tue Aug 11 18:00:00 IDT 2015 | Thu Mar 21 08:00:00 IST 2013 | Fri Jul 31 18:00:00 IDT 2015
1648 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TASK_DEPENDENT | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TASK_DEPENDENT | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1657 |  | Approach Tunnel Roof | Thu Sep 12 08:00:00 IDT 2013 | Tue Jul 07 18:00:00 IDT 2015 | Sat Jun 22 08:00:00 IDT 2013 | Tue Jul 07 18:00:00 IDT 2015
1658 | TASK_DEPENDENT | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TASK_DEPENDENT | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TASK_DEPENDENT | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TASK_DEPENDENT | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TASK_DEPENDENT | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TASK_DEPENDENT | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1666 |  | Bay 2a | Sat Jun 01 08:00:00 IDT 2013 | Sat Apr 11 18:00:00 IDT 2015 | Sat Feb 16 08:00:00 IST 2013 | Fri Feb 27 18:00:00 IST 2015
1667 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013
1668 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TASK_DEPENDENT | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TASK_DEPENDENT | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TASK_DEPENDENT | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TASK_DEPENDENT | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TASK_DEPENDENT | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TASK_DEPENDENT | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1679 |  | Southbound | Tue Jun 25 08:00:00 IDT 2013 | Mon Feb 24 18:00:00 IST 2014 | Sat Apr 20 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013
1680 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TASK_DEPENDENT | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1689 |  | Northbound | Sat Jun 08 08:00:00 IDT 2013 | Sat Apr 11 18:00:00 IDT 2015 | Mon Apr 15 08:00:00 IDT 2013 | Fri Feb 27 18:00:00 IST 2015
1690 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1699 |  | Approach Tunnel Roof | Thu Aug 01 08:00:00 IDT 2013 | Tue Jan 14 18:00:00 IST 2014 | Thu May 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013
1700 | TASK_DEPENDENT | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TASK_DEPENDENT | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TASK_DEPENDENT | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TASK_DEPENDENT | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TASK_DEPENDENT | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TASK_DEPENDENT | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1708 |  | Bay 2b | Sat Jun 01 08:00:00 IDT 2013 | Thu Jul 10 18:00:00 IDT 2014 | Wed Feb 20 08:00:00 IST 2013 | Fri Oct 18 18:00:00 IDT 2013
1709 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Mon Jun 24 18:00:00 IDT 2013
1710 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TASK_DEPENDENT | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TASK_DEPENDENT | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TASK_DEPENDENT | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TASK_DEPENDENT | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TASK_DEPENDENT | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1721 |  | Southbound | Thu Aug 01 08:00:00 IDT 2013 | Fri Feb 14 18:00:00 IST 2014 | Wed Jun 26 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013
1722 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TASK_DEPENDENT | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1731 |  | Northbound | Thu Aug 01 08:00:00 IDT 2013 | Thu Jul 10 18:00:00 IDT 2014 | Mon Jul 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013
1732 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TASK_DEPENDENT | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TASK_DEPENDENT | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1741 |  | Approach Tunnel Roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013
1742 | TASK_DEPENDENT | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TASK_DEPENDENT | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TASK_DEPENDENT | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TASK_DEPENDENT | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TASK_DEPENDENT | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TASK_DEPENDENT | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1750 |  | Bay 1a | Sat Jun 01 08:00:00 IDT 2013 | Mon Nov 24 18:00:00 IST 2014 | Mon Mar 11 08:00:00 IST 2013 | Fri May 09 18:00:00 IDT 2014
1751 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Jun 24 18:00:00 IDT 2013
1752 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TASK_DEPENDENT | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TASK_DEPENDENT | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TASK_DEPENDENT | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TASK_DEPENDENT | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TASK_DEPENDENT | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TASK_DEPENDENT | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1763 |  | Southbound | Mon Aug 05 08:00:00 IDT 2013 | Sat Feb 08 18:00:00 IST 2014 | Wed Jun 26 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013
1764 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TASK_DEPENDENT | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1773 |  | Northbound | Wed Aug 07 08:00:00 IDT 2013 | Mon Nov 24 18:00:00 IST 2014 | Mon Jul 08 08:00:00 IDT 2013 | Fri May 09 18:00:00 IDT 2014
1774 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TASK_DEPENDENT | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TASK_DEPENDENT | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1783 |  | Approach Tunnel Roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013
1784 | TASK_DEPENDENT | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TASK_DEPENDENT | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TASK_DEPENDENT | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TASK_DEPENDENT | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TASK_DEPENDENT | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TASK_DEPENDENT | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1792 |  | Bay 1b | Sat Jun 01 08:00:00 IDT 2013 | Tue Nov 18 18:00:00 IST 2014 | Thu Feb 21 08:00:00 IST 2013 | Fri May 09 18:00:00 IDT 2014
1793 |  | Base Slab | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013
1794 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TASK_DEPENDENT | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TASK_DEPENDENT | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TASK_DEPENDENT | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TASK_DEPENDENT | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TASK_DEPENDENT | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TASK_DEPENDENT | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1805 |  | Southbound | Tue Jul 09 08:00:00 IDT 2013 | Thu Jan 30 18:00:00 IST 2014 | Fri Mar 01 08:00:00 IST 2013 | Fri Oct 18 18:00:00 IDT 2013
1806 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TASK_DEPENDENT | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1815 |  | Northbound | Thu Jul 11 08:00:00 IDT 2013 | Tue Nov 18 18:00:00 IST 2014 | Fri Mar 08 08:00:00 IST 2013 | Fri May 09 18:00:00 IDT 2014
1816 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TASK_DEPENDENT | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TASK_DEPENDENT | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TASK_DEPENDENT | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1825 |  | Approach Tunnel Roof | Mon Sep 02 08:00:00 IDT 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013
1826 | TASK_DEPENDENT | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TASK_DEPENDENT | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TASK_DEPENDENT | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TASK_DEPENDENT | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TASK_DEPENDENT | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TASK_DEPENDENT | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1834 |  | Backfilling | Sat Jun 01 08:00:00 IDT 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Oct 21 18:00:00 IDT 2013
1835 | TASK_DEPENDENT | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TASK_DEPENDENT | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TASK_DEPENDENT | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TASK_DEPENDENT | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TASK_DEPENDENT | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TASK_DEPENDENT | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1841 |  | Shunt Tunnel | Thu Nov 24 08:00:00 IST 2011 | Sat Sep 02 18:00:00 IDT 2017 | Thu Nov 24 08:00:00 IST 2011
1842 |  | D-wall | Thu Nov 24 08:00:00 IST 2011 | Sat Dec 15 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Sat Dec 08 18:00:00 IST 2012
1843 | TASK_DEPENDENT | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TASK_DEPENDENT | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TASK_DEPENDENT | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TASK_DEPENDENT | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1847 |  | Excavation and Lateral Support | Sat Jun 01 08:00:00 IDT 2013 | Sat Jan 17 18:00:00 IST 2015 | Thu Jan 03 08:00:00 IST 2013 | Tue Jun 23 18:00:00 IDT 2015
1848 | TASK_DEPENDENT | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TASK_DEPENDENT | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TASK_DEPENDENT | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TASK_DEPENDENT | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TASK_DEPENDENT | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TASK_DEPENDENT | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1854 |  | Structure | Sat Jun 01 08:00:00 IDT 2013 | Wed Nov 11 18:00:00 IST 2015 | Fri Feb 15 08:00:00 IST 2013 | Wed Nov 11 18:00:00 IST 2015
1855 |  | Bay SN1 | Fri Nov 01 08:00:00 IST 2013 | Wed Apr 09 18:00:00 IDT 2014 | Sat Oct 26 08:00:00 IDT 2013 | Fri Mar 28 18:00:00 IDT 2014
1856 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TASK_DEPENDENT | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1865 |  | Bay SN2 | Thu Nov 14 08:00:00 IST 2013 | Fri Jun 05 18:00:00 IDT 2015 | Thu Nov 14 08:00:00 IST 2013 | Fri Jun 05 18:00:00 IDT 2015
1866 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TASK_DEPENDENT | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1875 |  | Bay SN3 | Thu Nov 28 08:00:00 IST 2013 | Thu Mar 27 18:00:00 IST 2014 | Thu Nov 28 08:00:00 IST 2013 | Thu Mar 27 18:00:00 IST 2014
1876 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TASK_DEPENDENT | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TASK_DEPENDENT | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1885 |  | Bay SN4 | Fri Dec 13 08:00:00 IST 2013 | Fri Mar 21 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Fri Mar 21 18:00:00 IST 2014
1886 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TASK_DEPENDENT | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TASK_DEPENDENT | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1895 |  | Bay SN5 | Mon Dec 30 08:00:00 IST 2013 | Sat Mar 15 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Mar 15 18:00:00 IST 2014
1896 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TASK_DEPENDENT | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TASK_DEPENDENT | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1905 |  | Bay SN6 | Fri Nov 01 08:00:00 IST 2013 | Mon Mar 10 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Mon Mar 10 18:00:00 IST 2014
1906 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TASK_DEPENDENT | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TASK_DEPENDENT | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TASK_DEPENDENT | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1915 |  | Bay SN7 | Mon Jun 17 08:00:00 IDT 2013 | Mon Feb 10 18:00:00 IST 2014 | Thu May 23 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014
1916 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TASK_DEPENDENT | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TASK_DEPENDENT | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1925 |  | Bay SN8 | Sat Jun 01 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 | Fri Feb 15 08:00:00 IST 2013 | Mon Mar 03 18:00:00 IST 2014
1926 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TASK_DEPENDENT | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TASK_DEPENDENT | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1935 |  | Bay SN9 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jan 25 18:00:00 IST 2014 | Fri Feb 22 08:00:00 IST 2013 | Sat Mar 01 18:00:00 IST 2014
1936 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TASK_DEPENDENT | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TASK_DEPENDENT | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TASK_DEPENDENT | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TASK_DEPENDENT | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1945 |  | Bay SN10 | Thu Apr 02 08:00:00 IDT 2015 | Wed Nov 04 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015
1946 | TASK_DEPENDENT | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TASK_DEPENDENT | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TASK_DEPENDENT | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TASK_DEPENDENT | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TASK_DEPENDENT | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TASK_DEPENDENT | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TASK_DEPENDENT | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TASK_DEPENDENT | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TASK_DEPENDENT | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1967 |  | Bay SN11 | Thu Jul 02 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015
1968 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TASK_DEPENDENT | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TASK_DEPENDENT | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TASK_DEPENDENT | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TASK_DEPENDENT | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TASK_DEPENDENT | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TASK_DEPENDENT | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TASK_DEPENDENT | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TASK_DEPENDENT | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1988 |  | Bay SN12 | Tue May 26 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015
1989 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TASK_DEPENDENT | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TASK_DEPENDENT | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TASK_DEPENDENT | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TASK_DEPENDENT | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TASK_DEPENDENT | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TASK_DEPENDENT | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TASK_DEPENDENT | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TASK_DEPENDENT | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TASK_DEPENDENT | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TASK_DEPENDENT | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2009 |  | Bay SN13 | Sat May 23 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015
2010 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TASK_DEPENDENT | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TASK_DEPENDENT | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TASK_DEPENDENT | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TASK_DEPENDENT | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TASK_DEPENDENT | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TASK_DEPENDENT | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TASK_DEPENDENT | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TASK_DEPENDENT | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TASK_DEPENDENT | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TASK_DEPENDENT | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2030 |  | Bay SN14 | Wed May 20 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Sat Oct 03 18:00:00 IDT 2015
2031 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TASK_DEPENDENT | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TASK_DEPENDENT | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TASK_DEPENDENT | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TASK_DEPENDENT | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TASK_DEPENDENT | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TASK_DEPENDENT | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TASK_DEPENDENT | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TASK_DEPENDENT | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TASK_DEPENDENT | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TASK_DEPENDENT | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TASK_DEPENDENT | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TASK_DEPENDENT | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2051 |  | Bay SN15 | Mon Apr 13 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Oct 02 18:00:00 IDT 2015
2052 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TASK_DEPENDENT | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TASK_DEPENDENT | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TASK_DEPENDENT | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TASK_DEPENDENT | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TASK_DEPENDENT | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TASK_DEPENDENT | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TASK_DEPENDENT | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TASK_DEPENDENT | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TASK_DEPENDENT | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TASK_DEPENDENT | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TASK_DEPENDENT | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2072 |  | Bay SN16 | Fri Dec 06 08:00:00 IST 2013 | Tue Jun 10 18:00:00 IDT 2014 | Fri Nov 15 08:00:00 IST 2013 | Thu Dec 04 18:00:00 IST 2014
2073 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TASK_DEPENDENT | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TASK_DEPENDENT | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TASK_DEPENDENT | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TASK_DEPENDENT | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TASK_DEPENDENT | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TASK_DEPENDENT | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TASK_DEPENDENT | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TASK_DEPENDENT | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TASK_DEPENDENT | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TASK_DEPENDENT | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2093 |  | Bay SN17 | Thu Dec 05 08:00:00 IST 2013 | Wed Jun 04 18:00:00 IDT 2014 | Thu Oct 17 08:00:00 IDT 2013 | Wed Dec 03 18:00:00 IST 2014
2094 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TASK_DEPENDENT | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TASK_DEPENDENT | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TASK_DEPENDENT | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TASK_DEPENDENT | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TASK_DEPENDENT | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TASK_DEPENDENT | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TASK_DEPENDENT | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TASK_DEPENDENT | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TASK_DEPENDENT | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TASK_DEPENDENT | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TASK_DEPENDENT | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TASK_DEPENDENT | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TASK_DEPENDENT | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2114 |  | Bay SN18 | Fri Nov 29 08:00:00 IST 2013 | Wed May 28 18:00:00 IDT 2014 | Thu Oct 17 08:00:00 IDT 2013 | Tue Dec 02 18:00:00 IST 2014
2115 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TASK_DEPENDENT | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TASK_DEPENDENT | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TASK_DEPENDENT | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TASK_DEPENDENT | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TASK_DEPENDENT | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TASK_DEPENDENT | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TASK_DEPENDENT | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TASK_DEPENDENT | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TASK_DEPENDENT | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TASK_DEPENDENT | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TASK_DEPENDENT | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TASK_DEPENDENT | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TASK_DEPENDENT | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TASK_DEPENDENT | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2135 |  | Bay SN19 (Including Emergency Exit Point) | Sat Nov 09 08:00:00 IST 2013 | Thu Mar 19 18:00:00 IST 2015 | Thu Sep 19 08:00:00 IDT 2013 | Thu Mar 19 18:00:00 IST 2015
2136 |  | Level +10.8mPD | Sat Nov 09 08:00:00 IST 2013 | Thu May 22 18:00:00 IDT 2014 | Thu Sep 19 08:00:00 IDT 2013 | Mon Dec 01 18:00:00 IST 2014
2137 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TASK_DEPENDENT | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TASK_DEPENDENT | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TASK_DEPENDENT | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TASK_DEPENDENT | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TASK_DEPENDENT | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TASK_DEPENDENT | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TASK_DEPENDENT | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TASK_DEPENDENT | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TASK_DEPENDENT | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TASK_DEPENDENT | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TASK_DEPENDENT | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TASK_DEPENDENT | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TASK_DEPENDENT | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2151 |  | Level +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jun 20 18:00:00 IDT 2014
2152 | TASK_DEPENDENT | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TASK_DEPENDENT | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TASK_DEPENDENT | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TASK_DEPENDENT | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TASK_DEPENDENT | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TASK_DEPENDENT | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TASK_DEPENDENT | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TASK_DEPENDENT | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TASK_DEPENDENT | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TASK_DEPENDENT | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TASK_DEPENDENT | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2163 |  | Level +24.0mPD | Wed Apr 02 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Jul 03 18:00:00 IDT 2014
2164 | TASK_DEPENDENT | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TASK_DEPENDENT | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TASK_DEPENDENT | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TASK_DEPENDENT | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TASK_DEPENDENT | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TASK_DEPENDENT | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TASK_DEPENDENT | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TASK_DEPENDENT | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TASK_DEPENDENT | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TASK_DEPENDENT | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TASK_DEPENDENT | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2175 |  | Level +30.406mPD | Thu Jun 19 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014
2176 | TASK_DEPENDENT | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TASK_DEPENDENT | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TASK_DEPENDENT | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TASK_DEPENDENT | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TASK_DEPENDENT | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TASK_DEPENDENT | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TASK_DEPENDENT | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TASK_DEPENDENT | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TASK_DEPENDENT | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TASK_DEPENDENT | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TASK_DEPENDENT | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TASK_DEPENDENT | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TASK_DEPENDENT | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TASK_DEPENDENT | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TASK_DEPENDENT | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TASK_DEPENDENT | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2192 |  | Level +32.856mPD | Wed Sep 03 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014
2193 | TASK_DEPENDENT | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TASK_DEPENDENT | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TASK_DEPENDENT | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TASK_DEPENDENT | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TASK_DEPENDENT | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TASK_DEPENDENT | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TASK_DEPENDENT | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TASK_DEPENDENT | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TASK_DEPENDENT | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TASK_DEPENDENT | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TASK_DEPENDENT | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2204 |  | Level +33.576mPD | Thu Oct 16 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 | Thu Oct 16 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014
2205 | TASK_DEPENDENT | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TASK_DEPENDENT | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TASK_DEPENDENT | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TASK_DEPENDENT | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TASK_DEPENDENT | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TASK_DEPENDENT | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TASK_DEPENDENT | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2212 |  | ABWF Works | Wed Nov 05 08:00:00 IST 2014 | Thu Mar 19 18:00:00 IST 2015 | Wed Nov 05 08:00:00 IST 2014 | Thu Mar 19 18:00:00 IST 2015
2213 | TASK_DEPENDENT | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TASK_DEPENDENT | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TASK_DEPENDENT | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2216 |  | Backfilling | Tue Jul 02 08:00:00 IDT 2013 | Sat Sep 02 18:00:00 IDT 2017 | Wed Mar 27 08:00:00 IST 2013
2217 |  | Bay SN1 to SN7 | Fri Nov 29 08:00:00 IST 2013 | Tue Mar 25 18:00:00 IST 2014 | Wed Jun 26 08:00:00 IDT 2013 | Sat May 03 18:00:00 IDT 2014
2218 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TASK_DEPENDENT | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TASK_DEPENDENT | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TASK_DEPENDENT | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2222 |  | Bay SN8 to SN9 | Tue Jul 02 08:00:00 IDT 2013 | Thu Mar 06 18:00:00 IST 2014 | Wed Mar 27 08:00:00 IST 2013 | Fri May 02 18:00:00 IDT 2014
2223 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TASK_DEPENDENT | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TASK_DEPENDENT | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TASK_DEPENDENT | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TASK_DEPENDENT | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TASK_DEPENDENT | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TASK_DEPENDENT | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TASK_DEPENDENT | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2232 |  | Bay SN10 to SN15 | Fri Aug 07 08:00:00 IDT 2015 | Fri Jan 29 18:00:00 IST 2016 | Thu Jul 02 08:00:00 IDT 2015 | Fri Apr 01 18:00:00 IDT 2016
2233 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TASK_DEPENDENT | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TASK_DEPENDENT | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TASK_DEPENDENT | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TASK_DEPENDENT | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TASK_DEPENDENT | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TASK_DEPENDENT | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2242 |  | Bay SN16 to SN19 | Wed Apr 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014
2243 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TASK_DEPENDENT | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TASK_DEPENDENT | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TASK_DEPENDENT | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TASK_DEPENDENT | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TASK_DEPENDENT | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TASK_DEPENDENT | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2250 |  | Reinstatement | Mon Jun 15 08:00:00 IDT 2015 | Sat Sep 02 18:00:00 IDT 2017 | Mon Jun 01 08:00:00 IDT 2015
2251 | TASK_DEPENDENT | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TASK_DEPENDENT | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TASK_DEPENDENT | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TASK_DEPENDENT | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2255 |  | TBM Bored Tunnel (ERS to Tse Uk Tsuen) | Tue Nov 15 08:00:00 IST 2011 | Tue Jan 19 18:00:00 IST 2016 | Tue Nov 15 08:00:00 IST 2011 | Tue Jan 19 18:00:00 IST 2016
2256 |  | Preliminaries | Tue Nov 15 08:00:00 IST 2011 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 15 08:00:00 IST 2011 | Wed May 29 18:00:00 IDT 2013
2257 | START_MILESTONE | Engineer Instruction for procurement of 2nd TBM | Tue Nov 15 08:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 |  | COMPLETED
2258 | TASK_DEPENDENT | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TASK_DEPENDENT | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TASK_DEPENDENT | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TASK_DEPENDENT | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TASK_DEPENDENT | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TASK_DEPENDENT | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TASK_DEPENDENT | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TASK_DEPENDENT | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TASK_DEPENDENT | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TASK_DEPENDENT | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TASK_DEPENDENT | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TASK_DEPENDENT | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TASK_DEPENDENT | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TASK_DEPENDENT | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TASK_DEPENDENT | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2273 |  | Southbound CH124+912 TO CH125+338 (Down Track) 426m | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 15 18:00:00 IST 2014 | Mon Oct 15 08:00:00 IST 2012 | Sat Sep 06 18:00:00 IDT 2014
2274 | TASK_DEPENDENT | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TASK_DEPENDENT | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TASK_DEPENDENT | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TASK_DEPENDENT | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TASK_DEPENDENT | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TASK_DEPENDENT | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TASK_DEPENDENT | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TASK_DEPENDENT | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TASK_DEPENDENT | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TASK_DEPENDENT | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2284 |  | Northbound CH124+927 TO CH125+353 (Up Track) 426m | Tue Nov 27 08:00:00 IST 2012 | Sat Oct 24 18:00:00 IDT 2015 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 10 18:00:00 IST 2015
2285 | TASK_DEPENDENT | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TASK_DEPENDENT | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TASK_DEPENDENT | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TASK_DEPENDENT | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TASK_DEPENDENT | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TASK_DEPENDENT | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TASK_DEPENDENT | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TASK_DEPENDENT | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TASK_DEPENDENT | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TASK_DEPENDENT | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TASK_DEPENDENT | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2296 |  | Cross Passenges | Fri Aug 01 08:00:00 IDT 2014 | Tue Jan 19 18:00:00 IST 2016 | Fri Aug 01 08:00:00 IDT 2014 | Tue Jan 19 18:00:00 IST 2016
2297 |  | CP32 | Fri Aug 01 08:00:00 IDT 2014 | Tue Jan 19 18:00:00 IST 2016 | Fri Aug 01 08:00:00 IDT 2014 | Tue Jan 19 18:00:00 IST 2016
2298 | TASK_DEPENDENT | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TASK_DEPENDENT | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TASK_DEPENDENT | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TASK_DEPENDENT | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TASK_DEPENDENT | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TASK_DEPENDENT | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TASK_DEPENDENT | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TASK_DEPENDENT | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TASK_DEPENDENT | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TASK_DEPENDENT | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TASK_DEPENDENT | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TASK_DEPENDENT | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TASK_DEPENDENT | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TASK_DEPENDENT | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TASK_DEPENDENT | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TASK_DEPENDENT | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2316 |  | Tse Uk Tsuen Shaft | Mon Mar 21 08:00:00 IST 2011 | Mon Jun 19 18:00:00 IDT 2017 | Mon Mar 21 08:00:00 IST 2011
2317 |  | D-Wall | Mon Mar 21 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Mon Mar 21 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012
2318 | TASK_DEPENDENT | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TASK_DEPENDENT | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TASK_DEPENDENT | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TASK_DEPENDENT | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TASK_DEPENDENT | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2323 |  | Ground Treatment | Thu Mar 01 08:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012 | Thu Mar 01 08:00:00 IST 2012 | Wed Oct 31 18:00:00 IST 2012
2324 | TASK_DEPENDENT | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TASK_DEPENDENT | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TASK_DEPENDENT | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TASK_DEPENDENT | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2328 |  | Excavation and Lateral Support | Thu Mar 01 08:00:00 IST 2012 | Mon Sep 30 18:00:00 IDT 2013 | Thu Mar 01 08:00:00 IST 2012 | Thu Jul 11 18:00:00 IDT 2013
2329 | TASK_DEPENDENT | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TASK_DEPENDENT | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TASK_DEPENDENT | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TASK_DEPENDENT | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TASK_DEPENDENT | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TASK_DEPENDENT | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TASK_DEPENDENT | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TASK_DEPENDENT | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TASK_DEPENDENT | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TASK_DEPENDENT | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TASK_DEPENDENT | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TASK_DEPENDENT | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TASK_DEPENDENT | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2342 | START_MILESTONE | Return TUT shaft by contract 822 | Mon Aug 26 08:00:00 IDT 2013 | Mon Aug 26 08:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 08:00:00 IST 2013 |  | COMPLETED
2343 | TASK_DEPENDENT | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TASK_DEPENDENT | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2345 |  | Structure | Fri Aug 08 08:00:00 IDT 2014 | Thu Apr 14 18:00:00 IDT 2016 | Thu Aug 14 08:00:00 IDT 2014 | Wed Mar 16 18:00:00 IST 2016
2346 |  | Southbound (Down Track) | Fri Aug 08 08:00:00 IDT 2014 | Thu Dec 11 18:00:00 IST 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Dec 11 18:00:00 IST 2014
2347 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TASK_DEPENDENT | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TASK_DEPENDENT | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TASK_DEPENDENT | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TASK_DEPENDENT | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TASK_DEPENDENT | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TASK_DEPENDENT | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TASK_DEPENDENT | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TASK_DEPENDENT | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TASK_DEPENDENT | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TASK_DEPENDENT | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TASK_DEPENDENT | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TASK_DEPENDENT | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2364 |  | Northbound (Up Track) | Sat Nov 07 08:00:00 IST 2015 | Thu Apr 14 18:00:00 IDT 2016 | Sat Nov 07 08:00:00 IST 2015 | Wed Mar 16 18:00:00 IST 2016
2365 | TASK_DEPENDENT | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TASK_DEPENDENT | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TASK_DEPENDENT | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TASK_DEPENDENT | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TASK_DEPENDENT | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TASK_DEPENDENT | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TASK_DEPENDENT | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TASK_DEPENDENT | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TASK_DEPENDENT | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TASK_DEPENDENT | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TASK_DEPENDENT | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TASK_DEPENDENT | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TASK_DEPENDENT | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TASK_DEPENDENT | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TASK_DEPENDENT | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TASK_DEPENDENT | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TASK_DEPENDENT | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TASK_DEPENDENT | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TASK_DEPENDENT | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TASK_DEPENDENT | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TASK_DEPENDENT | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TASK_DEPENDENT | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TASK_DEPENDENT | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TASK_DEPENDENT | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2389 |  | Backfilling | Thu Mar 17 08:00:00 IST 2016 | Mon Oct 03 18:00:00 IDT 2016 | Tue Mar 01 08:00:00 IST 2016 | Mon Sep 19 18:00:00 IDT 2016
2390 | TASK_DEPENDENT | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TASK_DEPENDENT | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TASK_DEPENDENT | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TASK_DEPENDENT | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TASK_DEPENDENT | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TASK_DEPENDENT | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TASK_DEPENDENT | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TASK_DEPENDENT | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TASK_DEPENDENT | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TASK_DEPENDENT | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TASK_DEPENDENT | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2401 |  | Reinstatement | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016
2402 | TASK_DEPENDENT | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
2403 |  | Option 1 - Tai Lam Kok Baring Facility